## Project List
client | project | notes | project manager | Work Plan Status | # of surveyors
CEMC Cymric | WATER WELL 1 | Miller | 3
CEMC Cymric | 7-3A | Miller | 3
Chevron CY | 1Y SSP Stage 2/3 Soft Water | Miller | 3
CEMC MCK | DEL MONTE THERMAL 5 | Miller | 2
Chevron CY | Antelope Shale | Miller | 2
CEMC MWSS | F15B | Miller | 2
CEMC MWSS | Tumbador 15 | Miller | 2
CEMC MWSS | Tumbador 5 | Miller | 2
CEMC MWSS | 35U 3 Wells (BLM) | Miller | 2
CEMC MWSS | 145 | Miller | 2
CEMC MWSS | CWOD B6-2 | Miller | 2
CEMC MWSS | 51 | Miller | 2
CEMC MWSS | 502 | Miller | 3
CEMC MWSS | 307 | Miller | 3
CEMC MWSS | Buick lease Restoration | Miller | 3
CEMC MWSS | 23 (BLM) | Miller | 2
CEMC MWSS | 35G Lease Restoration | Miller
Chevron CY | 35W 8-1A | Miller | 2
Chevron CY | 36W LeaseLine | Miller | 2
Chevron CY | 1Y FEL | Miller | 2
Chevron CY | 2017 7Z 8Z | Miller | 3
CEMC Cymric | McNeal Well Abandonments | Miller | 3
Chevron CY | DEL MONTE | Miller | 3
Chevron CY | Stevens | Miller | 4
Chevron CY | MCK MT CIVIL & TILT METERS | Miller | 4
Chevron Coalinga | 23D | Miller | 4
CEMC CO | Polvadero | Miller | 2
CEMC CO | Cagel | Miller | 2
CEMC CO | 2B & 3B | Miller
CEMC CO | Pleasant Valley | Miller | 6
Chevron MWSS | Borrow Area | Miller | 2
Chevron MWSS | 31F ETCHEGOIN | Miller | 2
Chevron MWSS | Tulare 2017 | Miller | 3
Chevron CY | Corn Camp | Miller | 3
LINN | Hill So Cal Gas Line |  | 3
LINN | 21Z Accelerated Survey |  | 2
LINN | FFA Accelerated Survey |  | 2
LINN | 2017 MC BNLL |  | 2
LINN | Origami |  | 2 or 3
LINN | Homebase BNLL |  | 5
RHC (Aera) | DEHY 2 to Cymric PL | RM | 3
Dudek | High Speed Rail CP 2-3 | RM | 6 to 8
AECOM | EPC Landfill | RM | 3
Arcadis | Fellows-Taft | SA | 3
Arcadis | Tupman-Norco Tap | SA | 3
Arcadis | Fellows-Midsun | SA | 3
Arcadis | Belridge Tap | SA | 2
Arcadis | Midway-Temblor | SA | 3
Arcadis | Vedder Tap | SA | 3
Tejon Ranch |  | AP | 2 poss 4
Windwolves Preserve |  | AP | 2
Valley Water | McKittrick Perc Ponds | JM | 3 | PENDING
CHEV CY | WATER PIPELINES | JM | 6 | SCHEDULED
CHEV CY | BEECROFT PIPELINES | JM | 3 | PENDING

## Survey Schedule
| JARED | ASHLEIGH | SABRINA | ERIKA | BLAINE | GARRETT | DONNA | SPENCER | SARAH | KIM | KAYLA | ANASTACIA | ARACELI | RAINEY | CODY | KORISSA | SAM | MATT | WOODY | COLIN | KAT | GILLIAN | ALEX | DAYNA | LEILANI | TOKY | KEVIN | ANNA | TOM | PRESTON | ODETTE | KAITLYN | ROBERT V | JAMIE | ROB K | CJ | JACOB | MOLLY | KATRINA | BRETT | RIGOBERTO | ALEX H | MITCH | REBECCA | BRANT | DANIEL | BRITTAN Y | KAMERON
2018-04-15 |  | CEH Lost Hills | TOM START | KAYLA START | SAM START | RAINEY OFF | COLINI START | MATT START | BRETT START | KAITLYN START | MOLLY START | [17 empty] | NEWBIES UNAVAILABLE | [27 empty] | 4 CONSEC. CEMC 6SF, 7S, D-06 (6/16 - 6/19)
2018-04-16 |  | CEH Lost Hills | TOM START | KAYLA START | SAM START | RAINEY OFF | COLINI START | MATT START | BRETT START | KAITLYN START | MOLLY START | [41 empty] | 27G DRAINAGES & 23L 4 CONSEC (5/29-6/1) |  | 2018-05-12 | 2018-05-12 |  |  | 4 CONSCECUTIVE CEMC GAS COMPRESSOR/ CWOD (5/29-6/1) |  |  | CEMC KRU, CHAP, GOVT2 4 CONSEC (5/3-5/6) |  |  |  | CHEV 32 US WESST & SECC 5 4 CONSECUTIVE (5/9-5/12) |  |  |  |  | 4 CONSECUTIVE CEMC Mays 57 & West Wells (5/7 -5/10) |  |  | 26F Day 1 (5/7) | Consec. 4 36T (5/7-5/10) |  | 4 CONSEC KOSS MORNING DR. (5/2 - 5/5) |  | 2018-05-28 | 2018-05-28
2018-04-17 |  | CEH Lost Hills | TOM START | KAYLA START | SAM START | RAINEY OFF | COLINI START | MATT START | BRETT START | KAITLYN START | MOLLY START | [43 empty] | 2018-05-22 | 2018-05-22 | [17 empty] | 26F Day 2 (5/9) |  |  |  |  | 2018-05-30 | 2018-05-30
2018-04-18 |  | CEH Lost Hills | TOM START | KAYLA START | SAM START | RAINEY OFF | COLINI START | MATT START | BRETT START | KAITLYN START | MOLLY START | [43 empty] | 2018-06-02 | 2018-06-02 | [17 empty] | 26F Day 3 (5/10) |  |  |  |  | 2018-06-03 | 2018-06-03
2018-04-19 |  | CEH Lost Hills | TOM START | KAYLA START | SAM START | RAINEY OFF | COLINI START | MATT START | BRETT START | KAITLYN START | MOLLY START | [43 empty] | 2018-06-07 | 2018-06-07 | 2018-06-21 | 2018-06-21 | [15 empty] | 26F DAY 4 (7/2) |  |  |  |  | 2018-06-15 | 2018-06-15
2018-04-20 |  | CEH Lost Hills | TOM START | KAYLA START | SAM START | COLINI START | MATT START | BRETT START | KAITLYN START | MOLLY START | [42 empty] | 2018-06-21 | 2018-06-21 | 2018-06-08 | 2018-06-08 | 2018-06-22 | 2018-06-22 | 2018-06-09 | 2018-06-09 | 2018-06-09 | 2018-06-07 | 2018-06-07 | 2018-06-07 | 2018-06-07 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 |  |  | 2018-06-04 | 2018-06-04 | 2018-06-04 |  |  |  | 2018-06-04 | 2018-06-04
2018-04-21 |  | CEH Lost Hills | TOM START | KAYLA START | SAM START | COLINI START | MATT START | BRETT START | KAITLYN START | MOLLY START | [42 empty] | 2018-06-29 | 2018-06-29 | 4 CONSEC. CEMC 30D, CHEV 2F (6/14 - 6/17) |  | 2018-07-02 | 2018-07-02 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 |  |  | CEMC MAYS 57 WEST, WEST WELLS, 36T, 26F 4 CONSECUTIVE (6/14 - 6/17) | [5 empty] | KOSS MORNING DR & EPC LANDFILL 4 CONSEC. (6/24 - 6/27)
2018-04-22 |  | CEH Lost Hills | TOM START | KAYLA START | SAM START | COLINI START | MATT START | BRETT START | KAITLYN START | MOLLY START | [42 empty] | 2018-06-30 | 2018-06-30 |  |  | 2018-07-04 | 2018-07-04 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23
2018-04-23 |  | CEH Lost Hills | TOM START | KAYLA START | SAM START | RAINEY OFF | COLINI START | MATT START | BRETT START | KAITLYN START | MOLLY START | [41 empty] | 2018-07-03 | 2018-07-03 |  |  | 2018-07-06 | 2018-07-06 | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02
2018-04-24 |  | CEH Lost Hills | TOM START | KAYLA START | SAM START | RAINEY OFF | COLINI START | MATT START | BRETT START | KAITLYN START | MOLLY START | [41 empty] | 2018-07-08 | 2018-07-08 |  |  | 2018-07-07 | 2018-07-07 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06
2018-04-25 |  | CEH Lost Hills | TOM START | KAYLA START | SAM START | RAINEY OFF | COLINI START | MATT START | BRETT START | KAITLYN START | MOLLY START | CHEV 32US EAST & SEC29 DAY 1 | CHEV 32US EAST & SEC29 DAY 1 | CHEV 32US EAST & SEC29 DAY 1 | CHEV 32US EAST & SEC29 DAY 1 | Derby Acres Burn; CEMC 2-22 Day 1 | Derby Acres Burn; CEMC 2-22 Day 1 | Derby Acres Burn; CEMC 2-22 Day 1 | Derby Acres Burn; CEMC 2-22 Day 1 | Derby Acres Burn; CEMC 2-22 Day 1 | UNAVAILABLE | [31 empty] | 2018-07-09 | 2018-07-09 | 2018-07-01 | 2018-07-01 | 2018-07-12 | 2018-07-12 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-11 | 2018-07-11 | 2018-07-11 | 2018-07-11 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 |  |  | 2018-07-01 | 2018-07-01 | 2018-07-01 |  |  |  | 2018-07-02 | 2018-07-02
2018-04-26 |  | CEH Lost Hills | TOM START | KAYLA START | SAM START | RAINEY OFF | COLINI START | MATT START | BRETT START | KAITLYN START | MOLLY START | CHEV 32US EAST & SEC29 DAY 2 | CHEV 32US EAST & SEC29 DAY 2 | CHEV 32US EAST & SEC29 DAY 2 | CHEV 32US EAST & SEC29 DAY 2 | Derby Acres Burn; CEMC 2-22 Day 2 | Derby Acres Burn; CEMC 2-22 Day 2 |  |  | UNAVAILABLE | [32 empty] | 2018-07-10 | 2018-07-10 | 2018-07-09 | 2018-07-09 | 2018-07-13 | 2018-07-13 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-09 | 2018-07-09 | 2018-07-09 | 2018-07-09 |  |  | 2018-07-03 | 2018-07-03 | 2018-07-03 |  |  |  | 2018-07-04 | 2018-07-04
2018-04-27 |  | CEH Lost Hills | TOM START | KAYLA START | SAM START | COLINI START | MATT START | BRETT START | KAITLYN START | MOLLY START | KAT OFF | [8 empty] | UNAVAILABLE | [32 empty] | 2018-07-11 | 2018-07-11 | 2018-07-12 | 2018-07-12 | 2018-07-14 | 2018-07-14 | 2018-07-10 | 2018-07-10 | 2018-07-10 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-14 | 2018-07-14 | 2018-07-14 | 2018-07-14 |  |  | 2018-07-04 | 2018-07-04 | 2018-07-04 |  |  |  | 2018-07-10 | 2018-07-10
2018-04-28 |  | CEH Lost Hills | SABRINA OFF | TOM START | KAYLA START | SAM START | COLINI START | MATT START | BRETT START | KAITLYN START | MOLLY START | KAT OFF | [44 empty] | 2018-07-15 | 2018-07-15
2018-04-29 |  | CEH Lost Hills | SABRINA OFF | TOM START | KAYLA START | SAM START | COLINI START | MATT START | BRETT START | KAITLYN START | MOLLY START | DAYNA OFF | [40 empty] | CHEV LH SOLAR 4 CONSECUTIVE (5/16 - 5/19) | [7 empty] | 2018-05-18 | 2018-05-18 | CHEV S25 & CHANSELOR 4 CONSECUTIVE (5/7-5/10) |  |  | 2018-05-22 | 2018-05-22 | 2018-05-22 | 2018-05-22 | 2018-05-22 | 2018-05-22 | 2018-05-22 | 2018-05-22 |  | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | Derby Burn & CEMC 2-22 Only 4/25/2018 | Derby Burn & CEMC 2-22 Only 4/25/2019 |  | Consecutive 4 (Trap & Pan Only) 5/9-5/12 |  | CONSECUTIVE 4 (O-P N & S ONLY) 5/7 - 5/10
2018-04-30 |  | CEH Lost Hills | TOM START | KAYLA START | SAM START | RAINEY OFF | COLINI START | MATT START | BRETT START | KAITLYN START | MOLLY START | DAYNA OFF | Temps | [47 empty] | 2018-05-19 | 2018-05-19 |  |  |  | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-23 |  | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | Derby Burn & CEMC 2-22 4/26/2018 | Derby Burn & CEMC 2-22 4/26/2019
2018-05-01 |  | CEH Lost Hills | TOM START | KAYLA START | SAM START | RAINEY OFF | COLINI START | MATT START | BRETT START | KAITLYN START | MOLLY START | DAYNA OFF | [48 empty] | 2018-05-27 | 2018-05-27 |  |  |  | 2018-05-24 | 2018-05-24 | 2018-05-24 | 2018-05-24 | 2018-05-24 | 2018-05-24 | 2018-05-24 | 2018-05-24 |  | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | Derby Burn Only & CEMC 2-22 5/4/2018 | Derby Burn Only & CEMC 2-22 5/4/2019
2018-05-02 |  | CEH Lost Hills | TOM START | KAYLA START | SAM START | COLINI START | MATT START | BRETT START | KAITLYN START | MOLLY START | DAYNA OFF | [6 empty] | KOSS 178 MORNING DR DAY 1 | KOSS 178 MORNING DR DAY 1 | KOSS 178 MORNING DR DAY 1 | KOSS 178 MORNING DR DAY 1 | [39 empty] | 2018-06-06 | 2018-06-06 |  |  |  | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 |  | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03 | Derby Burn & CEMC 2-22 5/12/2018 | Derby Burn CEMC 2-22 5/12/2019
2018-05-03 |  | CEH Lost Hills | TOM START | KAYLA START | SAM START | COLINI START | MATT START | BRETT START | KAITLYN START | MOLLY START | DAYNA OFF | CHEV 7S WEST DAY 1 | CHEV 7S WEST DAY 1 | CHEV 7S WEST DAY 1 | CHEV 7S WEST DAY 1 | MIDWAY TEMBLOR POLES DAY 1 | MIDWAY TEMBLOR POLES DAY 1 | KOSS 178 MORNING DR DAY 2 | KOSS 178 MORNING DR DAY 2 | CEMC KRU, CHAP, GOVT2 DAY 1 | CEMC KRU, CHAP, GOVT2 DAY 1 | CEMC KRU, CHAP, GOVT2 DAY 1 | CEMC KRU, CHAP, GOVT2 DAY 1 | UNAVAILABLE | [28 empty] | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | BERRY HB 1200H, HB SEC32 4 CONSEC. (6/16 - 6/19) |  | 2018-06-21 | 2018-06-21 | 2018-06-21 | AERA MIDBELRIDGE WEST 4 CONSECUTIVE (6/12 - 6/15) | [9 empty] | CEMS MWSS BRINE DISPOSAL, 2-22, DERBY BURN 4 CONSECUTIVE (6/7 - 6/10) | [6 empty] | 6/17/2018 (O-P NORTH & SOUTH ONLY) 6/19 (TRAP & PAN ONLY) | 6/17/2018 (O-P NORTH & SOUTH ONLY) 6/19 (TRAP & PAN ONLY) | 6/17/2018 (O-P NORTH & SOUTH ONLY) 6/19 (TRAP & PAN ONLY) | 6/17/2018 (O-P NORTH & SOUTH ONLY) 6/19 (TRAP & PAN ONLY)
2018-05-04 |  | CEH Lost Hills | TOM START | KAYLA START | SAM START | COLINI START | MATT START | BRETT START | KAITLYN START | MOLLY START | KORISSA OFF | CHEV 7S WEST DAY 2 | CHEV 7S WEST DAY 2 | CHEV 7S WEST DAY 2 | CHEV 7S WEST DAY 2 | MIDWAY TEMBLOR & SSM 687,8,12 POLES DAY 2 | MIDWAY TEMBLOR & SSM 687,8,12 POLES DAY 3 | KOSS 178 MORNING DR DAY 3 | KOSS 178 MORNING DR DAY 3 | CEMC KRU, CHAP, GOVT2 DAY 2 | CEMC KRU, CHAP, GOVT2 DAY 2 | CEMC KRU, CHAP, GOVT2 DAY 2 | CEMC KRU, CHAP, GOVT2 DAY 2 | Derby Acres Burn; CEMC 2-22 Day 3 | Derby Acres Burn; CEMC 2-22 Day 3 | UNAVAILABLE | [26 empty] | 2018-06-16 | 2018-06-16 | 2018-06-16 | 2018-06-16 | 2018-06-16 | 2018-06-16 | 2018-06-16 | 2018-06-16 |  |  | 2018-06-22 | 2018-06-22 | 2018-06-22 | [17 empty] | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25
2018-05-05 |  | CEH Lost Hills | SABRINA OFF | TOM START | KAYLA START | SAM START | COLINI START | MATT START | BRETT START | KAITLYN START | MOLLY START | KAT OFF | CHEV 7S WEST DAY 3 | CHEV 7S WEST DAY 3 | CHEV 7S WEST DAY 3 | CHEV 7S WEST DAY 3 | KOSS 178 MORNING DR DAY 4 | KOSS 178 MORNING DR DAY 4 |  |  | CEMC KRU, CHAP, GOVT2 DAY 3 | CEMC KRU, CHAP, GOVT2 DAY 3 | CEMC KRU, CHAP, GOVT2 DAY 3 | CEMC KRU, CHAP, GOVT2 DAY 3 | CEMC 1Y TANKS; WJ8 DAY 1 | CEMC 1Y TANKS; WJ8 DAY 1 | CEMC 1Y TANKS; WJ8 DAY 1 | [25 empty] | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 |  |  | 2018-06-23 | 2018-06-23 | 2018-06-23 | [17 empty] | 2018-06-26 | 2018-06-26 | 2018-06-26 | 2018-06-26
2018-05-06 |  | CEH Lost Hills | TOM START | KAYLA START | SAM START | COLINI START | MATT START | BRETT START | KAITLYN START | MOLLY START | KAT OFF | CHEV 7S WEST DAY 4 | CHEV 7S WEST DAY 4 | CHEV 7S WEST DAY 4 | CHEV 7S WEST DAY 4 |  | TENTATIVE: KOSS 1778 MORNING DRIVE |  |  |  | CEMC KRU, CHAP, GOVT2 DAY 4 | CEMC KRU, CHAP, GOVT2 DAY 4 | CEMC KRU, CHAP, GOVT2 DAY 4 | CEMC KRU, CHAP, GOVT2 DAY 4 | [28 empty] | 2018-06-19 | 2018-06-19 | 2018-06-19 | 2018-06-19 | 2018-06-19 | 2018-06-19 | 2018-06-19 | 2018-06-19 |  |  | 2018-06-24 | 2018-06-24 | 2018-06-24 | [17 empty] | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27
2018-05-07 |  | CEH Lost Hills | TOM START | SAM START | COLINI START | MATT START | BRETT START | KAITLYN START | MOLLY START | BERRY O-P N, O-P S, TRAP & PAN DAY 1 | BERRY O-P N, O-P S, TRAP & PAN DAY 1 | BERRY O-P N, O-P S, TRAP & PAN DAY 1 | BERRY O-P N, O-P S, TRAP & PAN DAY 1 | CHEV S25, CHANSELOR DAY 1 | CHEV S25, CHANSELOR DAY 1 | CHEV S25, CHANSELOR DAY 1 | CEMC MAYS 57; WEST WELLS DAY 1 | CEMC MAYS 57; WEST WELLS DAY 1 | CEMC MAYS 57; WEST WELLS DAY 1 | BERRY 21Z SOUTH DAY 1 | BERRY 21Z SOUTH DAY 1 | BERRY 21Z SOUTH DAY 1 | BERRY 21Z SOUTH DAY 1 | BERRY 21Z SOUTH DAY 1 |  |  | UNAVAILABLE | [25 empty] | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-07-01 | 2018-07-01 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 |  |  | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 |  |  |  | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02
2018-05-08 |  | CEH Lost Hills | TOM START | KAYLA START | SAM START | COLINI START | MATT START | BRETT START | KAITLYN START | MOLLY START | BERRY O-P N, O-P S, TRAP & PAN DAY 2 | BERRY O-P N, O-P S, TRAP & PAN DAY 2 | BERRY O-P N, O-P S, TRAP & PAN DAY 2 | BERRY O-P N, O-P S, TRAP & PAN DAY 2 | CHEV S25, CHANSELOR DAY 2 | CHEV S25, CHANSELOR DAY 2 | CHEV S25, CHANSELOR DAY 2 | CEMC MAYS 57; WEST WELLS DAY 2 | CEMC MAYS 57; WEST WELLS DAY 2 | CEMC MAYS 57; WEST WELLS DAY 2 |  |  |  |  | UNAVAILABLE | [27 empty] | 2018-06-26 | 2018-06-26 | 2018-06-26 | 2018-06-26 | 2018-06-26 | 2018-06-26 | 2018-06-26 | 2018-06-26 | 2018-07-06 | 2018-07-06 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 |  |  | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 |  |  |  | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03
2018-05-09 |  | CEH Lost Hills | SPENCER OFF | TOM START | KAYLA START | SAM START | COLINI START | MATT START | BRETT START | KAITLYN START | MOLLY START | BERRY O-P N, O-P S, TRAP & PAN DAY 3 | BERRY O-P N, O-P S, TRAP & PAN DAY 3 | BERRY O-P N, O-P S, TRAP & PAN DAY 3 | BERRY O-P N, O-P S, TRAP & PAN DAY 3 | CHEV 32US WEST & SEC5 DAY 1 | CHEV 32US WEST & SEC5 DAY 1 | CHEV 32US WEST & SEC5 DAY 1 | CHEV 32US WEST & SEC5 DAY 1 | CHEV S25, CHANSELOR DAY 3 | CHEV S25, CHANSELOR DAY 3 | CHEV S25, CHANSELOR DAY 3 | CEMC MAYS 57; WEST WELLS DAY 3 | CEMC MAYS 57; WEST WELLS DAY 3 | CEMC MAYS 57; WEST WELLS DAY 3 | [27 empty] | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-07-07 | 2018-07-07 | 2018-07-11 | 2018-07-11 | 2018-07-11 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29 |  |  | 2018-07-09 | 2018-07-09 | 2018-07-09 | 2018-07-09 |  |  |  | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08
2018-05-10 |  | CEH Lost Hills | TOM START | KAYLA START | SAM START | COLINI START | MATT START | BRETT START | KAITLYN START | MOLLY START | BERRY O-P N, O-P S, TRAP & PAN DAY 4 | BERRY O-P N, O-P S, TRAP & PAN DAY 4 | BERRY O-P N, O-P S, TRAP & PAN DAY 4 | BERRY O-P N, O-P S, TRAP & PAN DAY 4 | CHEV 32US WEST & SEC5 DAY 2 | CHEV 32US WEST & SEC5 DAY 2 | CHEV 32US WEST & SEC5 DAY 2 | CHEV 32US WEST & SEC5 DAY 2 | CHEV S25, CHANSELOR DAY 4 | CHEV S25, CHANSELOR DAY 4 | CHEV S25, CHANSELOR DAY 4 | CEMC MAYS 57; WEST WELLS DAY 4 | CEMC MAYS 57; WEST WELLS DAY 4 | CEMC MAYS 57; WEST WELLS DAY 4 |  |  | UNAVAILABLE | [25 empty] | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-13 | 2018-07-13 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-09 | 2018-07-09 | 2018-07-09 | 2018-07-09 | 2018-07-09 | 2018-07-09 | 2018-07-09 | 2018-07-09 |  |  | 2018-07-10 | 2018-07-10 | 2018-07-10 | 2018-07-10 |  |  |  | 2018-07-09 | 2018-07-09 | 2018-07-09 | 2018-07-09
2018-05-11 |  | CEH Lost Hills | ASHLEIGH VACAY | TOM START | MATT START | BRETT START | KAITLYN START | MOLLY START | CHEV 32US WEST & SEC5 DAY 3 | CHEV 32US WEST & SEC5 DAY 3 | CHEV 32US WEST & SEC5 DAY 3 | CHEV 32US WEST & SEC5 DAY 3 | AERA MIDDLE BELRIDGE EAST DAY 1 | AERA MIDDLE BELRIDGE EAST DAY 1 | AERA MIDDLE BELRIDGE EAST DAY 1 | AERA MIDDLE BELRIDGE EAST DAY 1 | AERA MIDDLE BELRIDGE EAST DAY 1 | AERA MIDDLE BELRIDGE EAST DAY 1 | CHEV 7S NORTH, 8S DAY 1 | CHEV 7S NORTH, 8S DAY 1 | CHEV 7S NORTH, 8S DAY 1 | CHEV 7S NORTH, 8S DAY 1 |  |  | UNAVAILABLE
2018-05-12 |  | CEH Lost Hills | ASHLEIGH VACAY | TOM START | KAYLA START | BRETT START | MOLLY START | CHEV 32US WEST & SEC5 DAY 4 | CHEV 32US WEST & SEC5 DAY 4 | CHEV 32US WEST & SEC5 DAY 4 | CHEV 32US WEST & SEC5 DAY 4 | SSM 687,8,12 Day1 | SSM 687,8,12 Day1 | Derby Acres Burn; CEMC 2-22 Day 4 | Derby Acres Burn; CEMC 2-22 Day 4 | CEMC 30D; CHEV 2F DAY 1 | CEMC 30D; CHEV 2F DAY 1 |  | CHEV 7S NORTH, 8S DAY 2 | CHEV 7S NORTH, 8S DAY 2 | CHEV 7S NORTH, 8S DAY 2 | CHEV 7S NORTH, 8S DAY 2 | [30 empty] | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-23 | CHEV 7S WEST 4 Consective (5/3-5/6) NOTE: 1st day did not finish last transect before 2pm |  |  |  | 2018-05-11 | 2018-05-11 | 2018-05-11 | 2018-05-11 |  | 21Z S 5/7/2018 | 21Z S 5/7/2018 | 21Z S 5/7/2018 | 21Z S 5/7/2018 | 21Z S 5/7/2018 | 21Z N 5/23/2018 | 21Z N 5/23/2018 | 21Z N 5/23/2018
2018-05-13 |  | CEH Lost Hills | ASHLEIGH VACAY | TOM START | KAYLA START | BRETT START | MOLLY START | [45 empty] | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-24 | 2018-05-24 | 2018-05-24 | 2018-05-24 | 2018-05-24 |  |  |  |  | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 |  | 21Z S 5/27/2018 | 21Z S 5/27/2018 | 21Z S 5/27/2018 | 21Z S 5/27/2018 | 21Z S 5/27/2018 | 21Z N 5/24/2018 | 21Z N 5/24/2018 | 21Z N 5/24/2018
2018-05-14 |  | CEH Lost Hills | ASHLEIGH VACAY | TOM START | KAYLA START | SAM START | COLINI START | MATT START | BRETT START | MOLLY START | CHEV CO 23D DAY 1 | CHEV CO 23D DAY 1 | CHEV CO 23D DAY 1 | CHEV CO 23D DAY 1 | CHEV CO 23D DAY 1 | CHEV CO 23D DAY 1 | CHEV CO 23D DAY 1 | AERA MIDDLE BELRIDGE EAST DAY 2 | AERA MIDDLE BELRIDGE EAST DAY 2 | AERA MIDDLE BELRIDGE EAST DAY 2 | AERA MIDDLE BELRIDGE EAST DAY 2 | AERA MIDDLE BELRIDGE EAST DAY 2 | AERA MIDDLE BELRIDGE EAST DAY 2 | [29 empty] | 2018-05-15: CHEV CO 23D 4 CONSEC 5/29 - 6/1; 2018-05-24: 2018-05-27; 2018-05-24: 2018-05-27; 2018-05-24: 2018-05-27; 2018-05-24: 2018-05-27; 2018-05-24: 2018-05-27 |  |  |  |  | 5/21/2018 & 6/12 (8S) | 5/21/2018 & 6/12 | 5/21/2018 & 6/12 | 5/21/2018 & 6/12 |  |  | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02
2018-05-15 |  | CEH Lost Hills | ASHLEIGH VACAY | TOM START | KAYLA START | SAM START | COLINI START | MATT START | BRETT START | MOLLY START | CHEV CO 23D DAY 2 | CHEV CO 23D DAY 2 | CHEV CO 23D DAY 2 | CHEV CO 23D DAY 2 | CHEV CO 23D DAY 2 | CHEV CO 23D DAY 2 | CHEV CO 23D DAY 2 | AERA MIDDLE BELRIDGE EAST DAY 3 | AERA MIDDLE BELRIDGE EAST DAY 3 | AERA MIDDLE BELRIDGE EAST DAY 3 | AERA MIDDLE BELRIDGE EAST DAY 3 | AERA MIDDLE BELRIDGE EAST DAY 3 | AERA MIDDLE BELRIDGE EAST DAY 3 | [29 empty] | 2018-05-24: 2018-05-28; 2018-05-24: 2018-05-28; 2018-05-24: 2018-05-28; 2018-05-24: 2018-05-28; 2018-05-24: 2018-05-28 |  |  |  |  | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 |  |  | 2018-06-03 | 2018-06-03 | 2018-06-03 | 2018-06-03 | 2018-06-03 | 2018-06-03
2018-05-16 |  | CEH Lost Hills | ASHLEIGH VACAY | TOM START | KAYLA START | SAM START | COLINI START | MATT START | BRETT START | MOLLY START |  |  | CHEV LH SOLAR DAY 1 | CHEV LH SOLAR DAY 1 | CHEV LH SOLAR DAY 1 | CHEV LH SOLAR DAY 1 | CHEV LH SOLAR DAY 1 | CHEV LH SOLAR DAY 1 | CHEV LH SOLAR DAY 1 | CHEV LH SOLAR DAY 1 | CHEV LH SOLAR DAY 1 | CHEV LH SOLAR DAY 1 | CHEV LH SOLAR DAY 1 | CHEV LH SOLAR DAY 1 | CHEV LH SOLAR DAY 1 | CHEV LH SOLAR DAY 1 | CHEV LH SOLAR DAY 1 | CHEV LH SOLAR DAY 1 |  | TEMPS (1.5 HOUR WINDOW. DOUBLE EFFORT ON CHEV LH SOLAR) | [22 empty] | 2018-05-24: CHEV MWSS 26F, 23F 4 CONSECUTIVE (6/11 - 6/14) | 2018-06-15 | 2018-06-15 | 2018-06-15 | 2018-06-15 | CHEV 7S NORTH, 8S 4 CONSECUTIVE (6/8 - 6/11) | [5 empty] | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05
2018-05-17 |  | CEH Lost Hills | ASHLEIGH VACAY | TOM START | KAYLA START | SAM START | ARACELI OFF | KAT OFF | COLINI START | MATT START | BRETT START | MOLLY START |  |  |  | CHEV LH SOLAR DAY 2 | CHEV LH SOLAR DAY 2 | CHEV LH SOLAR DAY 2 | CHEV LH SOLAR DAY 2 | CHEV LH SOLAR DAY 2 | CHEV LH SOLAR DAY 2 | CHEV LH SOLAR DAY 2 | CHEV LH SOLAR DAY 2 | CHEV LH SOLAR DAY 2 | CHEV LH SOLAR DAY 2 | CHEV LH SOLAR DAY 2 | CHEV LH SOLAR DAY 2 | [37 empty] | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | [6 empty] | BERRY 21Z NORTH & SOUTH 4 CONSECUTIVE (6/25 - 6/28)
2018-05-18 |  | CEH Lost Hills | ASHLEIGH VACAY | MOLLY START | KAYLA START | SAM START | ARACELI OFF | KAT OFF | COLINI START | MATT START | BRETT START |  | BERRY HB 1200H; HB S32 DAY 1 | BERRY HB 1200H; HB S32 DAY 1 | CHEV LH SOLAR DAY 3 | CHEV LH SOLAR DAY 3 | CHEV LH SOLAR DAY 3 | CHEV LH SOLAR DAY 3 | CHEV LH SOLAR DAY 3 | CHEV LH SOLAR DAY 3 | CHEV LH SOLAR DAY 3 | CHEV LH SOLAR DAY 3 | CHEV LH SOLAR DAY 3 | CHEV LH SOLAR DAY 3 | CHEV LH SOLAR DAY 3 | CHEV LH SOLAR DAY 3 | [26 empty] | 2018-05-15: 2018-06-18; 2018-05-15: 2018-06-18; 2018-05-15: 2018-06-18; 2018-05-15: 2018-06-18; 2018-05-15: 2018-06-18; 2018-05-15: 2018-06-18; 2018-05-15: 2018-06-18 | 2018-06-19 | 2018-06-19 | 2018-06-19 | 2018-06-19
2018-05-19 |  | CEH Lost Hills | ASHLEIGH VACAY | SPENCER OFF | MOLLY START | KAYLA START | KIM OFF | ARACELI OFF | KAT OFF | BRETT START |  | BERRY HB 1200H; HB S32 DAY 2 | BERRY HB 1200H; HB S32 DAY 2 | CHEV LH SOLAR DAY 4 | CHEV LH SOLAR DAY 4 | CHEV LH SOLAR DAY 4 | CHEV LH SOLAR DAY 4 | CHEV LH SOLAR DAY 4 | CHEV LH SOLAR DAY 4 | CHEV LH SOLAR DAY 4 | CHEV LH SOLAR DAY 4 | CHEV LH SOLAR DAY 4 | CHEV LH SOLAR DAY 4 | CHEV LH SOLAR DAY 4 | CHEV LH SOLAR DAY 4 | [27 empty] | 2018-05-15: 2018-06-19; 2018-05-15: 2018-06-19; 2018-05-15: 2018-06-19; 2018-05-15: 2018-06-19; 2018-05-15: 2018-06-19; 2018-05-15: 2018-06-19; 2018-05-15: 2018-06-19 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20
2018-05-20 |  | CEH Lost Hills | ASHLEIGH VACAY | SPENCER OFF | MOLLY START | KAYLA START | KIM OFF | ARACELI OFF | KAT OFF | BRETT START | [10 empty] | KAT OFF | [31 empty] | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-30 | 2018-06-30 | 2018-06-30 | 2018-06-30 | 6/18/2018 & 6/21 | 6/18/2018 & 6/21 | 6/18/2018 & 6/21 | 6/18/2018 & 6/21
2018-05-21 | 3 Monitors/Week | ASH OFF | ERIKA 2 DAYS/WEEK | 3 Monitors/Week | GARRETT 2 DAYS/WEEK | 3 Monitors/Week | SPENCER OFF | ANASTACIA 3 DAYS/WEEK | ARACELI OFF | RAINEY HSR | CODY HSR | KOR 3 DAYS/WEEK | SAM FRI-SUN ONLY | WOODY HSR | KAT OFF | GILLIAN OFF | ANNA START | ODETTE START | JAMIE HSR | ROB K START | CJ START | JACOB ORIENTATION | MOLLY START | KATRINA ORIENTATION | BRETT START |  |  |  |  | CHEV 32US EAST & SEC29 DAY 3 | CHEV 32US EAST & SEC29 DAY 3 | CHEV 32US EAST & SEC29 DAY 3 | CHEV 32US EAST & SEC29 DAY 3 | CHEV 7S NORTH, 8S DAY 3 | CHEV 7S NORTH, 8S DAY 3 | CHEV 7S NORTH, 8S DAY 3 | CHEV 7S NORTH, 8S DAY 3 | CEMC 1Y TANKS; WJ8 DAY 2 | CEMC 1Y TANKS; WJ8 DAY 2 | CEMC 1Y TANKS; WJ8 DAY 2 | [12 empty] | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 |  |  | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02
2018-05-22 | 3 Monitors/Week | ASH OFF | 3 Monitors/Week | ERIKA 2 DAYS/WEEK | 3 Monitors/Week | GARRETT 2 DAYS/WEEK | KIM OFF | GILLIAN OFF | ANASTACIA 3 DAYS/WEEK | RAINEY HSR | CODY HSR | KOR 3 DAYS/WEEK | SAM FRI-SUN ONLY | WOODY HSR | KAT OFF | ANNA START | ODETTE START | JAMIE HSR | ROB K START | CJ START | JACOB ORIENTATION | MOLLY START | KATRINA ORIENTATION | BRETT START |  |  |  | CEMC 30D; CHEV 2F DAY 2 | CEMC 30D; CHEV 2F DAY 2 | AERA MIDDLE BELRIDGE WEST DAY 1 | AERA MIDDLE BELRIDGE WEST DAY 1 | AERA MIDDLE BELRIDGE WEST DAY 1 | AERA MIDDLE BELRIDGE WEST DAY 1 | AERA MIDDLE BELRIDGE WEST DAY 1 | AERA MIDDLE BELRIDGE WEST DAY 1 | AERA MIDDLE BELRIDGE WEST DAY 1 | AERA MIDDLE BELRIDGE WEST DAY 1 | CEMC 1Y TANKS; WJ8 DAY 3 | CEMC 1Y TANKS; WJ8 DAY 3 | CEMC 1Y TANKS; WJ8 DAY 3 | [12 empty] | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-30 | 2018-06-30 | 2018-06-30 | 2018-06-30 | 2018-06-30 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 |  |  | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04
2018-05-23 | 3 Monitors/Week | ASH OFF | 3 Monitors/Week | 3 Monitors/Week | ANASTACIA 3 DAYS/WEEK | RAINEY HSR | CODY HSR | KOR 3 DAYS/WEEK | SAM FRI-SUN ONLY | WOODY HSR | KAT OFF | ANNA START | ODETTE START | JAMIE HSR | ROB K START | CJ START | JACOB ORIENTATION | BERRY 21Z NORTH DAY 1 | BERRY 21Z NORTH DAY 1 | BERRY 21Z NORTH DAY 1 | CHEV MWSS 26F, 23F DAY 1 | CHEV MWSS 26F, 23F DAY 1 | CHEV MWSS 26F, 23F DAY 1 | CHEV MWSS 26F, 23F DAY 1 | CHEV MWSS 26F, 23F DAY 1 | CHEV 25 HILL N & S DAY 1 | CHEV 25 HILL N & S DAY 1 | CHEV 25 HILL N & S DAY 1 | CHEV 25 HILL N & S DAY 1 | CHEV 25 HILL N & S DAY 1 | CHEV 25 HILL N & S DAY 1 | CHEV 25 HILL N & S DAY 1 | AERA MIDDLE BELRIDGE WEST DAY 2 | AERA MIDDLE BELRIDGE WEST DAY 2 | AERA MIDDLE BELRIDGE WEST DAY 2 | AERA MIDDLE BELRIDGE WEST DAY 2 | AERA MIDDLE BELRIDGE WEST DAY 2 | AERA MIDDLE BELRIDGE WEST DAY 2 | AERA MIDDLE BELRIDGE WEST DAY 2 | AERA MIDDLE BELRIDGE WEST DAY 2 | [12 empty] | 2018-06-30 | 2018-06-30 | 2018-06-30 | 2018-06-30 | 2018-06-30 | 2018-06-30 | 2018-06-30 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-14 | 2018-07-14 | 2018-07-14 | 2018-07-14 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 |  |  | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07
2018-05-24 | 3 Monitors/Week | 3 Monitors/Week | 3 Monitors/Week | RAINEY HSR | CODY HSR | SAM FRI-SUN ONLY | WOODY HSR | KAT OFF | GILLIAN OFF | ANNA START | JAMIE HSR | ROB K START | CJ START | ODETTE START | MOLLY START | BRETT START |  | BERRY 21Z NORTH DAY 2 | BERRY 21Z NORTH DAY 2 | BERRY 21Z NORTH DAY 2 | CHEV MWSS 26F, 23F DAY 2 | CHEV MWSS 26F, 23F DAY 2 | CHEV MWSS 26F, 23F DAY 2 | CHEV MWSS 26F, 23F DAY 2 | CHEV MWSS 26F, 23F DAY 2 | CHEV 25 HILL N DAY 2 | CHEV 25 HILL N DAY 2 | CHEV 25 HILL N DAY 2 | CHEV 25 HILL N DAY 2 | CHEV 25 HILL N DAY 2 | CHEV 25 HILL N DAY 2 | CHEV 25 HILL N DAY 2 | AERA MIDDLE BELRIDGE WEST DAY 3 | AERA MIDDLE BELRIDGE WEST DAY 3 | AERA MIDDLE BELRIDGE WEST DAY 3 | AERA MIDDLE BELRIDGE WEST DAY 3 | AERA MIDDLE BELRIDGE WEST DAY 3 | AERA MIDDLE BELRIDGE WEST DAY 3 | AERA MIDDLE BELRIDGE WEST DAY 3 | AERA MIDDLE BELRIDGE WEST DAY 3 | [12 empty] | 2018-06-30: 2018-06-14; 2018-06-30: 2018-06-14
2018-05-25 | 3 Monitors/Week | 3 Monitors/Week | 3 Monitors/Week | RAINEY HSR | CODY HSR | WOODY HSR | KAT OFF | ANNA START | ODETTE START | JAMIE HSR | ROB K START | MOLLY START | BRETT START | TEMPS | [38 empty] | 2018-05-11 | 2018-05-11 | 2018-05-11 | 2018-05-11 | 2018-05-11 | 2018-05-11 | AERA CALSO PIPE 4 CONSEC (5/29 - 6/1) | [5 empty] | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-23 | 5/23/2018 (TIMED OUT) | 5/23/2018 (TIMED OUT) | 5/23/2018 (TIMED OUT) |  |  | 5/12 (SSM 687,8,12 ONLY) | 5/12 (SSM 687,8,12 ONLY) | 5/3/2018 (Midway-Temblor Only) | 5/3/2018 (Midway-Temblor Only)
2018-05-26 | RAINEY HSR | CODY HSR | ERIKA OFF SAT & SUN | KAT OFF | GILLIAN OFF | LEILANI OFF SAT & SUN | ANNA START | ODETTE START | BRETT START |  |  |  |  | TEMPS | [38 empty] | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | [6 empty] | 2018-05-24 | 2018-05-24 | 2018-05-24 | 2018-05-24 | 2018-05-24 | 2018-05-24 | 2018-05-24 | CHEV 25 HILL S 4 CONSECUTIVE (5/29 - 6/1) | [5 empty] | MIDWAY-TEMBLOR & SSM 687,8,12 (5/27) | MIDWAY-TEMBLOR & SSM 687,8,12 (5/27)
2018-05-27 | ERIKA OFF SAT & SUN | BLAINE OFF SUN | SARAH OFF SUN | RAINEY HSR | CODY HSR | KAT OFF | GILLIAN OFF | LEILANI OFF SAT & SUN | ANNA START | ODETTE START | BRETT START |  |  | CHEV MWSS 26F, 23F DAY 3 | CHEV MWSS 26F, 23F DAY 3 | CHEV MWSS 26F, 23F DAY 3 | CHEV MWSS 26F, 23F DAY 3 | CHEV MWSS 26F, 23F DAY 3 | BERRY 21Z SOUTH DAY 2 | BERRY 21Z SOUTH DAY 2 | BERRY 21Z SOUTH DAY 2 | BERRY 21Z SOUTH DAY 2 | BERRY 21Z SOUTH DAY 2 | BERRY HB 1200H; HB S32 DAY 3 | BERRY HB 1200H; HB S32 DAY 3 | MIDWAY-TEMBLOR & SSM 687,8 POLES DAY 2 | MIDWAY-TEMBLOR & SSM 687,8,12 POLES DAY 2 | STEVENS DINO & TILT DAY 1 | STEVENS DINO & TILT DAY 1 | STEVENS DINO & TILT DAY 1 | STEVENS DINO & TILT DAY 1 | [21 empty] | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | [6 empty] | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | [6 empty] | MIDWAY-TEMBLOR & SSM 687,8,12 (6/2) | MIDWAY-TEMBLOR & SSM 687,8,12 (6/2)
2018-05-28 | ARACELI OFF | RAINEY HSR | CODY HSR | Woody OFF | COLIN HSR SUB FOR WOODY | KAT OFF | ANNA START | ODETTE START | MOLLY START | BRETT START |  |  |  | CHEV MWSS 26F, 23F DAY 4 | CHEV MWSS 26F, 23F DAY 4 | CHEV MWSS 26F, 23F DAY 4 | CHEV MWSS 26F, 23F DAY 4 | CHEV MWSS 26F, 23F DAY 4 | EPC LANDFILL DAY 1 | EPC LANDFILL DAY 1 | CHEV 25 HILL N DAY 3 | CHEV 25 HILL N DAY 3 | CHEV 25 HILL N DAY 3 | CHEV 25 HILL N DAY 3 | CHEV 25 HILL N DAY 3 | CHEV 25 HILL N DAY 3 | CHEV 25 HILL N DAY 3 | CHEV 7S NORTH, 8S DAY 4 | CHEV 7S NORTH, 8S DAY 4 | CHEV 7S NORTH, 8S DAY 4 | CHEV 7S NORTH, 8S DAY 4 | CEMC 15G LEASE DAY 1 | CEMC 15G LEASE DAY 1 | CEMC 15G LEASE DAY 1 | [18 empty] | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | [6 empty] | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | [6 empty] | MIDWAY-TEMBLOR & SSM 687,8,12 (6/16) | MIDWAY-TEMBLOR & SSM 687,8,12 (6/16)
2018-05-29 | 3 Monitors/Week | ASH 2 DAYS/WEEK | ERIKA 2 DAYS/WEEK | 3 Monitors/Week | GARRETT 2 DAYS/WEEK | RAINEY HSR | CODY HSR | 3 Monitors/Week | ANASTACIA 3 DAYS/WEEK | SAM FRI-SUN ONLY | Woody OFF | COLIN HSR SUB FOR WOODY | CHEV 32US EAST & SEC29 DAY 4 | CHEV 32US EAST & SEC29 DAY 4 | CHEV 32US EAST & SEC29 DAY 4 | CHEV 32US EAST & SEC29 DAY 4 | NERC SSM 523-534 & 632-642 Day 3 | NERC SSM 523-534 & 632-642 Day 3 | CHEV CO 23D DAY 3 | CHEV CO 23D DAY 3 | CHEV CO 23D DAY 3 | CHEV CO 23D DAY 3 | CHEV CO 23D DAY 3 | CHEV CO 23D DAY 3 | CHEV CO 23D DAY 3 | CHEV 25 HILL S DAY 2 | CHEV HILL S DAY 2 | CHEV 25 HILL S DAY 2 | AERA CAL SO PIPE DAY 1 | AERA CAL SO PIPE DAY 1 | AERA CAL SO PIPE DAY 1 | AERA CAL SO PIPE DAY 1 | AERA CAL SO PIPE DAY 1 | AERA CAL SO PIPE DAY 1 | 27G DRAINAGES & 23L DAY 1 | 27G DRAINAGES & 23L DAY 1 | CEMC GAS COMPRESSOR DAY 1 | CEMC GAS COMPRESSOR DAY 1 | CEMC GAS COMPRESSOR DAY 1 | CEMC GAS COMPRESSOR DAY 1 | [12 empty] | 2018-06-20: AERA MIDBELRIDGE EAST 4 CONSECUTIVE (6/18 - 6/21); 2018-06-20: 2018-06-22; 2018-06-27: 2018-06-22; 2018-06-27: 2018-06-22; 2018-06-27: 2018-06-22; 2018-06-27: 2018-06-22; 2018-06-27: 2018-06-22; 2018-06-30: CHEV 25 HILL N 4 CONSECUTIVE (6/13 - 6/16) | [9 empty] | MIDWAY-TEMBLOR & SSM 687,8,12 & 36W (6/19) | MIDWAY-TEMBLOR & SSM 687,8,12 & 36W (6/19) |  |  | 2018-05-05 | 2018-05-05 | 2018-05-05
2018-05-30 | 3 Monitors/Week | ANASTACIA 3 DAYS/WEEK | 3 Monitors/Week | RAINEY HSR | CODY HSR | KOR 3 DAYS/WEEK | ANNA START | 3 Monitors/Week | SAM FRI-SUN ONLY | Woody OFF | COLIN HSR SUB FOR WOODY | KAT OFF | GILLIAN OFF | ODETTE START | EPC LANDFILL DAY 2 | EPC LANDFILL DAY 2 | NERC SSM 523-534 & 632-642 Day 4 | NERC SSM 523-534 & 632-642 Day 4 | CHEV CO 23D DAY 4 | CHEV CO 23D DAY 4 | CHEV CO 23D DAY 4 | CHEV CO 23D DAY 4 | CHEV CO 23D DAY 4 | CHEV CO 23D DAY 4 | CHEV CO 23D DAY 4 | CHEV 25 HILL S DAY 3 | CHEV HILL S DAY 3 | CHEV 25 HILL S DAY 3 | AERA CAL SO PIPE DAY 2 | AERA CAL SO PIPE DAY 2 | AERA CAL SO PIPE DAY 2 | AERA CAL SO PIPE DAY 2 | AERA CAL SO PIPE DAY 2 | AERA CAL SO PIPE DAY 2 | 27G DRAINAGES & 23L DAY 2 | 27G DRAINAGES & 23L DAY 2 | CEMC GAS COMPRESSOR DAY 2 | CEMC GAS COMPRESSOR DAY 2 | CEMC GAS COMPRESSOR DAY 2 | CEMC GAS COMPRESSOR DAY 2 | [12 empty] | 2018-06-20: 2018-07-03; 2018-06-27: 2018-07-03; 2018-06-27: 2018-07-03; 2018-06-27: 2018-07-03; 2018-06-27: 2018-07-03; 2018-06-27: 2018-07-03 |  |  |  | 2018-06-22 | 2018-06-22 | 2018-06-22 |  |  |  | MIDWAY-TEMBLOR & SSM 687,8,12 & 36W (6/28) | MIDWAY-TEMBLOR & SSM 687,8,12 & 36W (6/28) |  |  | 2018-05-21 | 2018-05-21 | 2018-05-21
2018-05-31 | 3 Monitors/Week | 3 Monitors/Week | SARAH OFF | SAM FRI-SUN ONLY | 3 Monitors/Week | RAINEY HSR | CODY HSR | Woody OFF | COLIN HSR SUB FOR WOODY | KAT OFF | GILLIAN OFF | ODETTE START | JAMIE HSR | BRETT START | ANNA START | MOLLY START | NERC SSM 523-534 & 632-642 Day 5 | NERC SSM 523-534 & 632-642 Day 5 | CHEV CO 23D DAY 5 | CHEV CO 23D DAY 5 | CHEV CO 23D DAY 5 | CHEV CO 23D DAY 5 | CHEV CO 23D DAY 5 | CHEV CO 23D DAY 5 | CHEV CO 23D DAY 5 | CHEV 25 HILL S DAY 4 | CHEV HILL S DAY 4 | CHEV 25 HILL S DAY 4 | AERA CAL SO PIPE DAY 3 | AERA CAL SO PIPE DAY 3 | AERA CAL SO PIPE DAY 3 | AERA CAL SO PIPE DAY 3 | AERA CAL SO PIPE DAY 3 | AERA CAL SO PIPE DAY 3 | 27G DRAINAGES & 23L DAY 3 | 27G DRAINAGES & 23L DAY 3 | CEMC GAS COMPRESSOR DAY 3 | CEMC GAS COMPRESSOR DAY 3 | CEMC GAS COMPRESSOR DAY 3 | CEMC GAS COMPRESSOR DAY 3 | [12 empty] | 2018-06-20: 2018-07-05; 2018-06-27: 2018-07-05; 2018-06-27: 2018-07-05; 2018-06-27: 2018-07-05; 2018-06-27: 2018-07-05; 2018-06-27: 2018-07-05 |  |  |  | 2018-06-26 | 2018-06-26 | 2018-06-26 | [5 empty] | 36W DAY 1 (6/2) | 36W DAY 1 (6/2) | 2018-05-22 | 2018-05-22 | 2018-05-22
2018-06-01 | 3 Monitors/Week | 3 Monitors/Week | SARAH OFF | ANNA START | 3 Monitors/Week | RAINEY HSR | CODY HSR | Woody OFF | COLIN HSR SUB FOR WOODY | KAT OFF | ODETTE START | JAMIE HSR | BRETT START | [5 empty] | CHEV CO 23D DAY 6 | CHEV CO 23D DAY 6 | CHEV CO 23D DAY 6 | CHEV CO 23D DAY 6 | CHEV CO 23D DAY 6 | CHEV CO 23D DAY 6 | CHEV CO 23D DAY 6 | CHEV 25 HILL S DAY 5 | CHEV HILL S DAY 5 | CHEV 25 HILL S DAY 5 | AERA CAL SO PIPE DAY 4 | AERA CAL SO PIPE DAY 4 | AERA CAL SO PIPE DAY 4 | AERA CAL SO PIPE DAY 4 | AERA CAL SO PIPE DAY 4 | AERA CAL SO PIPE DAY 4 | 27G DRAINAGES & 23L DAY 4 | 27G DRAINAGES & 23L DAY 4 | CEMC GAS COMPRESSOR DAY 4 | CEMC GAS COMPRESSOR DAY 4 | CEMC GAS COMPRESSOR DAY 4 | CEMC GAS COMPRESSOR DAY 4 | [12 empty] | 2018-06-20: 2018-07-06; 2018-06-27: 2018-07-06; 2018-06-27: 2018-07-06; 2018-06-27: 2018-07-06; 2018-06-27: 2018-07-06; 2018-06-27: 2018-07-06 |  |  |  | 2018-06-27 | 2018-06-27 | 2018-06-27 | [5 empty] | 36W DAY 2 (6/4) | 36W DAY 2 (6/4) | 2018-06-04 | 2018-06-04 | 2018-06-04
2018-06-02 | ASH OFF | SABRINA OFF | ERIKA OFF SAT & SUN |  | LEILANI OFF SAT & SUN | ANNA START | ODETTE START | BRETT START | SARAH OFF | RAINEY HSR | CODY HSR | Woody OFF | COLIN HSR SUB FOR WOODY | KAT OFF | BERRY 21Z N & S DAY 3 | BERRY 21Z N & S DAY 3 | BERRY 21Z N & S DAY 3 | BERRY 21Z N & S DAY 3 | BERRY 21Z N & S DAY 3 | BERRY 21Z N & S DAY 3 | STEVENS DINO & TILT DAY 2 | STEVENS DINO & TILT DAY 2 | STEVENS DINO & TILT DAY 2 | STEVENS DINO & TILT DAY 2 | CHEV 25 HILL N DAY 4 | CHEV 25 HILL N DAY 4 | CHEV 25 HILL N DAY 4 | CHEV 25 HILL N DAY 4 | CHEV 25 HILL N DAY 4 | CHEV 25 HILL N DAY 4 | CHEV 25 HILL N DAY 4 | CYMRIC WATERLINE DAY 1 | CYMRIC WATERLINE DAY 1 | CYMRIC WATERLINE DAY 1 | CYMRIC WATERLINE DAY 1 | CYMRIC WATERLINE DAY 1 | CYMRIC WATERLINE DAY 1 | MIDWAY-TEMBLOR & SSM 687,8,12 & 36W POLES DAY 3 | MIDWAY-TEMBLOR & SSM 687,8,12 & 36W POLES DAY 3 | [13 empty] | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-07-10 | 2018-07-10 | 2018-07-10 | 2018-07-10 | 2018-07-10 | 2018-07-10 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29 | [7 empty] | 1Y TANKS, WJ8, 36W 4 CONSEC (6/11-6/14)
2018-06-03 | ASH OFF | SABRINA OFF | ERIKA OFF SAT & SUN | BLAINE OFF SUN | LEILANI OFF SAT & SUN | ANNA START | ODETTE START | BRETT START | SARAH OFF | RAINEY HSR | CODY HSR | Woody OFF | COLIN HSR SUB FOR WOODY | KAT OFF | BERRY 21Z N & S DAY 4 | BERRY 21Z N & S DAY 4 | BERRY 21Z N & S DAY 4 | BERRY 21Z N & S DAY 4 | BERRY 21Z N & S DAY 4 | BERRY 21Z N & S DAY 4 | CEMC 15G LEASE DAY 2 | CEMC 15G LEASE DAY 2 | CEMC 15G LEASE DAY 2 | EPC LANDFILL DAY 4 | EPC LANDFILL DAY 4 | [6 empty] | CYMRIC WATERLINE DAY 2 | CYMRIC WATERLINE DAY 2 | CYMRIC WATERLINE DAY 2 | CYMRIC WATERLINE DAY 2 | CYMRIC WATERLINE DAY 2 | CYMRIC WATERLINE DAY 2 | [15 empty] | 2018-06-26 | 2018-06-26 | 2018-06-26 | 2018-06-26 | 2018-06-26 | 2018-06-26 | 2018-07-11 | 2018-07-11 | 2018-07-11 | 2018-07-11 | 2018-07-11 | 2018-07-11 | 2018-06-30 | 2018-06-30 | 2018-06-30 | 2018-06-30 | 2018-06-30 | 2018-06-30 | 2018-06-30 | 2018-06-30 | 2018-06-30 | 2018-06-30
2018-06-04 | 3 Monitors/Week | ASH 2 DAYS/WEEK | 3 Monitors/Week | ERIKA 2 DAYS/WEEK | 3 Monitors/Week | GARRETT 2 DAYS/WEEK | ANASTACIA 3 DAYS/WEEK | ARACELI OFF | RAINEY HSR | CODY HSR | KOR 3 DAYS/WEEK | SAM FRI-SUN ONLY | KOSS 178 MORNING DR & EPC Landfill DAY 5 | KOSS 178 MORNING DR & EPC Landfill DAY 5 | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 5 | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 5 | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 5 | CEMC 1Y TANKS; WJ8 & 36W DAY 4 | CEMC 1Y TANKS; WJ8 & 36W DAY 4 | CEMC 1Y TANKS; WJ8 & 36W DAY 4 | SEC 11/13 GAUGES DAY 1 | SEC 11/13 GAUGES DAY 1 | SEC 11/13 GAUGES DAY 1 | SEC 11/13 GAUGES DAY 1 | SEC 11/13 GAUGES DAY 1 | SEC 11/13 GAUGES DAY 1 | ANTELLOPE SHALE & 7Z NOGO DAY 1 | ANTELLOPE SHALE & 7Z NOGO DAY 1 | ANTELLOPE SHALE & 7Z NOGO DAY 1 | 22G DRAINAGES DAY 1 | 22G DRAINAGES DAY 1 | CYMRIC WATERLINE DAY 3 | CYMRIC WATERLINE DAY 3 | CYMRIC WATERLINE DAY 3 | CYMRIC WATERLINE DAY 3 | CYMRIC WATERLINE DAY 3 | CYMRIC WATERLINE DAY 3 | CEMC 15G LEASE DAY 3 | CEMC 15G LEASE DAY 3 | CEMC 15G LEASE DAY 3 | [12 empty] | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-03 | 2018-07-03 | 2018-07-03
2018-06-05 | 3 Monitors/Week | ASH 2 DAYS/WEEK | 3 Monitors/Week | ERIKA 2 DAYS/WEEK | 3 Monitors/Week | GARRETT 2 DAYS/WEEK | RAINEY HSR | CODY HSR | [6 empty] | BERRY 21Z N&S DAY 5 | BERRY 21Z N&S DAY 5 | BERRY 21Z N&S DAY 5 | BERRY 21Z N&S DAY 5 | BERRY 21Z N&S DAY 5 | BERRY 21Z N&S DAY 5 | AERA MIDDLE BELRIDGE EAST DAY 4 | AERA MIDDLE BELRIDGE EAST DAY 4 | AERA MIDDLE BELRIDGE EAST DAY 4 | AERA MIDDLE BELRIDGE EAST DAY 4 | AERA MIDDLE BELRIDGE EAST DAY 4 | AERA MIDDLE BELRIDGE EAST DAY 4 | ANTELLOPE SHALE & 7Z NOGO DAY 2 | ANTELLOPE SHALE & 7Z NOGO DAY 2 | ANTELLOPE SHALE & 7Z NOGO DAY 2 | 22G DRAINAGES DAY 2 | 22G DRAINAGES DAY 2 | CYMRIC WATERLINE DAY 4 | CYMRIC WATERLINE DAY 4 | CYMRIC WATERLINE DAY 4 | CYMRIC WATERLINE DAY 4 | CYMRIC WATERLINE DAY 4 | CYMRIC WATERLINE DAY 4 | [15 empty] | 2018-07-06 | 2018-04-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-04 | 2018-07-04 | 2018-07-04
2018-06-06 | [9 empty] | CHEV LH SOLAR DAY 5 | CHEV LH SOLAR DAY 5 | CHEV LH SOLAR DAY 5 | CHEV LH SOLAR DAY 5 | CHEV LH SOLAR DAY 5 | CHEV LH SOLAR DAY 5 | CHEV LH SOLAR DAY 5 | CHEV LH SOLAR DAY 5 | STEVENS DINO & TILT DAY 3 | STEVENS DINO & TILT DAY 3 | STEVENS DINO & TILT DAY 3 | STEVENS DINO & TILT DAY 3 | BERRY HB 1200H; HB S32 DAY 4 | BERRY HB 1200H; HB S32 DAY 4 |  |  | TULARE-GATES PG&E POLES DAY 1 | TULARE-GATES PG&E POLES DAY 1 | ANTELLOPE SHALE & 7Z NOGO DAY 3 | ANTELLOPE SHALE & 7Z NOGO DAY 3 | ANTELLOPE SHALE & 7Z NOGO DAY 3 | 22G DRAINAGES DAY 3 | 22G DRAINAGES DAY 3 | AERA MIDDLE BELRIDGE WEST DAY 4 | AERA MIDDLE BELRIDGE WEST DAY 4 | AERA MIDDLE BELRIDGE WEST DAY 4 | AERA MIDDLE BELRIDGE WEST DAY 4 | AERA MIDDLE BELRIDGE WEST DAY 4 | AERA MIDDLE BELRIDGE WEST DAY 4 | AERA MIDDLE BELRIDGE WEST DAY 4 | AERA MIDDLE BELRIDGE WEST DAY 4 | [31 empty] | 2018-07-07 | 2018-07-07 | 2018-07-07 | [5 empty] | 36 W PAIRED W/ CYMRIC WATER LINE 7/3 | 36 W PAIRED W/ CYMRIC WATER LINE 7/3 | 7/1/2018 NOT 36W | 7/1/2018 NOT 36W | 7/1/2018 NOT 36W
2018-06-07 | 3 Monitors/Week | RAINEY HSR | CODY HSR | DAYNA OFF | [6 empty] | CEMC KRU, CHAP, GOVT2 DAY 5 | CEMC KRU, CHAP, GOVT2 DAY 5 | CEMC KRU, CHAP, GOVT2 DAY 5 | CEMC KRU, CHAP, GOVT2 DAY 5 | STEVENS DINO & TILT DAY 4 | STEVENS DINO & TILT DAY 4 | STEVENS DINO & TILT DAY 4 | STEVENS DINO & TILT DAY 4 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 1 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 1 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 1 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 1 |  |  | TULARE-GATES PG&E POLES DAY 2 | TULARE-GATES PG&E POLES DAY 2 | ANTELLOPE SHALE & 7Z NOGO DAY 4 | ANTELLOPE SHALE & 7Z NOGO DAY 4 | ANTELLOPE SHALE & 7Z NOGO DAY 4 | 22G DRAINAGES DAY 4 | 22G DRAINAGES DAY 4 | CEMC 15G LEASE DAY 4 | CEMC 15G LEASE DAY 4 | CEMC 15G LEASE DAY 4 | CEMC 30D; CHEV 2F DAY 3 | CEMC 30D; CHEV 2F DAY 3 | CHEV 32US EAST & SEC29 DAY 5 | CHEV 32US EAST & SEC29 DAY 5 | CHEV 32US EAST & SEC29 DAY 5 | CHEV 32US EAST & SEC29 DAY 5 | [12 empty] | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-29 | 2018-05-29 | SEC 22G DRAINAGES 4 CONSEC (6/5 -6/8) |  | 6/4 & 6/8 SEC 11 (6/4 & 6/8), SEC 13 ONLY (6/4) | 6/4 & 6/8 SEC 11 (6/4 & 6/8), SEC 13 ONLY (6/4) | 6/4 & 6/8 SEC 11 (6/4 & 6/8), SEC 13 ONLY (6/4) | 6/4 & 6/8 SEC 11 (6/4 & 6/8), SEC 13 ONLY (6/4) | 6/4 & 6/8 SEC 11 (6/4 & 6/8), SEC 13 ONLY (6/4) | 6/4 & 6/8 SEC 11 (6/4 & 6/8), SEC 13 ONLY (6/4) | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | TULARE-GATES 4 CONSEC (6/6 - 6/9) | [7 empty] | 2018-07-10 | 2018-07-10 | 2018-07-10
2018-06-08 | 3 Monitors/Week | WOODY HSR | DAYNA OFF | ANNA START | 3 Monitors/Week | RAINEY HSR | CODY HSR | 3 Monitors/Week | ODETTE START | SEC 11 WEST ONLY GAUGES DAY 1 |  |  | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 2 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 2 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 2 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 2 |  |  | COALINGA NOSE UNIT DAY 1 | COALINGA NOSE UNIT DAY 1 | COALINGA NOSE UNIT DAY 1 | COALINGA NOSE UNIT DAY 1 | COALINGA NOSE UNIT DAY 1 | COALINGA NOSE UNIT DAY 1 | COALINGA NOSE UNIT DAY 1 | COALINGA NOSE UNIT DAY 1 | COALINGA NOSE UNIT DAY 1 | COALINGA NOSE UNIT DAY 1 | TULARE-GATES PG&E POLES DAY 3 | TULARE-GATES PG&E POLES DAY 3 | CHEV 7S NORTH, 8S DAY 5 | CHEV 7S NORTH, 8S DAY 5 | CHEV 7S NORTH, 8S DAY 5 | CHEV 7S NORTH, 8S DAY 5 | CEMC 30D; CHEV 2F DAY 4 | CEMC 30D; CHEV 2F DAY 4 | CHEV 32US EAST & SEC29 DAY 6 | CHEV 32US EAST & SEC29 DAY 6 | CHEV 32US EAST & SEC29 DAY 6 | CHEV 32US EAST & SEC29 DAY 6 | [12 empty] | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-06-03 | 2018-06-03 | 2018-06-03 | 2018-05-30 | 2018-05-30 |  |  | SEC 11 & 13 GAUGES 4 CONSECUTIVE (6/10 - 6/13) | [5 empty] | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | [8 empty] | 2018-07-11 | 2018-07-11 | 2018-07-11
2018-06-09 | RAINEY HSR | CODY HSR | LEILANI OFF SAT & SUN | ERIKA OFF | BRETT START | ANNA START | ODETTE START |  |  | CEMC GAS COMPRESSOR/CWOD DAY 5 | CEMC GAS COMPRESSOR/CWOD DAY 5 | CEMC GAS COMPRESSOR/CWOD DAY 5 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 3 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 3 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 3 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 3 |  |  | COALINGA NOSE UNIT DAY 2 | COALINGA NOSE UNIT DAY 2 | COALINGA NOSE UNIT DAY 2 | COALINGA NOSE UNIT DAY 2 | COALINGA NOSE UNIT DAY 2 | COALINGA NOSE UNIT DAY 2 | COALINGA NOSE UNIT DAY 2 | COALINGA NOSE UNIT DAY 2 | COALINGA NOSE UNIT DAY 2 | COALINGA NOSE UNIT DAY 2 | TULARE-GATES PG&E POLES DAY 4 | TULARE-GATES PG&E POLES DAY 4 | CHEV 7S NORTH, 8S DAY 6 | CHEV 7S NORTH, 8S DAY 6 | CHEV 7S NORTH, 8S DAY 6 | CHEV 7S NORTH, 8S DAY 6 |  |  | CHEV 32US EAST & SEC29 DAY 7 | CHEV 32US EAST & SEC29 DAY 7 | CHEV 32US EAST & SEC29 DAY 7 | CHEV 32US EAST & SEC29 DAY 7 | [12 empty] | 5/21/2018 (TIMED OUT) | 5/21/2018 (TIMED OUT) | 5/21/2018 (TIMED OUT) | 5/21/2018 (TIMED OUT) | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-01 | 2018-06-01 | [8 empty] | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | [8 empty] | 2018-07-12 | 2018-07-12 | 2018-07-12
2018-06-10 | RAINEY HSR | CODY HSR | LEILANI OFF SAT & SUN | ERIKA OFF | BLAINE OFF SUN | ANNA START | SEC 11/13 GAUGES DAY 2 | SEC 11/13 GAUGES DAY 2 | SEC 11/13 GAUGES DAY 2 | SEC 11/13 GAUGES DAY 2 | SEC 11/13 GAUGES DAY 2 | SEC 11/13 GAUGES DAY 2 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 4 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 4 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 4 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 4 |  |  | COALINGA NOSE UNIT DAY 3 | COALINGA NOSE UNIT DAY 3 | COALINGA NOSE UNIT DAY 3 | COALINGA NOSE UNIT DAY 3 | COALINGA NOSE UNIT DAY 3 | COALINGA NOSE UNIT DAY 3 | COALINGA NOSE UNIT DAY 3 | COALINGA NOSE UNIT DAY 3 | COALINGA NOSE UNIT DAY 3 | COALINGA NOSE UNIT DAY 3 |  |  | CHEV 7S NORTH, 8S DAY 7 | CHEV 7S NORTH, 8S DAY 7 | CHEV 7S NORTH, 8S DAY 7 | CHEV 7S NORTH, 8S DAY 7 |  |  | CHEV 32US EAST & SEC29 DAY 8 | CHEV 32US EAST & SEC29 DAY 8 | CHEV 32US EAST & SEC29 DAY 8 | CHEV 32US EAST & SEC29 DAY 8 | [12 empty] | 2018-05-29 | 2018-05-29 | 2018-05-29 | 2018-05-29 | 2018-06-07 | 2018-06-07 | 2018-06-07 | [10 empty] | 2018-06-07 | 2018-06-07 | 2018-06-07 | 2018-06-07 |  |  |  | MARICOPA 12KV POLES DAY 1 | MARICOPA 12KV POLES DAY 1
2018-06-11 | 3 Monitors/Week | ASH 2 DAYS/WEEK | ODETTE START | CHEV 32US WEST & SEC5 DAY 5 | CHEV 32US WEST & SEC5 DAY 5 | CHEV 32US WEST & SEC5 DAY 5 | CHEV 32US WEST & SEC5 DAY 5 | CEMC 15G LEASE DAY 5 | CEMC 15G LEASE DAY 5 | CEMC 15G LEASE DAY 5 | CHEV MWSS 26F, 23F DAY 5 | CHEV MWSS 26F, 23F DAY 5 | CHEV MWSS 26F, 23F DAY 5 | CHEV MWSS 26F, 23F DAY 5 | CHEV MWSS 26F, 23F DAY 5 | CEMC 1Y TANKS; WJ8 & 36W DAY 5 | CEMC 1Y TANKS; WJ8 & 36W DAY 5 | CEMC 1Y TANKS; WJ8 & 36W DAY 5 | COALINGA NOSE UNIT DAY 4 | COALINGA NOSE UNIT DAY 4 | COALINGA NOSE UNIT DAY 4 | COALINGA NOSE UNIT DAY 4 | COALINGA NOSE UNIT DAY 4 | COALINGA NOSE UNIT DAY 4 | COALINGA NOSE UNIT DAY 4 | COALINGA NOSE UNIT DAY 4 | COALINGA NOSE UNIT DAY 4 | COALINGA NOSE UNIT DAY 4 |  |  | CHEV 7S NORTH, 8S DAY 8 | CHEV 7S NORTH, 8S DAY 8 | CHEV 7S NORTH, 8S DAY 8 | CHEV 7S NORTH, 8S DAY 8 | SEC 11/13 GAUGES DAY 3 | SEC 11/13 GAUGES DAY 3 | SEC 11/13 GAUGES DAY 3 | SEC 11/13 GAUGES DAY 3 | SEC 11/13 GAUGES DAY 3 | SEC 11/13 GAUGES DAY 3 | [12 empty] | 2018-04-25: CHEV 32US EAST & SEC 29 4 CONSECUTIVE (6/7 - 6/10); 2018-05-28: CEMC 15G LEASE 4 CONSEC (6/12 - 6/15) | 2018-06-21 | 2018-06-21 | [6 empty] | STEVENS DINO & TILT 4 CONSECUTIVE (6/15 - 6/18) |  |  |  | TULARE-GATES PG&E POLES DAY 5 | TULARE-GATES PG&E POLES DAY 5 |  | MARICOPA 12KV POLES DAY 2 | MARICOPA 12KV POLES DAY 2
2018-06-12 | 3 Monitors/Week | ASH 2 DAYS/WEEK | ODETTE START | ERIKA OFF | 3 Monitors/Week | GARRETT 2 DAYS/WEEK | ANNA START | CEMC 15G LEASE DAY 6 | CEMC 15G LEASE DAY 6 | CEMC 15G LEASE DAY 6 | CHEV MWSS 26F, 23F DAY 6 | CHEV MWSS 26F, 23F DAY 6 | CHEV MWSS 26F, 23F DAY 6 | CHEV MWSS 26F, 23F DAY 6 | CHEV MWSS 26F, 23F DAY 6 | CEMC 1Y TANKS; WJ8 & 36W DAY 6 | CEMC 1Y TANKS; WJ8 & 36W DAY 6 | CEMC 1Y TANKS; WJ8 & 36W DAY 6 | SEC 11/13 GAUGES DAY 4 | SEC 11/13 GAUGES DAY 4 | SEC 11/13 GAUGES DAY 4 | SEC 11/13 GAUGES DAY 4 | SEC 11/13 GAUGES DAY 4 | SEC 11/13 GAUGES DAY 4 | AERA MIDDLE BELRIDGE WEST DAY 5 | AERA MIDDLE BELRIDGE WEST DAY 5 | AERA MIDDLE BELRIDGE WEST DAY 5 | AERA MIDDLE BELRIDGE WEST DAY 5 | AERA MIDDLE BELRIDGE WEST DAY 5 | AERA MIDDLE BELRIDGE WEST DAY 5 | AERA MIDDLE BELRIDGE WEST DAY 5 | AERA MIDDLE BELRIDGE WEST DAY 5 | [20 empty] | 2018-05-29: NERC SSM 523-534 & 632-642 Day 6; 2018-05-29: NERC SSM 523-534 & 632-642 Day 6 | 2018-07-03 | 2018-07-03 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 |  |  |  |  | TULARE-GATES PG&E POLES DAY 6 | TULARE-GATES PG&E POLES DAY 6 |  | MARICOPA 12KV POLES DAY 3 | MARICOPA 12KV POLES DAY 3
2018-06-13 | 3 Monitors/Week | 3 Monitors/Week | ODETTE START | ANNA START |  |  |  | CEMC 15G LEASE DAY 7 | CEMC 15G LEASE DAY 7 | CEMC 15G LEASE DAY 7 | CHEV MWSS 26F, 23F DAY 7 | CHEV MWSS 26F, 23F DAY 7 | CHEV MWSS 26F, 23F DAY 7 | CHEV MWSS 26F, 23F DAY 7 | CHEV MWSS 26F, 23F DAY 7 | CEMC 1Y TANKS; WJ8 & 36W DAY 7 | CEMC 1Y TANKS; WJ8 & 36W DAY 7 | CEMC 1Y TANKS; WJ8 & 36W DAY 7 | SEC 11/13 GAUGES DAY 5 | SEC 11/13 GAUGES DAY 5 | SEC 11/13 GAUGES DAY 5 | SEC 11/13 GAUGES DAY 5 | SEC 11/13 GAUGES DAY 5 | SEC 11/13 GAUGES DAY 5 | AERA MIDDLE BELRIDGE WEST DAY 6 | AERA MIDDLE BELRIDGE WEST DAY 6 | AERA MIDDLE BELRIDGE WEST DAY 6 | AERA MIDDLE BELRIDGE WEST DAY 6 | AERA MIDDLE BELRIDGE WEST DAY 6 | AERA MIDDLE BELRIDGE WEST DAY 6 | AERA MIDDLE BELRIDGE WEST DAY 6 | AERA MIDDLE BELRIDGE WEST DAY 6 | CHEV 25 HILL N DAY 5 | CHEV 25 HILL N DAY 5 | CHEV 25 HILL N DAY 5 | CHEV 25 HILL N DAY 5 | CHEV 25 HILL N DAY 5 | CHEV 25 HILL N DAY 5 | CHEV 25 HILL N DAY 5 | [22 empty] | 2018-07-04 | 2018-07-04 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 |  |  |  |  | TULARE-GATES PG&E POLES DAY 7 | TULARE-GATES PG&E POLES DAY 7 |  | MARICOPA 12KV POLES DAY 4 | MARICOPA 12KV POLES DAY 4 | bar: 2018-04-25 to 2018-05-28
2018-06-14 | 3 Monitors/Week |  | ODETTE START |  | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 6 | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 6 | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 6 | CEMC 15G LEASE DAY 8 | CEMC 15G LEASE DAY 8 | CEMC 15G LEASE DAY 8 | CHEV MWSS 26F, 23F DAY 8 | CHEV MWSS 26F, 23F DAY 8 | CHEV MWSS 26F, 23F DAY 8 | CHEV MWSS 26F, 23F DAY 8 | CHEV MWSS 26F, 23F DAY 8 | CEMC 1Y TANKS; WJ8 & 36W DAY 8 | CEMC 1Y TANKS; WJ8 & 36W DAY 8 | CEMC 1Y TANKS; WJ8 & 36W DAY 8 | CEMC 30D; CHEV 2F DAY 5 | CEMC 30D; CHEV 2F DAY 5 |  |  | AERA MIDDLE BELRIDGE WEST DAY 7 | AERA MIDDLE BELRIDGE WEST DAY 7 | AERA MIDDLE BELRIDGE WEST DAY 7 | AERA MIDDLE BELRIDGE WEST DAY 7 | AERA MIDDLE BELRIDGE WEST DAY 7 | AERA MIDDLE BELRIDGE WEST DAY 7 | AERA MIDDLE BELRIDGE WEST DAY 7 | AERA MIDDLE BELRIDGE WEST DAY 7 | CHEV 25 HILL N DAY 6 | CHEV 25 HILL N DAY 6 | CHEV 25 HILL N DAY 6 | CHEV 25 HILL N DAY 6 | CHEV 25 HILL N DAY 6 | CHEV 25 HILL N DAY 6 | CHEV 25 HILL N DAY 6 | [24 empty] | 2018-07-07 | 2018-07-07 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 |  |  |  |  | TULARE-GATES PG&E POLES DAY 8 | TULARE-GATES PG&E POLES DAY 8 |  | MARICOPA 12KV POLES DAY 5 | MARICOPA 12KV POLES DAY 5 | bar: 2018-04-25 to 2018-05-28
2018-06-15 | 3 Monitors/Week |  | ODETTE START |  | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 7 | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 7 | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 7 | CHEV 7S WEST DAY 5 | CHEV 7S WEST DAY 5 | CHEV 7S WEST DAY 5 | CHEV 7S WEST DAY 5 | CEMC 30D; CHEV 2F DAY 6 | CEMC 30D; CHEV 2F DAY 6 | STEVENS DINO & TILT DAY 5 | STEVENS DINO & TILT DAY 5 | STEVENS DINO & TILT DAY 5 | STEVENS DINO & TILT DAY 5 | AERA MIDDLE BELRIDGE WEST DAY 8 | AERA MIDDLE BELRIDGE WEST DAY 8 | AERA MIDDLE BELRIDGE WEST DAY 8 | AERA MIDDLE BELRIDGE WEST DAY 8 | AERA MIDDLE BELRIDGE WEST DAY 8 | AERA MIDDLE BELRIDGE WEST DAY 8 | AERA MIDDLE BELRIDGE WEST DAY 8 | AERA MIDDLE BELRIDGE WEST DAY 8 | CHEV 25 HILL N DAY 7 | CHEV 25 HILL N DAY 7 | CHEV 25 HILL N DAY 7 | CHEV 25 HILL N DAY 7 | CHEV 25 HILL N DAY 7 | CHEV 25 HILL N DAY 7 | CHEV 25 HILL N DAY 7 | EPC LANDFILL DAY 3 | EPC LANDFILL DAY 3 | [18 empty] | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-27 | 2018-06-27 | 2018-06-27 |  |  | 2018-07-11 | 2018-07-11 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-06-26 | 2018-06-26 | 2018-06-26 | 2018-06-26 | 2018-07-06 | 2018-07-09 |  | MARICOPA 12KV POLES DAY 6 | MARICOPA 12KV POLES DAY 6
2018-06-16 | ANNA START | ERIKA OFF SAT & SUN | RAINEY HSR | CODY HSR | KORISSA OFF | LEILANI OFF SAT & SUN | KIM WORKSHOP | [5 empty] | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 8 | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 8 | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 8 | CEMC 30D; CHEV 2F DAY 7 | CEMC 30D; CHEV 2F DAY 7 | STEVENS DINO & TILT DAY 6 | STEVENS DINO & TILT DAY 6 | STEVENS DINO & TILT DAY 6 | STEVENS DINO & TILT DAY 6 | CEMC 6SF, 7S, D-06 DAY 1 | CEMC 6SF, 7S, D-06 DAY 1 | BERRY HB 1200H; HB S32 DAY 5 | BERRY HB 1200H; HB S32 DAY 5 | CHEV 25 HILL N DAY 8 | CHEV 25 HILL N DAY 8 | CHEV 25 HILL N DAY 8 | CHEV 25 HILL N DAY 8 | CHEV 25 HILL N DAY 8 | CHEV 25 HILL N DAY 8 | CHEV 25 HILL N DAY 8 | CHEV LH SOLAR DAY 6 | CHEV LH SOLAR DAY 6 | CHEV LH SOLAR DAY 6 | CHEV LH SOLAR DAY 6 | CHEV LH SOLAR DAY 6 | CHEV LH SOLAR DAY 6 | CHEV LH SOLAR DAY 6 | CHEV LH SOLAR DAY 6 | MIDWAY-TEMBLOR & SSM 687,8,12 POLES DAY 6 | MIDWAY-TEMBLOR & SSM 687,8,12 POLES DAY 6 | [10 empty] | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-07-03 | 2018-07-03 | 2018-07-03 |  |  | 2018-07-12 | 2018-07-12 | 2018-07-11 | 2018-07-11 | 2018-07-11 | 2018-07-11 | 2018-07-11 | 2018-07-11 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-07 | 2018-07-07
2018-06-17 | ANNA START | ERIKA OFF SAT & SUN | RAINEY HSR | CODY HSR | KORISSA OFF | LEILANI OFF SAT & SUN | SARAH OFF SUN | KIM WORKSHOP | CHEV 32US WEST & SEC5 DAY 6 | CHEV 32US WEST & SEC5 DAY 6 | CHEV 32US WEST & SEC5 DAY 6 | CHEV 32US WEST & SEC5 DAY 6 | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 9 | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 9 | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 9 | CEMC 30D; CHEV 2F DAY 8 | CEMC 30D; CHEV 2F DAY 8 | STEVENS DINO & TILT DAY 7 | STEVENS DINO & TILT DAY 7 | STEVENS DINO & TILT DAY 7 | STEVENS DINO & TILT DAY 7 | CEMC 6SF, 7S, D-06 DAY 2 | CEMC 6SF, 7S, D-06 DAY 2 | BERRY HB 1200H; HB S32 DAY 6 | BERRY HB 1200H; HB S32 DAY 6 | CHEV LH SOLAR DAY 7 | CHEV LH SOLAR DAY 7 | CHEV LH SOLAR DAY 7 | CHEV LH SOLAR DAY 7 | CHEV LH SOLAR DAY 7 | CHEV LH SOLAR DAY 7 | CHEV LH SOLAR DAY 7 | CHEV LH SOLAR DAY 7 | BERRY O-P N, O-P S, TRAP & PAN DAY 5 | BERRY O-P N, O-P S, TRAP & PAN DAY 5 | BERRY O-P N, O-P S, TRAP & PAN DAY 5 | BERRY O-P N, O-P S, TRAP & PAN DAY 5 | [15 empty] | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-07-04 | 2018-07-04 | 2018-07-04 |  |  | 2018-07-13 | 2018-07-13 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-08 | 2018-07-08
2018-06-18 | 3 Monitors/Week | ASH 2 DAYS/WEEK | ERIKA 2 DAYS/WEEK | 3 Monitors/Week | GARRETT 2 DAYS/WEEK | 3 Monitors/Week | ANASTACIA 3 DAYS/WEEK | ARACELI OFF | RAINEY HSR | CEMC 6SF, 7S, D-06 DAY 3 | CEMC 6SF, 7S, D-06 DAY 3 | CHEV 7S NORTH, 8S DAY 9 (6/10 OR LATER) | CHEV 7S NORTH, 8S DAY 9 (6/10 OR LATER) | CHEV 7S NORTH, 8S DAY 9 (6/10 OR LATER) | CHEV 7S NORTH, 8S DAY 9 (6/10 OR LATER) |  |  | STEVENS DINO & TILT DAY 8 | STEVENS DINO & TILT DAY 8 | STEVENS DINO & TILT DAY 8 | STEVENS DINO & TILT DAY 8 | BERRY HB 1200H; HB S32 DAY 7 | BERRY HB 1200H; HB S32 DAY 7 | AERA MIDDLE BELRIDGE EAST DAY 5 | AERA MIDDLE BELRIDGE EAST DAY 5 | AERA MIDDLE BELRIDGE EAST DAY 5 | AERA MIDDLE BELRIDGE EAST DAY 5 | AERA MIDDLE BELRIDGE EAST DAY 5 | AERA MIDDLE BELRIDGE EAST DAY 5 | NERC SSM 523-534 & 632-642 Day 4 | NERC SSM 523-534 & 632-642 Day 4 | MIDWAY-TEMBLOR & SSM 687,8,12 & 36W POLES DAY 4 | MIDWAY-TEMBLOR & SSM 687,8,12 & 36W POLES DAY 4 | CHEV 7S WEST DAY 6 | CHEV 7S WEST DAY 6 | CHEV 7S WEST DAY 6 | CHEV 7S WEST DAY 6 | CHEV CO 23D DAY 7 | CHEV CO 23D DAY 7 | CHEV CO 23D DAY 7 | CHEV CO 23D DAY 7 | CHEV CO 23D DAY 7 | CHEV CO 23D DAY 7 | CHEV CO 23D DAY 7 | [8 empty] | 2018-06-30 | 2018-06-30 | 2018-06-30 | 2018-06-30 | 2018-07-13 | 2018-07-13 | 2018-07-13 |  |  | 2018-07-14 | 2018-07-14 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-09 | 2018-07-09
2018-06-19 | 3 Monitors/Week | ASH 2 DAYS/WEEK | ERIKA 2 DAYS/WEEK | 3 Monitors/Week | GARRETT 2 DAYS/WEEK | 3 Monitors/Week | ANASTACIA 3 DAYS/WEEK | RAINEY HSR | CODY HSR | KOR 3 DAYS/WEEK | SAM FRI-SUN ONLY | CEMC 6SF, 7S, D-06 DAY 4 | CEMC 6SF, 7S, D-06 DAY 4 | CHEV LH SOLAR DAY 8 | CHEV LH SOLAR DAY 8 | CHEV LH SOLAR DAY 8 | CHEV LH SOLAR DAY 8 | CHEV LH SOLAR DAY 8 | CHEV LH SOLAR DAY 8 | CHEV LH SOLAR DAY 8 | CHEV LH SOLAR DAY 8 | BERRY HB 1200H; HB S32 DAY 8 | BERRY HB 1200H; HB S32 DAY 8 | AERA MIDDLE BELRIDGE EAST DAY 6 | AERA MIDDLE BELRIDGE EAST DAY 6 | AERA MIDDLE BELRIDGE EAST DAY 6 | AERA MIDDLE BELRIDGE EAST DAY 6 | AERA MIDDLE BELRIDGE EAST DAY 6 | AERA MIDDLE BELRIDGE EAST DAY 6 |  |  | MIDWAY-TEMBLOR & SSM 687,8,12 & 36W POLES DAY 5 | MIDWAY-TEMBLOR & SSM 687,8,12 & 36W POLES DAY 5 | CHEV 7S WEST DAY 7 | CHEV 7S WEST DAY 7 | CHEV 7S WEST DAY 7 | CHEV 7S WEST DAY 7 | CHEV CO 23D DAY 8 | CHEV CO 23D DAY 8 | CHEV CO 23D DAY 8 | CHEV CO 23D DAY 8 | CHEV CO 23D DAY 8 | CHEV CO 23D DAY 8 | CHEV CO 23D DAY 8 | [8 empty] | 2018-04-25: TRANSECTS 15-23 ONLY (7/7); 2018-04-25: TRANSECTS 15-23 ONLY (7/7)
2018-06-20 | 3 Monitors/Week | RAINEY HSR | CODY HSR | KOR 3 DAYS/WEEK | 3 Monitors/Week | 3 Monitors/Week | SAM FRI-SUN ONLY | WOODY HSR | ANASTACIA 3 DAYS/WEEK | CYMRIC WATERLINE DAY 5 | CYMRIC WATERLINE DAY 5 | CYMRIC WATERLINE DAY 5 | CYMRIC WATERLINE DAY 5 | CYMRIC WATERLINE DAY 5 | CYMRIC WATERLINE DAY 5 | CHEV LH SOLAR DAY 9 (6/15 OR LATER | CHEV LH SOLAR DAY 9 (6/15 OR LATER | CHEV LH SOLAR DAY 9 (6/15 OR LATER | CHEV LH SOLAR DAY 9 (6/15 OR LATER | CHEV LH SOLAR DAY 9 (6/15 OR LATER | CHEV LH SOLAR DAY 9 (6/15 OR LATER | CHEV LH SOLAR DAY 9 (6/15 OR LATER | CHEV LH SOLAR DAY 9 (6/15 OR LATER | AERA MIDDLE BELRIDGE EAST DAY 7 | AERA MIDDLE BELRIDGE EAST DAY 7 | AERA MIDDLE BELRIDGE EAST DAY 7 | AERA MIDDLE BELRIDGE EAST DAY 7 | AERA MIDDLE BELRIDGE EAST DAY 7 | AERA MIDDLE BELRIDGE EAST DAY 7 | NERC SSM 523-534 & 632-642 Day 5 | NERC SSM 523-534 & 632-642 Day 5 |  |  | CHEV 7S WEST DAY 8 | CHEV 7S WEST DAY 8 | CHEV 7S WEST DAY 8 | CHEV 7S WEST DAY 8 | CHEV CO 23D DAY 9 (6/13 OR LATER) | CHEV CO 23D DAY 9 (6/13 OR LATER) | CHEV CO 23D DAY 9 (6/13 OR LATER) | CHEV CO 23D DAY 9 (6/13 OR LATER) | CHEV CO 23D DAY 9 (6/13 OR LATER) | CHEV CO 23D DAY 9 (6/13 OR LATER) | CHEV CO 23D DAY 9 (6/13 OR LATER) | [8 empty] | 2018-04-25: COALINGA NOSE UNIT 4 CONSECUTIVE (6/8 - 6/11) High wind 6/10 |  | ANTELLOPE SHALE & 7Z NOGO 4 CONSECUTIVE (6/4 - 6/7) |  |  | CYMRIC WATERLINE 4 CONSECUTIVE (6/2 - 6/5)
2018-06-21 | 3 Monitors/Week | RAINEY HSR | CODY HSR | 3 Monitors/Week | SAM FRI-SUN ONLY | WOODY HSR | KAT OFF (6/11-24) | 3 Monitors/Week | ANNA ORIENTATION | KAITLYN OFF | JAMIE HSR | CEMC NMWSS BRINE DISPOSAL ONLY DAY 1 | CEMC NMWSS BRINE DISPOSAL ONLY DAY 1 | CEMC NMWSS BRINE DISPOSAL ONLY DAY 1 | CEMC NMWSS BRINE DISPOSAL ONLY DAY 1 | CEMC KRU, CHAP, GOVT2 DAY 6 | CEMC KRU, CHAP, GOVT2 DAY 6 | CEMC KRU, CHAP, GOVT2 DAY 6 | CEMC KRU, CHAP, GOVT2 DAY 6 | CHEV 32US EAST & SEC29 DAY 9 (5/25 OR LATER) | CHEV 32US EAST & SEC29 DAY 9 (5/25 OR LATER) | CHEV 32US EAST & SEC29 DAY 9 (5/25 OR LATER) | CHEV 32US EAST & SEC29 DAY 9 (5/25 OR LATER) | AERA MIDDLE BELRIDGE EAST DAY 8 | AERA MIDDLE BELRIDGE EAST DAY 9 | AERA MIDDLE BELRIDGE EAST DAY 10 | AERA MIDDLE BELRIDGE EAST DAY 11 | AERA MIDDLE BELRIDGE EAST DAY 12 | AERA MIDDLE BELRIDGE EAST DAY 13 | CHEV S25, CHANSELOR DAY 5 | CHEV S25, CHANSELOR DAY 5 | CHEV S25, CHANSELOR DAY 5 | 22G DRAINAGES DAY 5 | 22G DRAINAGES DAY 5 | 27G DRAINAGES & 23L DAY 5 | 27G DRAINAGES & 23L DAY 5 |  | CHEV CO 23D DAY 10 (6/14 OR LATER) | CHEV CO 23D DAY 10 (6/14 OR LATER) | CHEV CO 23D DAY 10 (6/14 OR LATER) | CHEV CO 23D DAY 10 (6/14 OR LATER) | CHEV CO 23D DAY 10 (6/14 OR LATER) | CHEV CO 23D DAY 10 (6/14 OR LATER) | CHEV CO 23D DAY 10 (6/14 OR LATER) | CEMC 6SF, 7S, D-06 DAY 5 | CEMC 6SF, 7S, D-06 DAY 5
2018-06-22 | 3 Monitors/Week | RAINEY HSR | CODY HSR | 3 Monitors/Week | 3 Monitors/Week | WOODY HSR | KAT OFF (6/11-24) | LEILANI OFF |  |  | COALINGA NOSE UNIT DAY 5 | COALINGA NOSE UNIT DAY 5 | COALINGA NOSE UNIT DAY 5 | COALINGA NOSE UNIT DAY 5 | COALINGA NOSE UNIT DAY 5 | COALINGA NOSE UNIT DAY 5 | COALINGA NOSE UNIT DAY 5 | COALINGA NOSE UNIT DAY 5 | COALINGA NOSE UNIT DAY 5 | COALINGA NOSE UNIT DAY 5 | CHEV 32US EAST & SEC29 DAY 10 (5/26 OR LATER) | CHEV 32US EAST & SEC29 DAY 10 (5/26 OR LATER) | CHEV 32US EAST & SEC29 DAY 10 (5/26 OR LATER) | CHEV 32US EAST & SEC29 DAY 10 (5/26 OR LATER) | CHEV 25 HILL S DAY 6 | CHEV HILL S DAY 6 | CHEV 25 HILL S DAY 6 |  |  | CHEV S25, CHANSELOR DAY 6 | CHEV S25, CHANSELOR DAY 6 | CHEV S25, CHANSELOR DAY 6 | SEC 11/13 GAUGES DAY 6 | SEC 11/13 GAUGES DAY 6 | SEC 11/13 GAUGES DAY 6 | SEC 11/13 GAUGES DAY 6 | SEC 11/13 GAUGES DAY 6 | SEC 11/13 GAUGES DAY 6 | AERA CAL SO PIPE DAY 5 | AERA CAL SO PIPE DAY 5 | AERA CAL SO PIPE DAY 5 | AERA CAL SO PIPE DAY 5 | AERA CAL SO PIPE DAY 5 | AERA CAL SO PIPE DAY 5 | CEMC 6SF, 7S, D-06 DAY 6 | CEMC 6SF, 7S, D-06 DAY 6
2018-06-23 | [9 empty] | COALINGA NOSE UNIT DAY 6 | COALINGA NOSE UNIT DAY 6 | COALINGA NOSE UNIT DAY 6 | COALINGA NOSE UNIT DAY 6 | COALINGA NOSE UNIT DAY 6 | COALINGA NOSE UNIT DAY 6 | COALINGA NOSE UNIT DAY 6 | COALINGA NOSE UNIT DAY 6 | COALINGA NOSE UNIT DAY 6 | COALINGA NOSE UNIT DAY 6 | CEMC KRU, CHAP, GOVT2 DAY 7 | CEMC KRU, CHAP, GOVT2 DAY 7 | CEMC KRU, CHAP, GOVT2 DAY 7 | CEMC KRU, CHAP, GOVT2 DAY 7 | ANTELLOPE SHALE & 7Z NOGO DAY 5 | ANTELLOPE SHALE & 7Z NOGO DAY 5 | ANTELLOPE SHALE & 7Z NOGO DAY 5 |  |  |  | CHEV S25, CHANSELOR DAY 7 | CHEV S25, CHANSELOR DAY 7 | CHEV S25, CHANSELOR DAY 7 | SEC 11/13 GAUGES DAY 7 | SEC 11/13 GAUGES DAY 7 | SEC 11/13 GAUGES DAY 7 | SEC 11/13 GAUGES DAY 7 | SEC 11/13 GAUGES DAY 7 | SEC 11/13 GAUGES DAY 7 | CHEV 32US WEST & SEC5 DAY 7 | CHEV 32US WEST & SEC5 DAY 7 | CHEV 32US WEST & SEC5 DAY 7 | CHEV 32US WEST & SEC5 DAY 7
2018-06-24 | RAINEY HSR | CODY HSR | ANASTACIA OFF | ERIKA OFF SAT & SUN | KAT OFF (6/11-24) | LEILANI OFF SAT & SUN | CEMC GAS COMPRESSOR/CWOD DAY 6 | CEMC GAS COMPRESSOR/CWOD DAY 6 | CEMC GAS COMPRESSOR/CWOD DAY 6 | COALINGA NOSE UNIT DAY 7 | COALINGA NOSE UNIT DAY 7 | COALINGA NOSE UNIT DAY 7 | COALINGA NOSE UNIT DAY 7 | COALINGA NOSE UNIT DAY 7 | COALINGA NOSE UNIT DAY 7 | COALINGA NOSE UNIT DAY 7 | COALINGA NOSE UNIT DAY 7 | COALINGA NOSE UNIT DAY 7 | COALINGA NOSE UNIT DAY 7 | CEMC KRU, CHAP, GOVT2 DAY 8 | CEMC KRU, CHAP, GOVT2 DAY 8 | CEMC KRU, CHAP, GOVT2 DAY 8 | CEMC KRU, CHAP, GOVT2 DAY 8 | ANTELLOPE SHALE & 7Z NOGO DAY 6 | ANTELLOPE SHALE & 7Z NOGO DAY 6 | ANTELLOPE SHALE & 7Z NOGO DAY 6 |  |  |  | CHEV S25, CHANSELOR DAY 8 | CHEV S25, CHANSELOR DAY 8 | CHEV S25, CHANSELOR DAY 8 | SEC 11/13 GAUGES DAY 8 | SEC 11/13 GAUGES DAY 8 | SEC 11/13 GAUGES DAY 8 | SEC 11/13 GAUGES DAY 8 | SEC 11/13 GAUGES DAY 8 | SEC 11/13 GAUGES DAY 8 | KOSS 178 MORNING DR & EPC Landfill DAY 6 | KOSS 178 MORNING DR & EPC Landfill DAY 6 | [12 empty] | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20
2018-06-25 | 3 Monitors/Week | ASH 2 DAYS/WEEK | ERIKA 2 DAYS/WEEK | 3 Monitors/Week | GARRETT 2 DAYS/WEEK | 3 Monitors/Week | ANTELLOPE SHALE & 7Z NOGO DAY 7 | ANTELLOPE SHALE & 7Z NOGO DAY 7 | ANTELLOPE SHALE & 7Z NOGO DAY 7 | CODY HSR | KOR 3 DAYS/WEEK | SAM FRI-SUN ONLY | WOODY HSR | AERA MIDDLE BELRIDGE EAST DAY 9 (6/10 OR LATER) | AERA MIDDLE BELRIDGE EAST DAY 9 (6/10 OR LATER) | AERA MIDDLE BELRIDGE EAST DAY 9 (6/10 OR LATER) | AERA MIDDLE BELRIDGE EAST DAY 9 (6/10 OR LATER) | AERA MIDDLE BELRIDGE EAST DAY 9 (6/10 OR LATER) | AERA MIDDLE BELRIDGE EAST DAY 9 (6/10 OR LATER) | CHEV 32US EAST & SEC29 DAY 11 (6/20 OR LESS) | CHEV 32US EAST & SEC29 DAY 11 (6/20 OR LESS) | CHEV 32US EAST & SEC29 DAY 11 (6/20 OR LESS) | CHEV 32US EAST & SEC29 DAY 11 (6/20 OR LESS) | BERRY 21Z N&S DAY 6 | BERRY 21Z N&S DAY 6 | BERRY 21Z N&S DAY 6 | BERRY 21Z N&S DAY 6 | BERRY 21Z N&S DAY 6 | BERRY 21Z N&S DAY 6 | COALINGA NOSE UNIT DAY 8 | COALINGA NOSE UNIT DAY 8 | COALINGA NOSE UNIT DAY 8 | COALINGA NOSE UNIT DAY 8 | COALINGA NOSE UNIT DAY 8 | COALINGA NOSE UNIT DAY 8 | COALINGA NOSE UNIT DAY 8 | COALINGA NOSE UNIT DAY 8 | COALINGA NOSE UNIT DAY 8 | COALINGA NOSE UNIT DAY 8 | KOSS 178 MORNING DR & EPC Landfill DAY 7 | KOSS 178 MORNING DR & EPC Landfill DAY 7 | PG&E Tulare Gates | PG&E Tulare Gates | PG&E Tulare Gates | PG&E Tulare Gates | CJ off | Brit off | Araceli off | BERRY O-P N, O-P S, TRAP & PAN DAY 6 | BERRY O-P N, O-P S, TRAP & PAN DAY 6 | BERRY O-P N, O-P S, TRAP & PAN DAY 6 | BERRY O-P N, O-P S, TRAP & PAN DAY 6 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28
2018-06-26 | 3 Monitors/Week | ASH 2 DAYS/WEEK | ERIKA 2 DAYS/WEEK | 3 Monitors/Week | GARRETT 2 DAYS/WEEK | 3 Monitors/Week | ANASTACIA 3 DAYS/WEEK | GILLIAN OFF BY 1 | RAINEY HSR | CODY HSR | KOR 3 DAYS/WEEK | SAM FRI-SUN ONLY | WOODY HSR | AERA MIDDLE BELRIDGE EAST DAY 10 (6/13 OR LATER) | AERA MIDDLE BELRIDGE EAST DAY 10 (6/13 OR LATER) | AERA MIDDLE BELRIDGE EAST DAY 10 (6/13 OR LATER) | AERA MIDDLE BELRIDGE EAST DAY 10 (6/13 OR LATER) | AERA MIDDLE BELRIDGE EAST DAY 10 (6/13 OR LATER) | AERA MIDDLE BELRIDGE EAST DAY 10 (6/13 OR LATER) | STEVENS DINO & TILT DAY 9 (6/26 OR LATER) | STEVENS DINO & TILT DAY 9 (6/26 OR LATER) | STEVENS DINO & TILT DAY 9 (6/26 OR LATER) | STEVENS DINO & TILT DAY 9 (6/26 OR LATER) | BERRY 21Z N&S DAY 7 | BERRY 21Z N&S DAY 7 | BERRY 21Z N&S DAY 7 | BERRY 21Z N&S DAY 7 | BERRY 21Z N&S DAY 7 | BERRY 21Z N&S DAY 7 | CHEV LH SOLAR DAY 10 (6/16 OR LATER) | CHEV LH SOLAR DAY 10 (6/16 OR LATER) | CHEV LH SOLAR DAY 10 (6/16 OR LATER) | CHEV LH SOLAR DAY 10 (6/16 OR LATER) | CHEV LH SOLAR DAY 10 (6/16 OR LATER) | CHEV LH SOLAR DAY 10 (6/16 OR LATER) | CHEV LH SOLAR DAY 10 (6/16 OR LATER) | CHEV LH SOLAR DAY 10 (6/16 OR LATER) | CHEV 25 HILL S DAY 7 | CHEV HILL S DAY 7 | CHEV 25 HILL S DAY 7 | KOSS 178 MORNING DR & EPC Landfill DAY 8 | KOSS 178 MORNING DR & EPC Landfill DAY 8 | PG&E Tulare Gates | PG&E Tulare Gates | PG&E Tulare Gates | PG&E Tulare Gates | CJ off | Brit off | BERRY O-P N, O-P S, TRAP & PAN DAY 7 | BERRY O-P N, O-P S, TRAP & PAN DAY 7 | BERRY O-P N, O-P S, TRAP & PAN DAY 7 | BERRY O-P N, O-P S, TRAP & PAN DAY 7 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29
2018-06-27 | 3 Monitors/Week | 3 Monitors/Week | 3 Monitors/Week | RAINEY HSR | CODY HSR | ANASTACIA 3 DAYS/WEEK | KOR 3 DAYS/WEEK | SAM FRI-SUN ONLY | WOODY HSR | JAMIE HSR | CEMC 15G LEASE DAY 9 (6/27 OR LATER) | CEMC 15G LEASE DAY 9 (6/27 OR LATER) | CEMC 15G LEASE DAY 9 (6/27 OR LATER) |  |  | CEMC NMWSS BRINE DISPOSAL ONLY DAY 2 | CEMC NMWSS BRINE DISPOSAL ONLY DAY 2 | CEMC NMWSS BRINE DISPOSAL ONLY DAY 2 | CEMC NMWSS BRINE DISPOSAL ONLY DAY 2 | AERA MIDDLE BELRIDGE WEST DAY 9 (6/21 OR LATER) | AERA MIDDLE BELRIDGE WEST DAY 9 (6/21 OR LATER) | AERA MIDDLE BELRIDGE WEST DAY 9 (6/21 OR LATER) | AERA MIDDLE BELRIDGE WEST DAY 9 (6/21 OR LATER) | AERA MIDDLE BELRIDGE WEST DAY 9 (6/21 OR LATER) | AERA MIDDLE BELRIDGE WEST DAY 9 (6/21 OR LATER) | AERA MIDDLE BELRIDGE WEST DAY 9 (6/21 OR LATER) | AERA MIDDLE BELRIDGE WEST DAY 9 (6/21 OR LATER) | BERRY 21Z N&S DAY 8 | BERRY 21Z N&S DAY 8 | BERRY 21Z N&S DAY 8 | BERRY 21Z N&S DAY 8 | BERRY 21Z N&S DAY 8 | BERRY 21Z N&S DAY 8 | CHEV MWSS 26F, 23F DAY 9 (6/22 OR LATER) | CHEV MWSS 26F, 23F DAY 9 (6/22 OR LATER) | CHEV MWSS 26F, 23F DAY 9 (6/22 OR LATER) | CHEV MWSS 26F, 23F DAY 9 (6/22 OR LATER) | CHEV MWSS 26F, 23F DAY 9 (6/22 OR LATER) | CHEV 25 HILL S DAY 8 | CHEV HILL S DAY 8 | CHEV 25 HILL S DAY 8 | KOSS 178 MORNING DR & EPC Landfill DAY 9 (6/27 LATER) | KOSS 178 MORNING DR & EPC Landfill DAY 9 (6/27 LATER) | PG&E Tulare Gates | PG&E Tulare Gates | PG&E Tulare Gates | PG&E Tulare Gates | Brit off | BERRY O-P N, O-P S, TRAP & PAN DAY 8 | BERRY O-P N, O-P S, TRAP & PAN DAY 8 | BERRY O-P N, O-P S, TRAP & PAN DAY 8 | BERRY O-P N, O-P S, TRAP & PAN DAY 8 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-06-30 | 2018-06-30 | 2018-06-30 | 2018-06-30 | 2018-06-30 | 2018-06-30
2018-06-28 | 3 Monitors/Week | 3 Monitors/Week | 3 Monitors/Week | RAINEY HSR | CODY HSR | KAYLA OFF | SAM FRI-SUN ONLY | WOODY HSR | JAMIE HSR | REBECCA OFF | CYMRIC WATERLINE + 36W DAY 6 | CYMRIC WATERLINE + 36W DAY 6 | CYMRIC WATERLINE + 36W DAY 6 | CYMRIC WATERLINE + 36W DAY 6 | CYMRIC WATERLINE + 36W DAY 6 | CYMRIC WATERLINE + 36W DAY 6 |  |  |  |  | AERA MIDDLE BELRIDGE WEST DAY 10 (6/22 OR LATER) | AERA MIDDLE BELRIDGE WEST DAY 10 (6/22 OR LATER) | AERA MIDDLE BELRIDGE WEST DAY 10 (6/22 OR LATER) | AERA MIDDLE BELRIDGE WEST DAY 10 (6/22 OR LATER) | AERA MIDDLE BELRIDGE WEST DAY 10 (6/22 OR LATER) | AERA MIDDLE BELRIDGE WEST DAY 10 (6/22 OR LATER) | AERA MIDDLE BELRIDGE WEST DAY 10 (6/22 OR LATER) | AERA MIDDLE BELRIDGE WEST DAY 10 (6/22 OR LATER) | BERRY 21Z N&S DAY 9 (6/26 OR LATER) | BERRY 21Z N&S DAY 9 (6/26 OR LATER) | BERRY 21Z N&S DAY 9 (6/26 OR LATER) | BERRY 21Z N&S DAY 9 (6/26 OR LATER) | BERRY 21Z N&S DAY 9 (6/26 OR LATER) | BERRY 21Z N&S DAY 9 (6/26 OR LATER) | CEMC NMWSS BRINE DISPOSAL ONLY DAY 3 | CEMC NMWSS BRINE DISPOSAL ONLY DAY 3 | CEMC NMWSS BRINE DISPOSAL ONLY DAY 3 | CEMC NMWSS BRINE DISPOSAL ONLY DAY 3 | CHEV LH SOLAR DAY 11 (6/17 OR LATER) | CHEV LH SOLAR DAY 11 (6/17 OR LATER) | CHEV LH SOLAR DAY 11 (6/17 OR LATER) | CHEV LH SOLAR DAY 11 (6/17 OR LATER) | CHEV LH SOLAR DAY 11 (6/17 OR LATER) | CHEV LH SOLAR DAY 11 (6/17 OR LATER) | CHEV LH SOLAR DAY 11 (6/17 OR LATER) | CHEV LH SOLAR DAY 11 (6/17 OR LATER) | CHEV MWSS 26F, 23F DAY 10 (6/23 OR LATER) | CHEV MWSS 26F, 23F DAY 10 (6/23 OR LATER) | CHEV MWSS 26F, 23F DAY 10 (6/23 OR LATER) | CHEV MWSS 26F, 23F DAY 10 (6/23 OR LATER) | CHEV MWSS 26F, 23F DAY 10 (6/23 OR LATER) |  | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03
2018-06-29 | 3 Monitors/Week | RAINEY HSR | CODY HSR | ERIKA OFF | 3 Monitors/Week | KAYLA OFF | WOODY HSR | 3 Monitors/Week | Brett off | 27G DRAINAGES & 23L DAY 6 | 27G DRAINAGES & 23L DAY 6 |  |  | CYMRIC WATERLINE DAY 7 | CYMRIC WATERLINE DAY 7 | CYMRIC WATERLINE DAY 7 | CYMRIC WATERLINE DAY 7 | CYMRIC WATERLINE DAY 7 | CYMRIC WATERLINE DAY 7 | CHEV S25, CHANSELOR DAY 9 (6/6 OR LATER) | CHEV S25, CHANSELOR DAY 9 (6/6 OR LATER) | CHEV S25, CHANSELOR DAY 9 (6/6 OR LATER) | AERA MIDDLE BELRIDGE WEST DAY 11 (6/23 OR LATER) | AERA MIDDLE BELRIDGE WEST DAY 11 (6/23 OR LATER) | AERA MIDDLE BELRIDGE WEST DAY 11 (6/23 OR LATER) | AERA MIDDLE BELRIDGE WEST DAY 11 (6/23 OR LATER) | AERA MIDDLE BELRIDGE WEST DAY 11 (6/23 OR LATER) | AERA MIDDLE BELRIDGE WEST DAY 11 (6/23 OR LATER) | AERA MIDDLE BELRIDGE WEST DAY 11 (6/23 OR LATER) | AERA MIDDLE BELRIDGE WEST DAY 11 (6/23 OR LATER) | CHEV 25 HILL N DAY 9 (6/22 OR LATER) | CHEV 25 HILL N DAY 9 (6/22 OR LATER) | CHEV 25 HILL N DAY 9 (6/22 OR LATER) | CHEV 25 HILL N DAY 9 (6/22 OR LATER) | CHEV 25 HILL N DAY 9 (6/22 OR LATER) | CHEV 25 HILL N DAY 9 (6/22 OR LATER) | CHEV 25 HILL N DAY 9 (6/22 OR LATER) | CHEV 25 HILL S DAY 9 (6/28 OR LATER) | CHEV 25 HILL S DAY 9 (6/28 OR LATER) | CHEV 25 HILL S DAY 9 (6/28 OR LATER) | CHEV CO 23D DAY 11 (6/28 OR LATER) | CHEV CO 23D DAY 11 (6/28 OR LATER) | CHEV CO 23D DAY 11 (6/28 OR LATER) | CHEV CO 23D DAY 11 (6/28 OR LATER) | CHEV CO 23D DAY 11 (6/28 OR LATER) | CHEV CO 23D DAY 11 (6/28 OR LATER) | CHEV CO 23D DAY 11 (6/28 OR LATER) | [5 empty] | 2018-07-09 | 2018-07-09 | 2018-07-09 | 2018-07-09 | 2018-07-09 | 2018-07-09 | 2018-07-09 | 2018-07-09 | 2018-07-09 | 2018-07-09 | 2018-07-10 | 2018-07-10 | 2018-07-10 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04
2018-06-30 | KAYLA OFF | RAINEY HSR | CODY HSR | ERIKA OFF | LEILANI OFF SAT & SUN | PRESTON OFF | Sabrina off | Brett off | Rebecca off | CHEV 32US EAST & SEC29 DAY 12 (6/28 OR LATER) | CHEV 32US EAST & SEC29 DAY 12 (6/28 OR LATER) | CHEV 32US EAST & SEC29 DAY 12 (6/28 OR LATER) | CHEV 32US EAST & SEC29 DAY 12 (6/28 OR LATER) | CHEV MWSS 26F, 23F DAY 11 (6/26 OR LATER) | CHEV MWSS 26F, 23F DAY 11 (6/26 OR LATER) | CHEV MWSS 26F, 23F DAY 11 (6/26 OR LATER) | CHEV MWSS 26F, 23F DAY 11 (6/26 OR LATER) | CHEV MWSS 26F, 23F DAY 11 (6/26 OR LATER) | CYMRIC WATERLINE DAY 8 | CYMRIC WATERLINE DAY 8 | CYMRIC WATERLINE DAY 8 | CYMRIC WATERLINE DAY 8 | CYMRIC WATERLINE DAY 8 | CYMRIC WATERLINE DAY 8 | 27G DRAINAGES & 23L DAY 7 | 27G DRAINAGES & 23L DAY 7 | CHEV 7S WEST DAY 9 (6/2 OR LATER) | CHEV 7S WEST DAY 9 (6/2 OR LATER) | CHEV 7S WEST DAY 9 (6/2 OR LATER) | CHEV 7S WEST DAY 9 (6/2 OR LATER) | CHEV 25 HILL N DAY 10 (6/23 OR LATER) | CHEV 25 HILL N DAY 10 (6/23 OR LATER) | CHEV 25 HILL N DAY 10 (6/23 OR LATER) | CHEV 25 HILL N DAY 10 (6/23 OR LATER) | CHEV 25 HILL N DAY 10 (6/23 OR LATER) | CHEV 25 HILL N DAY 10 (6/23 OR LATER) | CHEV 25 HILL N DAY 10 (6/23 OR LATER) | CHEV 25 HILL S DAY 10 (6/29 OR LATER) | CHEV 25 HILL S DAY 10 (6/29 OR LATER) | CHEV 25 HILL S DAY 10 (6/29 OR LATER) | CHEV CO 23D DAY 12 (6/29 OR LATER) | CHEV CO 23D DAY 12 (6/29 OR LATER) | CHEV CO 23D DAY 12 (6/29 OR LATER) | CHEV CO 23D DAY 12 (6/29 OR LATER) | CHEV CO 23D DAY 12 (6/29 OR LATER) | CHEV CO 23D DAY 12 (6/29 OR LATER) | CHEV CO 23D DAY 12 (6/29 OR LATER) | [5 empty] | 2018-07-10 | 2018-07-10 | 2018-07-10 | 2018-07-10 | 2018-07-10 | 2018-07-10 | 2018-07-10 | 2018-07-10 | 2018-07-10 | 2018-07-10 | 2018-07-11 | 2018-07-11 | 2018-07-11 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06
2018-07-01 | KAYLA OFF | RAINEY HSR | CODY HSR | ERIKA OFF | BLAINE OFF SUN | SARAH OFF SUN | DAYNA OFF | LEILANI OFF SAT & SUN | COLIN OFF | PRESTON OFF | Brett off | CHEV MWSS 26F, 23F DAY 12 (6/27 OR LATER) | CHEV MWSS 26F, 23F DAY 12 (6/27 OR LATER) | CHEV MWSS 26F, 23F DAY 12 (6/27 OR LATER) | CHEV MWSS 26F, 23F DAY 12 (6/27 OR LATER) | CHEV MWSS 26F, 23F DAY 12 (6/27 OR LATER) | CHEV S25, CHANSELOR DAY 10 (6/7 OR LATER) | CHEV S25, CHANSELOR DAY 10 (6/7 OR LATER) | CHEV S25, CHANSELOR DAY 10 (6/7 OR LATER) | ANTELLOPE SHALE & 7Z NOGO DAY 8 | ANTELLOPE SHALE & 7Z NOGO DAY 8 | ANTELLOPE SHALE & 7Z NOGO DAY 8 | CHEV 7S NORTH, 8S DAY 10 (6/11 OR LATER) | CHEV 7S NORTH, 8S DAY 10 (6/11 OR LATER) | CHEV 7S NORTH, 8S DAY 10 (6/11 OR LATER) | CHEV 7S NORTH, 8S DAY 10 (6/11 OR LATER) | CEMC 30D; CHEV 2F DAY 10 (6/21 OR LATER) | CEMC 30D; CHEV 2F DAY 10 (6/21 OR LATER) |  |  | CHEV 25 HILL N DAY 11 (6/28 OR LATER) | CHEV 25 HILL N DAY 11 (6/28 OR LATER) | CHEV 25 HILL N DAY 11 (6/28 OR LATER) | CHEV 25 HILL N DAY 11 (6/28 OR LATER) | CHEV 25 HILL N DAY 11 (6/28 OR LATER) | CHEV 25 HILL N DAY 11 (6/28 OR LATER) | CHEV 25 HILL N DAY 11 (6/28 OR LATER) | CEMC GAS COMPRESSOR/CWOD DAY 7 | CEMC GAS COMPRESSOR/CWOD DAY 7 | CEMC GAS COMPRESSOR/CWOD DAY 7 | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 10 (6/8 OR LATER) | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 10 (6/8 OR LATER) | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 10 (6/8 OR LATER) | BERRY HB 1200H; HB S32 DAY 9 (6/17 OR LATER) | BERRY HB 1200H; HB S32 DAY 9 (6/17 OR LATER) | CEMC 1Y TANKS & WJ8 DAY 9 (7/2 OR LATER) | CEMC 1Y TANKS & WJ8 DAY 9 (7/2 OR LATER) | CEMC 1Y TANKS & WJ8 DAY 9 (7/2 OR LATER) |  |  |  |  | 2018-07-11 | 2018-07-11 | 2018-07-11 | 2018-07-11 | 2018-07-11 | 2018-07-11 | 2018-07-11 | 2018-07-11 | 2018-07-11 | 2018-07-11 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13
2018-07-02 | 3 Monitors/Week | ASH 2 DAYS/WEEK | 3 Monitors/Week | ERIKA OFF | 3 Monitors/Week | GARRETT 2 DAYS/WEEK | KAYLA OFF | ANASTACIA 3 DAYS/WEEK | ARACELI OFF | RAINEY HSR | CODY HSR | CEMC 6SF, 7S, D-06 DAY 7 | CEMC 6SF, 7S, D-06 DAY 7 | KOSS 178 MORNING DR & EPC Landfill DAY 10 (6/2 OR LATER) | KOSS 178 MORNING DR & EPC Landfill DAY 10 (6/2 OR LATER) | BERRY 21Z N&S DAY 10 (7/2 OR LATER) | BERRY 21Z N&S DAY 10 (7/2 OR LATER) | BERRY 21Z N&S DAY 10 (7/2 OR LATER) | BERRY 21Z N&S DAY 10 (7/2 OR LATER) | BERRY 21Z N&S DAY 10 (7/2 OR LATER) | BERRY 21Z N&S DAY 10 (7/2 OR LATER) | CHEV 32US WEST & SEC5 DAY 8 | CHEV 32US WEST & SEC5 DAY 8 | CHEV 32US WEST & SEC5 DAY 8 | CHEV 32US WEST & SEC5 DAY 8 |  | BERRY O-P N, O-P S, TRAP & PAN DAY 9 (6/8 OR LATER) | BERRY O-P N, O-P S, TRAP & PAN DAY 9 (6/8 OR LATER) | BERRY O-P N, O-P S, TRAP & PAN DAY 9 (6/8 OR LATER) | BERRY O-P N, O-P S, TRAP & PAN DAY 9 (6/8 OR LATER) | CHEV 25 HILL N DAY 12 (7/2 OR LATER) | CHEV 25 HILL N DAY 12 (7/2 OR LATER) | CHEV 25 HILL N DAY 12 (7/2 OR LATER) | CHEV 25 HILL N DAY 12 (7/2 OR LATER) | CHEV 25 HILL N DAY 12 (7/2 OR LATER) | CHEV 25 HILL N DAY 12 (7/2 OR LATER) | CHEV 25 HILL N DAY 12 (7/2 OR LATER) | STEVENS DINO & TILT DAY + CECM 27F 10 (7/2 OR LATER) | STEVENS DINO & TILT DAY + CECM 27F 10 (7/2 OR LATER) | STEVENS DINO & TILT DAY + CECM 27F 10 (7/2 OR LATER) | STEVENS DINO & TILT DAY + CECM 27F 10 (7/2 OR LATER) | AERA MIDDLE BELRIDGE EAST DAY 11 (6/14 OR LATER) | AERA MIDDLE BELRIDGE EAST DAY 11 (6/14 OR LATER) | AERA MIDDLE BELRIDGE EAST DAY 11 (6/14 OR LATER) | AERA MIDDLE BELRIDGE EAST DAY 11 (6/14 OR LATER) | AERA MIDDLE BELRIDGE EAST DAY 11 (6/14 OR LATER) | AERA MIDDLE BELRIDGE EAST DAY 11 (6/14 OR LATER) | Brett off |  |  |  |  | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14
2018-07-03 | 3 Monitors/Week | RAINEY HSR | CODY HSR | KOR 3 DAYS/WEEK | 3 Monitors/Week | ANASTACIA 3 DAYS/WEEK | WOODY HSR | 3 Monitors/Week | GILLIAN OFF BY 1 | CEMC KRU, CHAP, GOVT2 DAY 9 (6/2 OR LATER) | CEMC KRU, CHAP, GOVT2 DAY 9 (6/2 OR LATER) | CEMC KRU, CHAP, GOVT2 DAY 9 (6/2 OR LATER) | CEMC KRU, CHAP, GOVT2 DAY 9 (6/2 OR LATER) | CEMC 15G LEASE DAY 10 (7/3 OR LATER) | CEMC 15G LEASE DAY 10 (7/3 OR LATER) | CEMC 15G LEASE DAY 10 (7/3 OR LATER) | TULARE-GATES PG&E POLES DAY 9 (7/6 OR LATER) | TULARE-GATES PG&E POLES DAY 9 (7/6 OR LATER) | AERA CAL SO PIPE DAY 6 | AERA CAL SO PIPE DAY 6 | AERA CAL SO PIPE DAY 6 | AERA CAL SO PIPE DAY 6 | AERA CAL SO PIPE DAY 6 | AERA CAL SO PIPE DAY 6 | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 11 (6/9 OR LATER) | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 11 (6/9 OR LATER) | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 11 (6/9 OR LATER) | BERRY O-P N, O-P S, TRAP & PAN DAY 10 (6/9 OR LATER) | BERRY O-P N, O-P S, TRAP & PAN DAY 10 (6/9 OR LATER) | BERRY O-P N, O-P S, TRAP & PAN DAY 10 (6/9 OR LATER) | BERRY O-P N, O-P S, TRAP & PAN DAY 10 (6/9 OR LATER) | CYMRIC WATERLINE + 36W DAY 9 (7/2 OR LATER) | CYMRIC WATERLINE + 36W DAY 9 (7/2 OR LATER) | CYMRIC WATERLINE + 36W DAY 9 (7/2 OR LATER) | CYMRIC WATERLINE + 36W DAY 9 (7/2 OR LATER) | CYMRIC WATERLINE + 36W DAY 9 (7/2 OR LATER) | CYMRIC WATERLINE + 36W DAY 9 (7/2 OR LATER) | CHEV 25 HILL S DAY 11 (6/30 OR LATER) | CHEV 25 HILL S DAY 11 (6/30 OR LATER) | CHEV 25 HILL S DAY 11 (6/30 OR LATER) | CEMC GAS COMPRESSOR/CWOD DAY 8 | CEMC GAS COMPRESSOR/CWOD DAY 8 | CEMC GAS COMPRESSOR/CWOD DAY 8 | CEMC NMWSS BRINE DISPOSAL DAY 4 | CEMC NMWSS BRINE DISPOSAL DAY 4 | CEMC NMWSS BRINE DISPOSAL DAY 4 | CEMC NMWSS BRINE DISPOSAL DAY 4 | 27G DRAINAGES & 23L DAY 8 | 27G DRAINAGES & 23L DAY 8 | 22G DRAINAGES DAY 6 | 22G DRAINAGES DAY 6
2018-07-04 | RAINEY HSR | CODY HSR | JAMIE HSR | Rigo off | KAYLA OFF | Katrina off | HOLIDAY | HOLIDAY | CEMC 6SF, 7S, D-06 | CEMC 6SF, 7S, D-06 | KOSS 178 MORNING DR & EPC Landfill DAY 11 (6/3 OR LATER) | KOSS 178 MORNING DR & EPC Landfill DAY 11 (6/3 OR LATER) | CEMC 15G LEASE DAY 11 (7/4 OR LATER) | CEMC 15G LEASE DAY 11 (7/4 OR LATER) | CEMC 15G LEASE DAY 11 (7/4 OR LATER) | BERRY 21Z N&S DAY 11 (7/3 OR LATER) | BERRY 21Z N&S DAY 11 (7/3 OR LATER) | BERRY 21Z N&S DAY 11 (7/3 OR LATER) | BERRY 21Z N&S DAY 11 (7/3 OR LATER) | BERRY 21Z N&S DAY 11 (7/3 OR LATER) | BERRY 21Z N&S DAY 11 (7/3 OR LATER) |  |  | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 12 (7/4 OR LATER) | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 12 (7/4 OR LATER) | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 12 (7/4 OR LATER) |  |  |  | TULARE-GATES PG&E POLES DAY 10 (7/7 OR LATER) | TULARE-GATES PG&E POLES DAY 10 (7/7 OR LATER) | CYMRIC WATERLINE DAY 10 (7/3 OR LATER) | CYMRIC WATERLINE DAY 10 (7/3 OR LATER) | CYMRIC WATERLINE DAY 10 (7/3 OR LATER) | CYMRIC WATERLINE DAY 10 (7/3 OR LATER) | CYMRIC WATERLINE DAY 10 (7/3 OR LATER) | CYMRIC WATERLINE DAY 10 (7/3 OR LATER) | CHEV 25 HILL S DAY 12 (7/1 OR LATER) | CHEV 25 HILL S DAY 12 (7/1 OR LATER) | CHEV 25 HILL S DAY 12 (7/1 OR LATER) | ANTELLOPE SHALE & 7Z NOGO DAY 9 (7/4 OR LATER) | ANTELLOPE SHALE & 7Z NOGO DAY 9 (7/4 OR LATER) | ANTELLOPE SHALE & 7Z NOGO DAY 9 (7/4 OR LATER) | CEMC GAS COMPRESSOR/CWOD DAY 9 (6/28 OR LATER) | CEMC GAS COMPRESSOR/CWOD DAY 9 (6/28 OR LATER) | CEMC GAS COMPRESSOR/CWOD DAY 9 (6/28 OR LATER) | Brit off | 22G DRAINAGES DAY 7 | 22G DRAINAGES DAY 7
2018-07-05 | 3 Monitors/Week | RAINEY HSR | CODY HSR | 3 Monitors/Week | MATT OFF | WOODY HSR | Rigo off | KAYLA OFF | Katrina off |  | AERA CAL SO PIPE DAY 7 | AERA CAL SO PIPE DAY 7 | AERA CAL SO PIPE DAY 7 | AERA CAL SO PIPE DAY 7 | AERA CAL SO PIPE DAY 7 | AERA CAL SO PIPE DAY 7 | TULARE-GATES PG&E POLES DAY 11 (7/8 OR LATER) | TULARE-GATES PG&E POLES DAY 11 (7/8 OR LATER)
2018-07-06 | Rigo off | KAYLA OFF | MATT OFF |  | CEMC 6SF, 7S, D-06 | CEMC 6SF, 7S, D-06 | TULARE-GATES PG&E POLES DAY 12 (7/9 OR LATER) | TULARE-GATES PG&E POLES DAY 12 (7/9 OR LATER) | BERRY HB 1200H; HB S32 DAY 10 (6/18 OR LATER) | BERRY HB 1200H; HB S32 DAY 10 (6/18 OR LATER) | AERA CAL SO PIPE DAY 8 | AERA CAL SO PIPE DAY 8 | AERA CAL SO PIPE DAY 8 | AERA CAL SO PIPE DAY 8 | AERA CAL SO PIPE DAY 8 | AERA CAL SO PIPE DAY 8 | AERA MIDDLE BELRIDGE EAST DAY 12 (7/2 OR LATER) | AERA MIDDLE BELRIDGE EAST DAY 12 (7/2 OR LATER) | AERA MIDDLE BELRIDGE EAST DAY 12 (7/2 OR LATER) | AERA MIDDLE BELRIDGE EAST DAY 12 (7/2 OR LATER) | AERA MIDDLE BELRIDGE EAST DAY 12 (7/2 OR LATER) | AERA MIDDLE BELRIDGE EAST DAY 12 (7/2 OR LATER) | STEVENS DINO & TILT DAY 11 (7/6 OR LATER) | STEVENS DINO & TILT DAY 11 (7/6 OR LATER) | STEVENS DINO & TILT DAY 11 (7/6 OR LATER) | STEVENS DINO & TILT DAY 11 (7/6 OR LATER) | [5 empty] | CYMRIC WATERLINE DAY 11 (7/4 OR LATER) | CYMRIC WATERLINE DAY 11 (7/4 OR LATER) | CYMRIC WATERLINE DAY 11 (7/4 OR LATER) | CYMRIC WATERLINE DAY 11 (7/4 OR LATER) | CYMRIC WATERLINE DAY 11 (7/4 OR LATER) | CYMRIC WATERLINE DAY 11 (7/4 OR LATER) | CEMC GAS COMPRESSOR/CWOD DAY 10 (6/29 OR LATER) | CEMC GAS COMPRESSOR/CWOD DAY 10 (6/29 OR LATER) | CEMC GAS COMPRESSOR/CWOD DAY 10 (6/29 OR LATER) | CHEV 32US WEST & SEC5 DAY 9 (6/8 OR LATER) | CHEV 32US WEST & SEC5 DAY 9 (6/8 OR LATER) | CHEV 32US WEST & SEC5 DAY 9 (6/8 OR LATER) | CHEV 32US WEST & SEC5 DAY 9 (6/8 OR LATER) |  |  |  | Dayna off
2018-07-07 | ALEX OFF | RAINEY HSR | CODY HSR | ERIKA OFF SAT & SUN | RIGO OFF | LEILANI OFF SAT & SUN | Sabrina off |  | CHEV LH SOLAR DAY 12 (6/18 OR LATER) | CHEV LH SOLAR DAY 12 (6/18 OR LATER) | CHEV LH SOLAR DAY 12 (6/18 OR LATER) | CHEV LH SOLAR DAY 12 (6/18 OR LATER) | CHEV LH SOLAR DAY 12 (6/18 OR LATER) | CHEV LH SOLAR DAY 12 (6/18 OR LATER) |  |  | CEMC NMWSS BRINE DISPOSAL, Derby Burn, 2-22 DAY 9 (7/7 OR LATER) | CEMC NMWSS BRINE DISPOSAL, Derby Burn, 2-22 DAY 9 (7/7 OR LATER) | CEMC NMWSS BRINE DISPOSAL, Derby Burn, 2-22 DAY 9 (7/7 OR LATER) | CEMC NMWSS BRINE DISPOSAL, Derby Burn, 2-22 DAY 9 (7/7 OR LATER) |  | STEVENS DINO & TILT DAY 12 (7/7 OR LATER) | STEVENS DINO & TILT DAY 12 (7/7 OR LATER) | STEVENS DINO & TILT DAY 12 (7/7 OR LATER) | STEVENS DINO & TILT DAY 12 (7/7 OR LATER) | BERRY HB 1200H; HB S32 DAY 11 (6/26 OR LATER) | BERRY HB 1200H; HB S32 DAY 11 (6/26 OR LATER) | CHEV 25 HILL S DAY 13 | CHEV HILL S DAY 13 | CHEV 25 HILL S DAY 13 |  |  | CHEV 7S NORTH, 8S DAY 11 (6/20 OR LATER) | CHEV 7S NORTH, 8S DAY 11 (6/20 OR LATER) | CHEV 7S NORTH, 8S DAY 11 (6/20 OR LATER) | CHEV 7S NORTH, 8S DAY 11 (6/20 OR LATER) | CEMC 6SF, 7S, D-06 DAY 8 | CEMC 6SF, 7S, D-06 DAY 8 | BERRY 21Z N&S DAY 12 (7/5 OR LATER) | BERRY 21Z N&S DAY 12 (7/5 OR LATER) | BERRY 21Z N&S DAY 12 (7/5 OR LATER) | BERRY 21Z N&S DAY 12 (7/5 OR LATER) | BERRY 21Z N&S DAY 12 (7/5 OR LATER) | BERRY 21Z N&S DAY 12 (7/5 OR LATER) | 22G DRAINAGES DAY 8 | 22G DRAINAGES DAY 8 | CHEV 7S WEST DAY 10 (6/3 OR LATER) | CHEV 7S WEST DAY 10 (6/3 OR LATER) | CHEV 7S WEST DAY 10 (6/3 OR LATER) | CHEV 7S WEST DAY 10 (6/3 OR LATER)
2018-07-08 | ALEX OFF | RAINEY HSR | CODY HSR | ERIKA OFF SAT & SUN | BLAINE OFF SUN | RIGO OFF | [5 empty] | ANTELLOPE SHALE & 7Z NOGO DAY 10 (7/5 OR LATER) | ANTELLOPE SHALE & 7Z NOGO DAY 10 (7/5 OR LATER) | ANTELLOPE SHALE & 7Z NOGO DAY 10 (7/5 OR LATER) | 27G DRAINAGES & 23L DAY 9 (6/23 OR LATER) | 27G DRAINAGES & 23L DAY 9 (6/23 OR LATER) | CEMC NMWSS BRINE DISPOSAL, Derby Burn, 2-22 DAY 10 (7/8 OR LATER) | CEMC NMWSS BRINE DISPOSAL, Derby Burn, 2-22 DAY 10 (7/8 OR LATER) | CEMC NMWSS BRINE DISPOSAL, Derby Burn, 2-22 DAY 10 (7/8 OR LATER) | CEMC NMWSS BRINE DISPOSAL, Derby Burn, 2-22 DAY 10 (7/8 OR LATER) | SEC 11/13 GAUGES DAY 9 (7/8 OR LATER) | SEC 11/13 GAUGES DAY 9 (7/8 OR LATER) | SEC 11/13 GAUGES DAY 9 (7/8 OR LATER) | SEC 11/13 GAUGES DAY 9 (7/8 OR LATER) | SEC 11/13 GAUGES DAY 9 (7/8 OR LATER) | SEC 11/13 GAUGES DAY 9 (7/8 OR LATER) | BERRY O-P N, O-P S, TRAP & PAN DAY 11 (6/10 OR LATER) | BERRY O-P N, O-P S, TRAP & PAN DAY 11 (6/10 OR LATER) | BERRY O-P N, O-P S, TRAP & PAN DAY 11 (6/10 OR LATER) | BERRY O-P N, O-P S, TRAP & PAN DAY 11 (6/10 OR LATER) | COALINGA NOSE UNIT DAY 9 (7/8 OR LATER) | COALINGA NOSE UNIT DAY 9 (7/8 OR LATER) | COALINGA NOSE UNIT DAY 9 (7/8 OR LATER) | COALINGA NOSE UNIT DAY 9 (7/8 OR LATER) | COALINGA NOSE UNIT DAY 9 (7/8 OR LATER) | COALINGA NOSE UNIT DAY 9 (7/8 OR LATER) | COALINGA NOSE UNIT DAY 9 (7/8 OR LATER) | COALINGA NOSE UNIT DAY 9 (7/8 OR LATER) | COALINGA NOSE UNIT DAY 9 (7/8 OR LATER) | COALINGA NOSE UNIT DAY 9 (7/8 OR LATER) | CEMC GAS COMPRESSOR/CWOD DAY 11 (6/30 OR LATER) | CEMC GAS COMPRESSOR/CWOD DAY 11 (6/30 OR LATER) | CEMC GAS COMPRESSOR/CWOD DAY 11 (6/30 OR LATER) | CHEV 32US WEST & SEC5 DAY 10 (6/9 OR LATER) | CHEV 32US WEST & SEC5 DAY 10 (6/9 OR LATER) | CHEV 32US WEST & SEC5 DAY 10 (6/9 OR LATER) | CHEV 32US WEST & SEC5 DAY 10 (6/9 OR LATER)
2018-07-09 | 3 Monitors/Week | ASH 2 DAYS/WEEK | JAMIE HSR | KOR 3 DAYS/WEEK | 3 Monitors/Week | GARRETT 2 DAYS/WEEK | WOODY HSR | 3 Monitors/Week | ANASTACIA 3 DAYS/WEEK | ARACELI OFF | RAINEY HSR | CEMC 30D; CHEV 2F DAY 11 (7/7 OR LATER) | CEMC 30D; CHEV 2F DAY 11 (7/7 OR LATER) | 27G DRAINAGES & 23L DAY 10 (6/24 OR LATER) | 27G DRAINAGES & 23L DAY 10 (6/24 OR LATER) | CEMC NMWSS BRINE DISPOSAL, Derby Burn, 2-22 DAY 11 (7/9 OR LATER) | CEMC NMWSS BRINE DISPOSAL, Derby Burn, 2-22 DAY 11 (7/9 OR LATER) | CEMC NMWSS BRINE DISPOSAL, Derby Burn, 2-22 DAY 11 (7/9 OR LATER) | CEMC NMWSS BRINE DISPOSAL, Derby Burn, 2-22 DAY 11 (7/9 OR LATER) | AERA MIDDLE BELRIDGE WEST DAY 12 (7/6 OR LATER) | AERA MIDDLE BELRIDGE WEST DAY 12 (7/6 OR LATER) | AERA MIDDLE BELRIDGE WEST DAY 12 (7/6 OR LATER) | AERA MIDDLE BELRIDGE WEST DAY 12 (7/6 OR LATER) | AERA MIDDLE BELRIDGE WEST DAY 12 (7/6 OR LATER) | AERA MIDDLE BELRIDGE WEST DAY 12 (7/6 OR LATER) | AERA MIDDLE BELRIDGE WEST DAY 12 (7/6 OR LATER) | AERA MIDDLE BELRIDGE WEST DAY 12 (7/6 OR LATER) | BERRY O-P N, O-P S, TRAP & PAN DAY 12 (6/11 OR LATER) | BERRY O-P N, O-P S, TRAP & PAN DAY 12 (6/11 OR LATER) | BERRY O-P N, O-P S, TRAP & PAN DAY 12 (6/11 OR LATER) | BERRY O-P N, O-P S, TRAP & PAN DAY 12 (6/11 OR LATER) | COALINGA NOSE UNIT DAY 10 (7/9 OR LATER) | COALINGA NOSE UNIT DAY 10 (7/9 OR LATER) | COALINGA NOSE UNIT DAY 10 (7/9 OR LATER) | COALINGA NOSE UNIT DAY 10 (7/9 OR LATER) | COALINGA NOSE UNIT DAY 10 (7/9 OR LATER) | COALINGA NOSE UNIT DAY 10 (7/9 OR LATER) | COALINGA NOSE UNIT DAY 10 (7/9 OR LATER) | COALINGA NOSE UNIT DAY 10 (7/9 OR LATER) | COALINGA NOSE UNIT DAY 10 (7/9 OR LATER) | COALINGA NOSE UNIT DAY 10 (7/9 OR LATER) | CHEV 32US WEST & SEC5 DAY 11 (AFTER 6/10 OR LATER) | CHEV 32US WEST & SEC5 DAY 11 (AFTER 6/10 OR LATER) | CHEV 32US WEST & SEC5 DAY 11 (AFTER 6/10 OR LATER) | CHEV 32US WEST & SEC5 DAY 11 (AFTER 6/10 OR LATER) | RIGO off | Brit off | Brett jury
2018-07-10 | 3 Monitors/Week | ASH 2 DAYS/WEEK | 3 Monitors/Week | ERIKA 2 DAYS/WEEK | 3 Monitors/Week | GARRETT 2 DAYS/WEEK | RAINEY HSR | CODY HSR | KOR 3 DAYS/WEEK | ANASTACIA 3 DAYS/WEEK | WOODY HSR | ANTELLOPE SHALE & 7Z NOGO DAY 11 (7/6 OR LATER) | ANTELLOPE SHALE & 7Z NOGO DAY 11 (7/6 OR LATER) | ANTELLOPE SHALE & 7Z NOGO DAY 11 (7/6 OR LATER) | 27G DRAINAGES & 23L DAY 11 (6/25 OR LATER) | 27G DRAINAGES & 23L DAY 11 (6/25 OR LATER) | CEMC NMWSS BRINE DISPOSAL, Derby Burn, 2-22 DAY 12 (7/10 OR LATER) | CEMC NMWSS BRINE DISPOSAL, Derby Burn, 2-22 DAY 12 (7/10 OR LATER) | CEMC NMWSS BRINE DISPOSAL, Derby Burn, 2-22 DAY 12 (7/10 OR LATER) | CEMC NMWSS BRINE DISPOSAL, Derby Burn, 2-22 DAY 12 (7/10 OR LATER) | AERA CAL SO PIPE DAY 9 (6/28 OR LATER) | AERA CAL SO PIPE DAY 9 (6/28 OR LATER) | AERA CAL SO PIPE DAY 9 (6/28 OR LATER) | AERA CAL SO PIPE DAY 9 (6/28 OR LATER) | AERA CAL SO PIPE DAY 9 (6/28 OR LATER) | AERA CAL SO PIPE DAY 9 (6/28 OR LATER) | CEMC 1Y TANKS; WJ8 & 36W DAY 10 (7/4 OR LATER) | CEMC 1Y TANKS; WJ8 & 36W DAY 10 (7/4 OR LATER) | CEMC 1Y TANKS; WJ8 & 36W DAY 10 (7/4 OR LATER) |  | COALINGA NOSE UNIT DAY 11 (7/10 OR LATER) | COALINGA NOSE UNIT DAY 11 (7/10 OR LATER) | COALINGA NOSE UNIT DAY 11 (7/10 OR LATER) | COALINGA NOSE UNIT DAY 11 (7/10 OR LATER) | COALINGA NOSE UNIT DAY 11 (7/10 OR LATER) | COALINGA NOSE UNIT DAY 11 (7/10 OR LATER) | COALINGA NOSE UNIT DAY 11 (7/10 OR LATER) | COALINGA NOSE UNIT DAY 11 (7/10 OR LATER) | COALINGA NOSE UNIT DAY 11 (7/10 OR LATER) | COALINGA NOSE UNIT DAY 11 (7/10 OR LATER) | CEMC GAS COMPRESSOR/CWOD DAY 12 (7/1 OR LATER) | CEMC GAS COMPRESSOR/CWOD DAY 12 (7/1 OR LATER) | CEMC GAS COMPRESSOR/CWOD DAY 12 (7/1 OR LATER) | KOSS 178 MORNING DR & EPC Landfill DAY 12 (7/4 OR LATER) | KOSS 178 MORNING DR & EPC Landfill DAY 12 (7/4 OR LATER) |  | Brit off | Brett jury
2018-07-11 | 3 Monitors/Week | 3 Monitors/Week | JAMIE HSR | WOODY HSR | 3 Monitors/Week | RAINEY HSR | CODY HSR | KOR 3 DAYS/WEEK | AERA CAL SO PIPE DAY 10 (6/29 OR LATER) | AERA CAL SO PIPE DAY 10 (6/29 OR LATER) | AERA CAL SO PIPE DAY 10 (6/29 OR LATER) | AERA CAL SO PIPE DAY 10 (6/29 OR LATER) | AERA CAL SO PIPE DAY 10 (6/29 OR LATER) | AERA CAL SO PIPE DAY 10 (6/29 OR LATER) | 27G DRAINAGES & 23L DAY 12 (6/26 OR LATER) | 27G DRAINAGES & 23L DAY 12 (6/26 OR LATER) | CEMC KRU, CHAP, GOVT2 DAY 10 (6/3 OR LATER) | CEMC KRU, CHAP, GOVT2 DAY 10 (6/3 OR LATER) | CEMC KRU, CHAP, GOVT2 DAY 10 (6/3 OR LATER) | CEMC KRU, CHAP, GOVT2 DAY 10 (6/3 OR LATER) | SEC 11/13 GAUGES DAY 10 (7/10 OR LATER) | SEC 11/13 GAUGES DAY 10 (7/10 OR LATER) | SEC 11/13 GAUGES DAY 10 (7/10 OR LATER) | SEC 11/13 GAUGES DAY 10 (7/10 OR LATER) | SEC 11/13 GAUGES DAY 10 (7/10 OR LATER) | SEC 11/13 GAUGES DAY 10 (7/10 OR LATER) | CEMC 1Y TANKS; WJ8 & 36W DAY 11 (7/11 OR LATER) | CEMC 1Y TANKS; WJ8 & 36W DAY 11 (7/11 OR LATER) | CEMC 1Y TANKS; WJ8 & 36W DAY 11 (7/11 OR LATER) |  | COALINGA NOSE UNIT DAY 12 (7/11 OR LATER) | COALINGA NOSE UNIT DAY 12 (7/11 OR LATER) | COALINGA NOSE UNIT DAY 12 (7/11 OR LATER) | COALINGA NOSE UNIT DAY 12 (7/11 OR LATER) | COALINGA NOSE UNIT DAY 12 (7/11 OR LATER) | COALINGA NOSE UNIT DAY 12 (7/11 OR LATER) | COALINGA NOSE UNIT DAY 12 (7/11 OR LATER) | COALINGA NOSE UNIT DAY 12 (7/11 OR LATER) | COALINGA NOSE UNIT DAY 12 (7/11 OR LATER) | COALINGA NOSE UNIT DAY 12 (7/11 OR LATER) | CHEV S25, CHANSELOR DAY 11 (6/8 OR LATER) | CHEV S25, CHANSELOR DAY 11 (6/8 OR LATER) | CHEV S25, CHANSELOR DAY 11 (6/8 OR LATER) |  | 22G DRAINAGES DAY 9 (7/5 OR LATER) | 22G DRAINAGES DAY 9 (7/5 OR LATER) | Brit off | Brett jury
2018-07-12 | 3 Monitors/Week | 3 Monitors/Week | KAT OFF | WOODY HSR | 3 Monitors/Week | JAMIE HSR | RAINEY HSR | CODY HSR | AERA CAL SO PIPE DAY 11 (6/30 OR LATER) | AERA CAL SO PIPE DAY 11 (6/30 OR LATER) | AERA CAL SO PIPE DAY 11 (6/30 OR LATER) | AERA CAL SO PIPE DAY 11 (6/30 OR LATER) | AERA CAL SO PIPE DAY 11 (6/30 OR LATER) | AERA CAL SO PIPE DAY 11 (6/30 OR LATER) | CEMC 6SF, 7S, D-06 DAY 9 (7/6 OR LATER) | CEMC 6SF, 7S, D-06 DAY 9 (7/6 OR LATER) | CEMC KRU, CHAP, GOVT2 DAY 11 (6/4 OR LATER) | CEMC KRU, CHAP, GOVT2 DAY 11 (6/4 OR LATER) | CEMC KRU, CHAP, GOVT2 DAY 11 (6/4 OR LATER) | CEMC KRU, CHAP, GOVT2 DAY 11 (6/4 OR LATER) | SEC 11/13 GAUGES DAY 11 (7/11 OR LATER) | SEC 11/13 GAUGES DAY 11 (7/11 OR LATER) | SEC 11/13 GAUGES DAY 11 (7/11 OR LATER) | SEC 11/13 GAUGES DAY 11 (7/11 OR LATER) | SEC 11/13 GAUGES DAY 11 (7/11 OR LATER) | SEC 11/13 GAUGES DAY 11 (7/11 OR LATER) | CEMC 1Y TANKS; WJ8 & 36W DAY 11 (7/12 OR LATER) | CEMC 1Y TANKS; WJ8 & 36W DAY 11 (7/12 OR LATER) | CEMC 1Y TANKS; WJ8 & 36W DAY 11 (7/12 OR LATER) | CHEV 7S NORTH, 8S DAY 12 (6/27 OR LATER) | CHEV 7S NORTH, 8S DAY 12 (6/27 OR LATER) | CHEV 7S NORTH, 8S DAY 12 (6/27 OR LATER) | CHEV 7S NORTH, 8S DAY 12 (6/27 OR LATER) | CHEV S25, CHANSELOR DAY 12 (6/9 OR LATER) | CHEV S25, CHANSELOR DAY 12 (6/9 OR LATER) | CHEV S25, CHANSELOR DAY 12 (6/9 OR LATER) | CEMC 30D; CHEV 2F DAY 12 (7/8 OR LATER) | CEMC 30D; CHEV 2F DAY 12 (7/8 OR LATER) |  |  | CHEV 7S WEST DAY 11 (6/4 OR LATER) | CHEV 7S WEST DAY 11 (6/4 OR LATER) | CHEV 7S WEST DAY 11 (6/4 OR LATER) | CHEV 7S WEST DAY 11 (6/4 OR LATER) | 22G DRAINAGES DAY 10 (7/6 OR LATER) | 22G DRAINAGES DAY 10 (7/6 OR LATER)
2018-07-13 | 3 Monitors/Week | ASH OFF | 3 Monitors/Week | 3 Monitors/Week | RAINEY HSR | CODY HSR | WOODY HSR |  | KAT OFF | Gillian off |  | ANTELLOPE SHALE & 7Z NOGO DAY 12 (7/7 OR LATER) | ANTELLOPE SHALE & 7Z NOGO DAY 12 (7/7 OR LATER) | ANTELLOPE SHALE & 7Z NOGO DAY 12 (7/7 OR LATER) | CEMC 6SF, 7S, D-06 DAY 10 (7/7 OR LATER) | CEMC 6SF, 7S, D-06 DAY 10 (7/7 OR LATER) | CEMC KRU, CHAP, GOVT2 DAY 12 (6/5 OR LATER) | CEMC KRU, CHAP, GOVT2 DAY 12 (6/5 OR LATER) | CEMC KRU, CHAP, GOVT2 DAY 12 (6/5 OR LATER) | CEMC KRU, CHAP, GOVT2 DAY 12 (6/5 OR LATER) | SEC 11/13 GAUGES DAY 12 (7/12 OR LATER) | SEC 11/13 GAUGES DAY 12 (7/12 OR LATER) | SEC 11/13 GAUGES DAY 12 (7/12 OR LATER) | SEC 11/13 GAUGES DAY 12 (7/12 OR LATER) | SEC 11/13 GAUGES DAY 12 (7/12 OR LATER) | SEC 11/13 GAUGES DAY 12 (7/12 OR LATER) | AERA CAL SO PIPE DAY 12 (7/1 OR LATER) | AERA CAL SO PIPE DAY 12 (7/1 OR LATER) | AERA CAL SO PIPE DAY 12 (7/1 OR LATER) | AERA CAL SO PIPE DAY 12 (7/1 OR LATER) | AERA CAL SO PIPE DAY 12 (7/1 OR LATER) | AERA CAL SO PIPE DAY 12 (7/1 OR LATER) | CYMRIC WATERLINE DAY 12 (7/5 OR LATER) | CYMRIC WATERLINE DAY 12 (7/5 OR LATER) | CYMRIC WATERLINE DAY 12 (7/5 OR LATER) | CYMRIC WATERLINE DAY 12 (7/5 OR LATER) | CYMRIC WATERLINE DAY 12 (7/5 OR LATER) | CYMRIC WATERLINE DAY 12 (7/5 OR LATER) | BERRY HB 1200H; HB S32 DAY 12 (7/6 OR LATER) | BERRY HB 1200H; HB S32 DAY 12 (7/6 OR LATER) | CEMC 15G LEASE DAY 12 (7/5 OR LATER) | CEMC 15G LEASE DAY 12 (7/5 OR LATER) | CEMC 15G LEASE DAY 12 (7/5 OR LATER) |  | 22G DRAINAGES DAY 11 (7/7 OR LATER) | 22G DRAINAGES DAY 11 (7/7 OR LATER)
2018-07-14 | KAT OFF | ASH OFF | ERIKA OFF SAT & SUN | RAINEY HSR | CODY HSR | LEILANI OFF SAT & SUN | [8 empty] | CEMC 6SF, 7S, D-06 DAY 11 (7/8 OR LATER) | CEMC 6SF, 7S, D-06 DAY 11 (7/8 OR LATER) | [20 empty] | CHEV 32US WEST & SEC5 DAY 12 (AFTER 6/11 OR LATER) | CHEV 32US WEST & SEC5 DAY 12 (AFTER 6/11 OR LATER) | CHEV 32US WEST & SEC5 DAY 12 (AFTER 6/11 OR LATER) | CHEV 32US WEST & SEC5 DAY 12 (AFTER 6/11 OR LATER) | CHEV 7S WEST DAY 12 (6/5 OR LATER) | CHEV 7S WEST DAY 12 (6/5 OR LATER) | CHEV 7S WEST DAY 12 (6/5 OR LATER) | CHEV 7S WEST DAY 12 (6/5 OR LATER) | 22G DRAINAGES DAY 12 (7/8 OR LATER) | 22G DRAINAGES DAY 12 (7/8 OR LATER)
2018-07-15 | KAT OFF | ASH OFF | ERIKA OFF SAT & SUN | BLAINE OFF SUN | RAINEY HSR | CODY HSR | SARAH OFF SUN | PRESTON OFF | LEILANI OFF SAT & SUN | Woody off |  |  |  |  | CEMC 6SF, 7S, D-06 DAY 12 (7/9 OR LATER) | CEMC 6SF, 7S, D-06 DAY 12 (7/9 OR LATER)
| KAT OFF | ASH OFF | [7 empty] | Woody off
| KAT OFF | ASH OFF | [7 empty] | Woody off
| KAT OFF | ASH OFF | [7 empty] | Woody off
| KAT OFF | ASH OFF |  | weekend | [5 empty] | Woody off
|  | ASH OFF |  | holiday | [5 empty] | Woody off
|  | ASH OFF | [7 empty] | Woody off
ASH OFF
ASH OFF
Note on A63: JayAnna Miller: Day 4 must be done by this date to finish surveys in protocol

## Juvenile period
| JARED | ASHLEIGH | SABRINA | ERIKA | BLAINE | GARRETT | DONNA | SPENCER | SARAH | KIM | KAYLA | ANASTACIA | ARACELI | RAINEY | CODY | KORISSA | SAM | MATT | WOODY | COLIN | KAT | GILLIAN | ALEX | DAYNA | LEILANI | TOKY | KEVIN | ANNA | TOM | PRESTON | ODETTE | KAITLYN | ROBERT V | JAMIE | ROB K | CJ | JACOB | MOLLY | KATRINA | BRETT | RIGOBERTO | ALEX H | MITCH | REBECCA | BRANT | DANIEL | BRITTAN Y | KAMERON
2018-08-01 | [17 empty] | MATT OFF | [10 empty] | TOM BTS |  | ODETTE OFF |  |  |  |  | CJ OFF | [6 empty] | MITCH OFF |  |  |  | BRIT OFF
2018-08-02 | [28 empty] | TOM BTS |  | ODETTE OFF | [11 empty] | MITCH OFF |  |  |  | BRIT OFF |  | 27G DRAINAGES & 23L DAY 1 | 27G DRAINAGES & 23L DAY 1 | CEMC 30D; CHEV 2F DAY 1 | CEMC 30D; CHEV 2F DAY 1 | CEMC 6SF, 7S, D-06 DAY 1 | CEMC 6SF, 7S, D-06 DAY 1 | CEMC GAS COMPRESSOR/CWOD DAY 1 | CEMC GAS COMPRESSOR/CWOD DAY 1 | CEMC GAS COMPRESSOR/CWOD DAY 1 | CEMC KRU, CHAP, GOVT2 DAY 1 | CEMC KRU, CHAP, GOVT2 DAY 1 | CEMC KRU, CHAP, GOVT2 DAY 1 | CEMC KRU, CHAP, GOVT2 DAY 1 | CHEV 32US WEST & SEC5 DAY 1 | CHEV 32US WEST & SEC5 DAY 1 | CHEV 32US WEST & SEC5 DAY 1 | CHEV 32US WEST & SEC5 DAY 1 | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 1 | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 1 | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 1 | KOSS 178 MORNING DR & EPC Landfill DAY 1 | KOSS 178 MORNING DR & EPC Landfill DAY 1
2018-08-03 | [28 empty] | TOM BTS |  | ODETTE OFF | [5 empty] | JACOB OFF | [5 empty] | MITCH OFF | [5 empty] | 27G DRAINAGES & 23L DAY 2 | 27G DRAINAGES & 23L DAY 2 | CEMC 30D; CHEV 2F DAY 2 | CEMC 30D; CHEV 2F DAY 2 | CEMC 6SF, 7S, D-06 DAY 2 | CEMC 6SF, 7S, D-06 DAY 2 | CEMC GAS COMPRESSOR/CWOD DAY 2 | CEMC GAS COMPRESSOR/CWOD DAY 2 | CEMC GAS COMPRESSOR/CWOD DAY 2 | CEMC KRU, CHAP, GOVT2 DAY 2 | CEMC KRU, CHAP, GOVT2 DAY 2 | CEMC KRU, CHAP, GOVT2 DAY 2 | CEMC KRU, CHAP, GOVT2 DAY 2 | CHEV 32US WEST & SEC5 DAY 2 | CHEV 32US WEST & SEC5 DAY 2 | CHEV 32US WEST & SEC5 DAY 2 | CHEV 32US WEST & SEC5 DAY 2 | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 2 | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 2 | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 2 | KOSS 178 MORNING DR & EPC Landfill DAY 2 | KOSS 178 MORNING DR & EPC Landfill DAY 2
2018-08-04 | [20 empty] | KAT OFF |  |  |  | LEILANI OFF |  |  |  | TOM BTS | [7 empty] | JACOB OFF |  |  |  | RIGO OFF |  | MITCH OFF | [5 empty] | 27G DRAINAGES & 23L DAY 3 | 27G DRAINAGES & 23L DAY 3 | CEMC 30D; CHEV 2F DAY 3 | CEMC 30D; CHEV 2F DAY 3 | CEMC 6SF, 7S, D-06 DAY 3 | CEMC 6SF, 7S, D-06 DAY 3 | CEMC GAS COMPRESSOR/CWOD DAY 3 | CEMC GAS COMPRESSOR/CWOD DAY 3 | CEMC GAS COMPRESSOR/CWOD DAY 3 | CEMC KRU, CHAP, GOVT2 DAY 3 | CEMC KRU, CHAP, GOVT2 DAY 3 | CEMC KRU, CHAP, GOVT2 DAY 3 | CEMC KRU, CHAP, GOVT2 DAY 3 | CHEV 32US WEST & SEC5 DAY 3 | CHEV 32US WEST & SEC5 DAY 3 | CHEV 32US WEST & SEC5 DAY 3 | CHEV 32US WEST & SEC5 DAY 3 | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 3 | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 3 | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 3 | KOSS 178 MORNING DR & EPC Landfill DAY 3 | KOSS 178 MORNING DR & EPC Landfill DAY 3
2018-08-05 | [18 empty] | WOODY OFF | COLIN OFF |  |  |  |  | LEILANI OFF |  |  |  | TOM BTS | PRESTON OFF | [6 empty] | JACOB OFF | [5 empty] | MITCH OFF | [5 empty] | 27G DRAINAGES & 23L DAY 4 | 27G DRAINAGES & 23L DAY 4 | CEMC 30D; CHEV 2F DAY 4 | CEMC 30D; CHEV 2F DAY 4 | CEMC 6SF, 7S, D-06 DAY 4 | CEMC 6SF, 7S, D-06 DAY 4 | CEMC GAS COMPRESSOR/CWOD DAY 4 | CEMC GAS COMPRESSOR/CWOD DAY 4 | CEMC GAS COMPRESSOR/CWOD DAY 4 | CEMC KRU, CHAP, GOVT2 DAY 4 | CEMC KRU, CHAP, GOVT2 DAY 4 | CEMC KRU, CHAP, GOVT2 DAY 4 | CEMC KRU, CHAP, GOVT2 DAY 4 | CHEV 32US WEST & SEC5 DAY 4 | CHEV 32US WEST & SEC5 DAY 4 | CHEV 32US WEST & SEC5 DAY 4 | CHEV 32US WEST & SEC5 DAY 4 | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 4 | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 4 | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 4 | KOSS 178 MORNING DR & EPC Landfill DAY 4 | KOSS 178 MORNING DR & EPC Landfill DAY 4
2018-08-06 | [12 empty] | ARACELI OFF | [6 empty] | COLIN OFF | [8 empty] | TOM BTS | [13 empty] | MITCH OFF | [5 empty] | 27G DRAINAGES & 23L DAY 5 | 27G DRAINAGES & 23L DAY 5 | CEMC 30D; CHEV 2F DAY 5 | CEMC 30D; CHEV 2F DAY 5 | CEMC 6SF, 7S, D-06 DAY 5 | CEMC 6SF, 7S, D-06 DAY 5 | CEMC GAS COMPRESSOR/CWOD DAY 5 | CEMC GAS COMPRESSOR/CWOD DAY 5 | CEMC GAS COMPRESSOR/CWOD DAY 5 | CEMC KRU, CHAP, GOVT2 DAY 5 | CEMC KRU, CHAP, GOVT2 DAY 5 | CEMC KRU, CHAP, GOVT2 DAY 5 | CEMC KRU, CHAP, GOVT2 DAY 5 | CHEV 32US WEST & SEC5 DAY 5 | CHEV 32US WEST & SEC5 DAY 5 | CHEV 32US WEST & SEC5 DAY 5 | CHEV 32US WEST & SEC5 DAY 5 | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 5 | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 5 | CEMC MAYS 57, WEST WELLS, 36T & 26F DAY 5 | KOSS 178 MORNING DR & EPC Landfill DAY 5 | KOSS 178 MORNING DR & EPC Landfill DAY 5
2018-08-07 | [17 empty] | MATT OFF |  | COLIN OFF |  | GILLIAN OFF BY 1 | [6 empty] | TOM BTS | [13 empty] | MITCH OFF
2018-08-08 | [5 empty] | GARRETT OFF | [11 empty] | MATT OFF |  | COLIN OFF |  | GILLIAN OFF | [6 empty] | TOM BTS | [13 empty] | MITCH OFF | [5 empty] | CHEV LH SOLAR DAY 1 | CHEV LH SOLAR DAY 1 | CHEV LH SOLAR DAY 1 | CHEV LH SOLAR DAY 1 | CHEV LH SOLAR DAY 1 | CHEV LH SOLAR DAY 1 | BERRY HB 1200H; HB S32 DAY 1 | BERRY HB 1200H; HB S32 DAY 1 | CHEV S25, CHANSELOR DAY 1 | CHEV S25, CHANSELOR DAY 1 | CHEV S25, CHANSELOR DAY 1 | AERA MIDDLE BELRIDGE WEST DAY 1 | AERA MIDDLE BELRIDGE WEST DAY 1 | AERA MIDDLE BELRIDGE WEST DAY 1 | AERA MIDDLE BELRIDGE WEST DAY 1 | AERA MIDDLE BELRIDGE WEST DAY 1 | AERA MIDDLE BELRIDGE WEST DAY 1 | AERA MIDDLE BELRIDGE WEST DAY 1 | AERA MIDDLE BELRIDGE WEST DAY 1 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 1 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 1 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 1 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 1 | BERRY O-P N, O-P S, TRAP & PAN DAY 1 | BERRY O-P N, O-P S, TRAP & PAN DAY 1 | BERRY O-P N, O-P S, TRAP & PAN DAY 1 | BERRY O-P N, O-P S, TRAP & PAN DAY 1
2018-08-09 |  |  | SABRINA OFF |  |  | GARRETT OFF | [13 empty] | COLIN OFF | [8 empty] | TOM BTS |  |  |  | ROBERT V BTS | [15 empty] | CHEV LH SOLAR DAY 2 | CHEV LH SOLAR DAY 2 | CHEV LH SOLAR DAY 2 | CHEV LH SOLAR DAY 2 | CHEV LH SOLAR DAY 2 | CHEV LH SOLAR DAY 2 | BERRY HB 1200H; HB S32 DAY 2 | BERRY HB 1200H; HB S32 DAY 2 | CHEV S25, CHANSELOR DAY 2 | CHEV S25, CHANSELOR DAY 2 | CHEV S25, CHANSELOR DAY 2 | AERA MIDDLE BELRIDGE WEST DAY 2 | AERA MIDDLE BELRIDGE WEST DAY 2 | AERA MIDDLE BELRIDGE WEST DAY 2 | AERA MIDDLE BELRIDGE WEST DAY 2 | AERA MIDDLE BELRIDGE WEST DAY 2 | AERA MIDDLE BELRIDGE WEST DAY 2 | AERA MIDDLE BELRIDGE WEST DAY 2 | AERA MIDDLE BELRIDGE WEST DAY 2 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 2 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 2 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 2 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 2 | BERRY O-P N, O-P S, TRAP & PAN DAY 2 | BERRY O-P N, O-P S, TRAP & PAN DAY 2 | BERRY O-P N, O-P S, TRAP & PAN DAY 2 | BERRY O-P N, O-P S, TRAP & PAN DAY 2
2018-08-10 |  |  | SABRINA OFF |  |  | GARRETT OFF | [13 empty] | COLIN OFF | [8 empty] | TOM BTS |  |  |  | ROBERT V BTS | [15 empty] | CHEV LH SOLAR DAY 3 | CHEV LH SOLAR DAY 3 | CHEV LH SOLAR DAY 3 | CHEV LH SOLAR DAY 3 | CHEV LH SOLAR DAY 3 | CHEV LH SOLAR DAY 3 | BERRY HB 1200H; HB S32 DAY 3 | BERRY HB 1200H; HB S32 DAY 3 | CHEV S25, CHANSELOR DAY 3 | CHEV S25, CHANSELOR DAY 3 | CHEV S25, CHANSELOR DAY 3 | AERA MIDDLE BELRIDGE WEST DAY 3 | AERA MIDDLE BELRIDGE WEST DAY 3 | AERA MIDDLE BELRIDGE WEST DAY 3 | AERA MIDDLE BELRIDGE WEST DAY 3 | AERA MIDDLE BELRIDGE WEST DAY 3 | AERA MIDDLE BELRIDGE WEST DAY 3 | AERA MIDDLE BELRIDGE WEST DAY 3 | AERA MIDDLE BELRIDGE WEST DAY 3 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 3 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 3 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 3 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 3 | BERRY O-P N, O-P S, TRAP & PAN DAY 3 | BERRY O-P N, O-P S, TRAP & PAN DAY 3 | BERRY O-P N, O-P S, TRAP & PAN DAY 3 | BERRY O-P N, O-P S, TRAP & PAN DAY 3
2018-08-11 |  |  | SABRINA OFF |  |  | GARRETT OFF | [12 empty] | WOODY OFF | COLIN OFF |  |  |  |  | LEILANI OFF |  |  |  | TOM BTS | PRESTON BTS |  |  | ROBERT V BTS | [15 empty] | CHEV LH SOLAR DAY 4 | CHEV LH SOLAR DAY 4 | CHEV LH SOLAR DAY 4 | CHEV LH SOLAR DAY 4 | CHEV LH SOLAR DAY 4 | CHEV LH SOLAR DAY 4 | BERRY HB 1200H; HB S32 DAY 4 | BERRY HB 1200H; HB S32 DAY 4 | CHEV S25, CHANSELOR DAY 4 | CHEV S25, CHANSELOR DAY 4 | CHEV S25, CHANSELOR DAY 4 | AERA MIDDLE BELRIDGE WEST DAY 4 | AERA MIDDLE BELRIDGE WEST DAY 4 | AERA MIDDLE BELRIDGE WEST DAY 4 | AERA MIDDLE BELRIDGE WEST DAY 4 | AERA MIDDLE BELRIDGE WEST DAY 4 | AERA MIDDLE BELRIDGE WEST DAY 4 | AERA MIDDLE BELRIDGE WEST DAY 4 | AERA MIDDLE BELRIDGE WEST DAY 4 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 4 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 4 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 4 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 4 | BERRY O-P N, O-P S, TRAP & PAN DAY 4 | BERRY O-P N, O-P S, TRAP & PAN DAY 4 | BERRY O-P N, O-P S, TRAP & PAN DAY 4 | BERRY O-P N, O-P S, TRAP & PAN DAY 4
2018-08-12 | JARED OFF |  | SABRINA OFF |  |  | GARRETT OFF |  | TOM BTS | [10 empty] | WOODY OFF | [5 empty] | LEILANI OFF |  |  |  | TOM BTS | PRESTON BTS |  |  | ROBERT V BTS | [15 empty] | CHEV LH SOLAR DAY 5 | CHEV LH SOLAR DAY 5 | CHEV LH SOLAR DAY 5 | CHEV LH SOLAR DAY 5 | CHEV LH SOLAR DAY 5 | CHEV LH SOLAR DAY 5 | BERRY HB 1200H; HB S32 DAY 5 | BERRY HB 1200H; HB S32 DAY 5 | CHEV S25, CHANSELOR DAY 5 | CHEV S25, CHANSELOR DAY 5 | CHEV S25, CHANSELOR DAY 5 | AERA MIDDLE BELRIDGE WEST DAY 5 | AERA MIDDLE BELRIDGE WEST DAY 5 | AERA MIDDLE BELRIDGE WEST DAY 5 | AERA MIDDLE BELRIDGE WEST DAY 5 | AERA MIDDLE BELRIDGE WEST DAY 5 | AERA MIDDLE BELRIDGE WEST DAY 5 | AERA MIDDLE BELRIDGE WEST DAY 5 | AERA MIDDLE BELRIDGE WEST DAY 5 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 5 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 5 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 5 | CEMC NMWSS BRINE DISPOSAL, DERBY BURN, 2-22 DAY 5 | BERRY O-P N, O-P S, TRAP & PAN DAY 5 | BERRY O-P N, O-P S, TRAP & PAN DAY 5 | BERRY O-P N, O-P S, TRAP & PAN DAY 5 | BERRY O-P N, O-P S, TRAP & PAN DAY 5
2018-08-13 | JARED OFF |  | SABRINA OFF |  |  | GARRETT OFF | [6 empty] | ARACELI OFF | [15 empty] | TOM BTS | PRESTON BTS |  | KAITLYN OFF | ROBERT V BTS |  |  |  | JACOB OFF | [9 empty] | BRIT BTS
2018-08-14 |  |  | SABRINA OFF |  |  | GARRETT OFF | [15 empty] | GILLIAN BTS | [6 empty] | TOM BTS | PRESTON BTS |  | KAITLYN OFF | ROBERT V BTS |  |  |  | JACOB OFF | [9 empty] | BRIT BTS |  | CHEV CO 23D DAY 1 | CHEV CO 23D DAY 1 | CHEV CO 23D DAY 1 | CHEV CO 23D DAY 1 | CHEV CO 23D DAY 1 | CHEV CO 23D DAY 1 | CHEV CO 23D DAY 1 | CHEV MWSS 26F, 23F DAY 1 | CHEV MWSS 26F, 23F DAY 1 | CHEV MWSS 26F, 23F DAY 1 | CHEV MWSS 26F, 23F DAY 1 | CHEV MWSS 26F, 23F DAY 1 | CHEV 7S WEST DAY 1 | CHEV 7S WEST DAY 1 | CHEV 7S WEST DAY 1 | CHEV 7S WEST DAY 1 | CHEV 7S NORTH, 8S DAY 1 | CHEV 7S NORTH, 8S DAY 1 | CHEV 7S NORTH, 8S DAY 1 | CHEV 7S NORTH, 8S DAY 1 | BERRY 21Z N & S DAY 1 | BERRY 21Z N & S DAY 1 | BERRY 21Z N & S DAY 1 | BERRY 21Z N & S DAY 1 | BERRY 21Z N & S DAY 1 | BERRY 21Z N & S DAY 1
2018-08-15 | [5 empty] | GARRETT OFF | [15 empty] | GILLIAN BTS | [6 empty] | TOM BTS | PRESTON BTS |  | KAITLYN OFF | ROBERT V BTS |  |  |  | JACOB OFF | [9 empty] | BRIT BTS |  | CHEV CO 23D DAY 2 | CHEV CO 23D DAY 2 | CHEV CO 23D DAY 2 | CHEV CO 23D DAY 2 | CHEV CO 23D DAY 2 | CHEV CO 23D DAY 2 | CHEV CO 23D DAY 2 | CHEV MWSS 26F, 23F DAY 2 | CHEV MWSS 26F, 23F DAY 2 | CHEV MWSS 26F, 23F DAY 2 | CHEV MWSS 26F, 23F DAY 2 | CHEV MWSS 26F, 23F DAY 2 | CHEV 7S WEST DAY 2 | CHEV 7S WEST DAY 2 | CHEV 7S WEST DAY 2 | CHEV 7S WEST DAY 2 | CHEV 7S NORTH, 8S DAY 2 | CHEV 7S NORTH, 8S DAY 2 | CHEV 7S NORTH, 8S DAY 2 | CHEV 7S NORTH, 8S DAY 2 | BERRY 21Z N & S DAY 2 | BERRY 21Z N & S DAY 2 | BERRY 21Z N & S DAY 2 | BERRY 21Z N & S DAY 2 | BERRY 21Z N & S DAY 2 | BERRY 21Z N & S DAY 2
2018-08-16 | [5 empty] | GARRETT OFF | [15 empty] | GILLIAN BTS | [6 empty] | TOM BTS | PRESTON BTS |  | KAITLYN OFF | ROBERT V BTS |  |  |  | JACOB OFF | [9 empty] | BRIT BTS |  | CHEV CO 23D DAY 3 | CHEV CO 23D DAY 3 | CHEV CO 23D DAY 3 | CHEV CO 23D DAY 3 | CHEV CO 23D DAY 3 | CHEV CO 23D DAY 3 | CHEV CO 23D DAY 3 | CHEV MWSS 26F, 23F DAY 3 | CHEV MWSS 26F, 23F DAY 3 | CHEV MWSS 26F, 23F DAY 3 | CHEV MWSS 26F, 23F DAY 3 | CHEV MWSS 26F, 23F DAY 3 | CHEV 7S WEST DAY 3 | CHEV 7S WEST DAY 3 | CHEV 7S WEST DAY 3 | CHEV 7S WEST DAY 3 | CHEV 7S NORTH, 8S DAY 3 | CHEV 7S NORTH, 8S DAY 3 | CHEV 7S NORTH, 8S DAY 3 | CHEV 7S NORTH, 8S DAY 3 | BERRY 21Z N & S DAY 3 | BERRY 21Z N & S DAY 3 | BERRY 21Z N & S DAY 3 | BERRY 21Z N & S DAY 3 | BERRY 21Z N & S DAY 3 | BERRY 21Z N & S DAY 3
2018-08-17 | [5 empty] | GARRETT OFF | [11 empty] | MATT OFF |  |  | KAT OFF | GILLIAN BTS | [6 empty] | TOM BTS | PRESTON BTS |  |  | ROBERT V BTS |  |  |  | JACOB OFF | [9 empty] | BRIT BTS |  | CHEV CO 23D DAY 4 | CHEV CO 23D DAY 4 | CHEV CO 23D DAY 4 | CHEV CO 23D DAY 4 | CHEV CO 23D DAY 4 | CHEV CO 23D DAY 4 | CHEV CO 23D DAY 4 | CHEV MWSS 26F, 23F DAY 4 | CHEV MWSS 26F, 23F DAY 4 | CHEV MWSS 26F, 23F DAY 4 | CHEV MWSS 26F, 23F DAY 4 | CHEV MWSS 26F, 23F DAY 4 | CHEV 7S WEST DAY 4 | CHEV 7S WEST DAY 4 | CHEV 7S WEST DAY 4 | CHEV 7S WEST DAY 4 | CHEV 7S NORTH, 8S DAY 4 | CHEV 7S NORTH, 8S DAY 4 | CHEV 7S NORTH, 8S DAY 4 | CHEV 7S NORTH, 8S DAY 4 | BERRY 21Z N & S DAY 4 | BERRY 21Z N & S DAY 4 | BERRY 21Z N & S DAY 4 | BERRY 21Z N & S DAY 4 | BERRY 21Z N & S DAY 4 | BERRY 21Z N & S DAY 4
2018-08-18 | [5 empty] | GARRETT OFF | [14 empty] | KAT OFF | GILLIAN BTS |  |  | LEILANI OFF |  |  | ANNA OFF | TOM BTS | PRESTON BTS | ODETTE OFF |  | ROBERT V BTS |  |  |  | JACOB OFF | [9 empty] | BRIT BTS |  | CHEV CO 23D DAY 5 | CHEV CO 23D DAY 5 | CHEV CO 23D DAY 5 | CHEV CO 23D DAY 5 | CHEV CO 23D DAY 5 | CHEV CO 23D DAY 5 | CHEV CO 23D DAY 5 | CHEV MWSS 26F, 23F DAY 5 | CHEV MWSS 26F, 23F DAY 5 | CHEV MWSS 26F, 23F DAY 5 | CHEV MWSS 26F, 23F DAY 5 | CHEV MWSS 26F, 23F DAY 5 | CHEV 7S WEST DAY 5 | CHEV 7S WEST DAY 5 | CHEV 7S WEST DAY 5 | CHEV 7S WEST DAY 5 | CHEV 7S NORTH, 8S DAY 5 | CHEV 7S NORTH, 8S DAY 5 | CHEV 7S NORTH, 8S DAY 5 | CHEV 7S NORTH, 8S DAY 5 | BERRY 21Z N & S DAY 5 | BERRY 21Z N & S DAY 5 | BERRY 21Z N & S DAY 5 | BERRY 21Z N & S DAY 5 | BERRY 21Z N & S DAY 5 | BERRY 21Z N & S DAY 5
2018-08-19 | [20 empty] | KAT OFF | GILLIAN BTS |  |  | LEILANI OFF |  |  | ANNA OFF | TOM BTS | PRESTON BTS | ODETTE OFF |  | ROBERT V BTS |  |  |  | JACOB OFF | [9 empty] | BRIT BTS
2018-08-20 | [12 empty] | ARACELI OFF | [7 empty] | KAT OFF | GILLIAN BTS | [6 empty] | TOM BTS | PRESTON BTS |  | KAITLYN BTS | ROBERT V BTS | [13 empty] | BRIT BTS |  | AERA MIDDLE BELRIDGE EAST DAY 1 | AERA MIDDLE BELRIDGE EAST DAY 1 | AERA MIDDLE BELRIDGE EAST DAY 1 | AERA MIDDLE BELRIDGE EAST DAY 1 | AERA MIDDLE BELRIDGE EAST DAY 1 | AERA MIDDLE BELRIDGE EAST DAY 1 | AERA CAL SO PIPE DAY 1 | AERA CAL SO PIPE DAY 1 | AERA CAL SO PIPE DAY 1 | AERA CAL SO PIPE DAY 1 | AERA CAL SO PIPE DAY 1 | AERA CAL SO PIPE DAY 1 | CHEV 25 HILL N DAY 1 | CHEV 25 HILL N DAY 1 | CHEV 25 HILL N DAY 1 | CHEV 25 HILL N DAY 1 | CHEV 25 HILL N DAY 1 | CHEV 25 HILL N DAY 1 | CHEV 25 HILL N DAY 1 | CHEV 25 HILL S DAY 1 | CHEV HILL S DAY 1 | CHEV 25 HILL S DAY 1
2018-08-21 | [20 empty] | KAT OFF | GILLIAN BTS | [6 empty] | TOM BTS | PRESTON BTS |  | KAITLYN BTS | ROBERT V BTS | JAMIE BTS | [5 empty] | BRET BTS | [6 empty] | BRIT BTS |  | AERA MIDDLE BELRIDGE EAST DAY 2 | AERA MIDDLE BELRIDGE EAST DAY 2 | AERA MIDDLE BELRIDGE EAST DAY 2 | AERA MIDDLE BELRIDGE EAST DAY 2 | AERA MIDDLE BELRIDGE EAST DAY 2 | AERA MIDDLE BELRIDGE EAST DAY 2 | AERA CAL SO PIPE DAY 2 | AERA CAL SO PIPE DAY 2 | AERA CAL SO PIPE DAY 2 | AERA CAL SO PIPE DAY 2 | AERA CAL SO PIPE DAY 2 | AERA CAL SO PIPE DAY 2 | CHEV 25 HILL N DAY 2 | CHEV 25 HILL N DAY 2 | CHEV 25 HILL N DAY 2 | CHEV 25 HILL N DAY 2 | CHEV 25 HILL N DAY 2 | CHEV 25 HILL N DAY 2 | CHEV 25 HILL N DAY 2 | CHEV 25 HILL S DAY 2 | CHEV HILL S DAY 2 | CHEV 25 HILL S DAY 2
2018-08-22 | [20 empty] | KAT OFF | GILLIAN BTS | [6 empty] | TOM BTS | PRESTON BTS |  | KAITLYN BTS | ROBERT V BTS | JAMIE BTS | [5 empty] | BRET BTS | [6 empty] | BRIT BTS |  | AERA MIDDLE BELRIDGE EAST DAY 3 | AERA MIDDLE BELRIDGE EAST DAY 3 | AERA MIDDLE BELRIDGE EAST DAY 3 | AERA MIDDLE BELRIDGE EAST DAY 3 | AERA MIDDLE BELRIDGE EAST DAY 3 | AERA MIDDLE BELRIDGE EAST DAY 3 | AERA CAL SO PIPE DAY 3 | AERA CAL SO PIPE DAY 3 | AERA CAL SO PIPE DAY 3 | AERA CAL SO PIPE DAY 3 | AERA CAL SO PIPE DAY 3 | AERA CAL SO PIPE DAY 3 | CHEV 25 HILL N DAY 3 | CHEV 25 HILL N DAY 3 | CHEV 25 HILL N DAY 3 | CHEV 25 HILL N DAY 3 | CHEV 25 HILL N DAY 3 | CHEV 25 HILL N DAY 3 | CHEV 25 HILL N DAY 3 | CHEV 25 HILL S DAY 3 | CHEV HILL S DAY 3 | CHEV 25 HILL S DAY 3
2018-08-23 | [20 empty] | KAT OFF | GILLIAN BTS | [6 empty] | TOM BTS | PRESTON BTS |  | KAITLYN BTS | ROBERT V BTS | JAMIE BTS | [5 empty] | BRET BTS | [6 empty] | BRIT BTS |  | AERA MIDDLE BELRIDGE EAST DAY 4 | AERA MIDDLE BELRIDGE EAST DAY 4 | AERA MIDDLE BELRIDGE EAST DAY 4 | AERA MIDDLE BELRIDGE EAST DAY 4 | AERA MIDDLE BELRIDGE EAST DAY 4 | AERA MIDDLE BELRIDGE EAST DAY 4 | AERA CAL SO PIPE DAY 4 | AERA CAL SO PIPE DAY 4 | AERA CAL SO PIPE DAY 4 | AERA CAL SO PIPE DAY 4 | AERA CAL SO PIPE DAY 4 | AERA CAL SO PIPE DAY 4 | CHEV 25 HILL N DAY 4 | CHEV 25 HILL N DAY 4 | CHEV 25 HILL N DAY 4 | CHEV 25 HILL N DAY 4 | CHEV 25 HILL N DAY 4 | CHEV 25 HILL N DAY 4 | CHEV 25 HILL N DAY 4 | CHEV 25 HILL S DAY 4 | CHEV HILL S DAY 4 | CHEV 25 HILL S DAY 4
2018-08-24 | [20 empty] | KAT OFF | GILLIAN BTS | [6 empty] | TOM BTS | PRESTON BTS |  |  | ROBERT V BTS | JAMIE BTS | [5 empty] | BRET BTS | [6 empty] | BRIT BTS |  | AERA MIDDLE BELRIDGE EAST DAY 5 | AERA MIDDLE BELRIDGE EAST DAY 5 | AERA MIDDLE BELRIDGE EAST DAY 5 | AERA MIDDLE BELRIDGE EAST DAY 5 | AERA MIDDLE BELRIDGE EAST DAY 5 | AERA MIDDLE BELRIDGE EAST DAY 5 | AERA CAL SO PIPE DAY 5 | AERA CAL SO PIPE DAY 5 | AERA CAL SO PIPE DAY 5 | AERA CAL SO PIPE DAY 5 | AERA CAL SO PIPE DAY 5 | AERA CAL SO PIPE DAY 5 | CHEV 25 HILL N DAY 5 | CHEV 25 HILL N DAY 5 | CHEV 25 HILL N DAY 5 | CHEV 25 HILL N DAY 5 | CHEV 25 HILL N DAY 5 | CHEV 25 HILL N DAY 5 | CHEV 25 HILL N DAY 5 | CHEV 25 HILL S DAY 5 | CHEV HILL S DAY 5 | CHEV 25 HILL S DAY 5
2018-08-25 | [20 empty] | KAT OFF | GILLIAN BTS |  | DAYNA OFF | LEILANI OFF |  |  |  | TOM BTS | PRESTON BTS |  |  | ROBERT V BTS | JAMIE BTS | [5 empty] | BRET BTS | [6 empty] | BRIT BTS
2018-08-26 | [20 empty] | KAT OFF | GILLIAN BTS |  | DAYNA OFF | LEILANI OFF |  |  |  | TOM BTS | PRESTON BTS | ODETTE OFF |  | ROBERT V BTS | JAMIE BTS | [5 empty] | BRET BTS |  |  |  |  | BRANT BTS |  | BRIT BTS |  | CHEV 32US EAST & SEC29 DAY 1 | CHEV 32US EAST & SEC29 DAY 1 | CHEV 32US EAST & SEC29 DAY 1 | CHEV 32US EAST & SEC29 DAY 1 | CEMC 15G LEASE DAY 1 | CEMC 15G LEASE DAY 1 | CEMC 15G LEASE DAY 1 | 22G DRAINAGES DAY 1 | 22G DRAINAGES DAY 1 | SEC 11/13 GAUGES DAY 1 | SEC 11/13 GAUGES DAY 1 | SEC 11/13 GAUGES DAY 1 | SEC 11/13 GAUGES DAY 1 | SEC 11/13 GAUGES DAY 1 | SEC 11/13 GAUGES DAY 1 | STEVENS DINO & TILT DAY 1 | STEVENS DINO & TILT DAY 1 | STEVENS DINO & TILT DAY 1 | STEVENS DINO & TILT DAY 1 | CEMC 1Y TANKS; WJ8 & 36W DAY 1 | CEMC 1Y TANKS; WJ8 & 36W DAY 1 | CEMC 1Y TANKS; WJ8 & 36W DAY 1
2018-08-27 | [12 empty] | ARACELI OFF | RAINEY BTS |  |  | SAM BTS | MATT BTS |  | COLIN BTS | KAT OFF | GILLIAN BTS | [6 empty] | TOM BTS | PRESTON BTS |  | KAITLYN BTS | ROBERT V BTS | JAMIE BTS |  |  | JACOB BTS |  |  | BRET BTS |  |  | MITCH BTS |  | BRANT BTS |  | BRIT BTS |  | CHEV 32US EAST & SEC29 DAY 2 | CHEV 32US EAST & SEC29 DAY 2 | CHEV 32US EAST & SEC29 DAY 2 | CHEV 32US EAST & SEC29 DAY 2 | CEMC 15G LEASE DAY 2 | CEMC 15G LEASE DAY 2 | CEMC 15G LEASE DAY 2 | 22G DRAINAGES DAY 2 | 22G DRAINAGES DAY 2 | SEC 11/13 GAUGES DAY 2 | SEC 11/13 GAUGES DAY 2 | SEC 11/13 GAUGES DAY 2 | SEC 11/13 GAUGES DAY 2 | SEC 11/13 GAUGES DAY 2 | SEC 11/13 GAUGES DAY 2 | STEVENS DINO & TILT DAY 2 | STEVENS DINO & TILT DAY 2 | STEVENS DINO & TILT DAY 2 | STEVENS DINO & TILT DAY 2 | CEMC 1Y TANKS; WJ8 & 36W DAY 2 | CEMC 1Y TANKS; WJ8 & 36W DAY 2 | CEMC 1Y TANKS; WJ8 & 36W DAY 2
2018-08-28 | [13 empty] | RAINEY BEFORE 2 |  |  | SAM BTS | MATT BTS |  | COLIN BTS | KAT OFF | GILLIAN BTS | [6 empty] | TOM BTS | PRESTON BTS |  | KAITLYN BTS | ROBERT V BTS | JAMIE BTS |  |  | JACOB BTS |  |  | BRET BTS |  |  | MITCH BTS |  | BRANT BTS |  | BRIT BTS |  | CHEV 32US EAST & SEC29 DAY 3 | CHEV 32US EAST & SEC29 DAY 3 | CHEV 32US EAST & SEC29 DAY 3 | CHEV 32US EAST & SEC29 DAY 3 | CEMC 15G LEASE DAY 1 | CEMC 15G LEASE DAY 1 | CEMC 15G LEASE DAY 1 | 22G DRAINAGES DAY 3 | 22G DRAINAGES DAY 3 | SEC 11/13 GAUGES DAY 3 | SEC 11/13 GAUGES DAY 3 | SEC 11/13 GAUGES DAY 3 | SEC 11/13 GAUGES DAY 3 | SEC 11/13 GAUGES DAY 3 | SEC 11/13 GAUGES DAY 3 | STEVENS DINO & TILT DAY 3 | STEVENS DINO & TILT DAY 3 | STEVENS DINO & TILT DAY 3 | STEVENS DINO & TILT DAY 3 | CEMC 1Y TANKS; WJ8 & 36W DAY 3 | CEMC 1Y TANKS; WJ8 & 36W DAY 3 | CEMC 1Y TANKS; WJ8 & 36W DAY 3
2018-08-29 | [13 empty] | RAINEY BTS |  |  | SAM BTS | MATT BTS |  | COLIN BTS | KAT OFF | GILLIAN BTS | [6 empty] | TOM BTS | PRESTON BTS |  | KAITLYN BTS | ROBERT V BTS | JAMIE BTS |  |  | JACOB BTS |  |  | BRET BTS |  |  | MITCH BTS |  | BRANT BTS |  | BRIT BTS |  | CHEV 32US EAST & SEC29 DAY 4 | CHEV 32US EAST & SEC29 DAY 4 | CHEV 32US EAST & SEC29 DAY 4 | CHEV 32US EAST & SEC29 DAY 4 | CEMC 15G LEASE DAY 2 | CEMC 15G LEASE DAY 2 | CEMC 15G LEASE DAY 2 | 22G DRAINAGES DAY 4 | 22G DRAINAGES DAY 4 | SEC 11/13 GAUGES DAY 4 | SEC 11/13 GAUGES DAY 4 | SEC 11/13 GAUGES DAY 4 | SEC 11/13 GAUGES DAY 4 | SEC 11/13 GAUGES DAY 4 | SEC 11/13 GAUGES DAY 4 | STEVENS DINO & TILT DAY 4 | STEVENS DINO & TILT DAY 4 | STEVENS DINO & TILT DAY 4 | STEVENS DINO & TILT DAY 4 | CEMC 1Y TANKS; WJ8 & 36W DAY 4 | CEMC 1Y TANKS; WJ8 & 36W DAY 4 | CEMC 1Y TANKS; WJ8 & 36W DAY 4
2018-08-30 | [13 empty] | RAINEY BEFORE 2 |  | KORISSA OFF | SAM BTS | MATT BTS |  | COLIN BTS | KAT OFF | GILLIAN BTS | [6 empty] | TOM BTS | PRESTON BTS |  | KAITLYN BTS | ROBERT V BTS | JAMIE BTS |  |  | JACOB BTS |  |  | BRET BTS |  |  | MITCH BTS |  | BRANT BTS |  | BRIT BTS |  | CHEV 32US EAST & SEC29 DAY 5 | CHEV 32US EAST & SEC29 DAY 5 | CHEV 32US EAST & SEC29 DAY 5 | CHEV 32US EAST & SEC29 DAY 5 | CEMC 15G LEASE DAY 1 | CEMC 15G LEASE DAY 1 | CEMC 15G LEASE DAY 1 | 22G DRAINAGES DAY 5 | 22G DRAINAGES DAY 5 | SEC 11/13 GAUGES DAY 5 | SEC 11/13 GAUGES DAY 5 | SEC 11/13 GAUGES DAY 5 | SEC 11/13 GAUGES DAY 5 | SEC 11/13 GAUGES DAY 5 | SEC 11/13 GAUGES DAY 5 | STEVENS DINO & TILT DAY 5 | STEVENS DINO & TILT DAY 5 | STEVENS DINO & TILT DAY 5 | STEVENS DINO & TILT DAY 5 | CEMC 1Y TANKS; WJ8 & 36W DAY 5 | CEMC 1Y TANKS; WJ8 & 36W DAY 5 | CEMC 1Y TANKS; WJ8 & 36W DAY 5
2018-08-31 | [11 empty] | ANASTASIYA OFF |  | RAINEY BTS |  | KORISSA OFF | SAM BTS |  |  | COLIN BTS |  | GILLIAN BTS | [6 empty] | TOM BTS | PRESTON BTS |  |  | ROBERT V BTS | JAMIE BTS | [5 empty] | BRET BTS |  |  | MITCH BTS |  | BRANT BTS |  | BRIT BTS
2018-09-01 | [11 empty] | ANASTASIYA OFF |  |  |  | KORISSA OFF | [5 empty] | GILLIAN BTS |  |  | LEILANI OFF |  |  | ANNA OFF | TOM BTS | PRESTON BTS |  |  | ROBERT V BTS | JAMIE BTS | [5 empty] | BRET BTS |  |  | MITCH BTS |  | BRANT BTS |  | BRIT BTS |  | COALINGA NOSE UNIT DAY 1 | COALINGA NOSE UNIT DAY 1 | COALINGA NOSE UNIT DAY 1 | COALINGA NOSE UNIT DAY 1 | COALINGA NOSE UNIT DAY 1 | COALINGA NOSE UNIT DAY 1 | COALINGA NOSE UNIT DAY 1 | COALINGA NOSE UNIT DAY 1 | COALINGA NOSE UNIT DAY 1 | COALINGA NOSE UNIT DAY 1 | ANTELLOPE SHALE & 7Z NOGO DAY 1 | ANTELLOPE SHALE & 7Z NOGO DAY 1 | ANTELLOPE SHALE & 7Z NOGO DAY 1 | CYMRIC WATERLINE DAY 1 | CYMRIC WATERLINE DAY 1 | CYMRIC WATERLINE DAY 1 | CYMRIC WATERLINE DAY 1 | CYMRIC WATERLINE DAY 1 | CYMRIC WATERLINE DAY 1
2018-09-02 | [11 empty] | ANASTASIYA OFF |  |  |  | KORISSA OFF | [5 empty] | GILLIAN BTS |  |  | LEILANI OFF |  |  |  | TOM BTS | PRESTON BTS |  |  | ROBERT V BTS | JAMIE BTS | [5 empty] | BRET BTS |  |  | MITCH BTS |  | BRANT BTS |  | BRIT BTS |  | COALINGA NOSE UNIT DAY 2 | COALINGA NOSE UNIT DAY 2 | COALINGA NOSE UNIT DAY 2 | COALINGA NOSE UNIT DAY 2 | COALINGA NOSE UNIT DAY 2 | COALINGA NOSE UNIT DAY 2 | COALINGA NOSE UNIT DAY 2 | COALINGA NOSE UNIT DAY 2 | COALINGA NOSE UNIT DAY 2 | COALINGA NOSE UNIT DAY 2 | ANTELLOPE SHALE & 7Z NOGO DAY 2 | ANTELLOPE SHALE & 7Z NOGO DAY 2 | ANTELLOPE SHALE & 7Z NOGO DAY 2 | CYMRIC WATERLINE DAY 2 | CYMRIC WATERLINE DAY 2 | CYMRIC WATERLINE DAY 2 | CYMRIC WATERLINE DAY 2 | CYMRIC WATERLINE DAY 2 | CYMRIC WATERLINE DAY 2
2018-09-03 | [11 empty] | ANASTASIYA OFF | ARACELI OFF | RAINEY BTS |  | KORISSA OFF | SAM BTS | MATT BTS |  | COLIN BTS |  | GILLIAN BTS | [6 empty] | TOM BTS | PRESTON BTS |  | KAITLYN BTS | ROBERT V BTS | JAMIE BTS |  |  | JACOB BTS |  |  | BRET BTS |  |  | MITCH BTS |  | BRANT BTS |  | BRIT BTS |  | COALINGA NOSE UNIT DAY 3 | COALINGA NOSE UNIT DAY 3 | COALINGA NOSE UNIT DAY 3 | COALINGA NOSE UNIT DAY 3 | COALINGA NOSE UNIT DAY 3 | COALINGA NOSE UNIT DAY 3 | COALINGA NOSE UNIT DAY 3 | COALINGA NOSE UNIT DAY 3 | COALINGA NOSE UNIT DAY 3 | COALINGA NOSE UNIT DAY 3 | ANTELLOPE SHALE & 7Z NOGO DAY 3 | ANTELLOPE SHALE & 7Z NOGO DAY 3 | ANTELLOPE SHALE & 7Z NOGO DAY 3 | CYMRIC WATERLINE DAY 3 | CYMRIC WATERLINE DAY 3 | CYMRIC WATERLINE DAY 3 | CYMRIC WATERLINE DAY 3 | CYMRIC WATERLINE DAY 3 | CYMRIC WATERLINE DAY 3
2018-09-04 | [11 empty] | ANASTASIYA OFF |  | RAINEY BEFORE 2 |  |  | SAM BTS | MATT BTS |  | COLIN BTS |  | GILLIAN BTS | [6 empty] | TOM BTS | PRESTON BTS |  | KAITLYN BTS | ROBERT V BTS | JAMIE BTS |  |  | JACOB BTS |  |  | BRET BTS |  |  | MITCH BTS |  | BRANT BTS |  | BRIT BTS |  | COALINGA NOSE UNIT DAY 4 | COALINGA NOSE UNIT DAY 4 | COALINGA NOSE UNIT DAY 4 | COALINGA NOSE UNIT DAY 4 | COALINGA NOSE UNIT DAY 4 | COALINGA NOSE UNIT DAY 4 | COALINGA NOSE UNIT DAY 4 | COALINGA NOSE UNIT DAY 4 | COALINGA NOSE UNIT DAY 4 | COALINGA NOSE UNIT DAY 4 | ANTELLOPE SHALE & 7Z NOGO DAY 4 | ANTELLOPE SHALE & 7Z NOGO DAY 4 | ANTELLOPE SHALE & 7Z NOGO DAY 4 | CYMRIC WATERLINE DAY 4 | CYMRIC WATERLINE DAY 4 | CYMRIC WATERLINE DAY 4 | CYMRIC WATERLINE DAY 4 | CYMRIC WATERLINE DAY 4 | CYMRIC WATERLINE DAY 4
2018-09-05 | [11 empty] | ANASTASIYA OFF |  | RAINEY BTS |  |  | SAM BTS | MATT BTS |  | COLIN BTS |  | GILLIAN BTS | [6 empty] | TOM BTS | PRESTON BTS |  | KAITLYN BTS | ROBERT V BTS | JAMIE BTS |  |  | JACOB BTS |  |  | BRET BTS |  |  | MITCH BTS |  | BRANT BTS |  | BRIT BTS |  | COALINGA NOSE UNIT DAY 5 | COALINGA NOSE UNIT DAY 5 | COALINGA NOSE UNIT DAY 5 | COALINGA NOSE UNIT DAY 5 | COALINGA NOSE UNIT DAY 5 | COALINGA NOSE UNIT DAY 5 | COALINGA NOSE UNIT DAY 5 | COALINGA NOSE UNIT DAY 5 | COALINGA NOSE UNIT DAY 5 | COALINGA NOSE UNIT DAY 5 | ANTELLOPE SHALE & 7Z NOGO DAY 5 | ANTELLOPE SHALE & 7Z NOGO DAY 5 | ANTELLOPE SHALE & 7Z NOGO DAY 5 | CYMRIC WATERLINE DAY 5 | CYMRIC WATERLINE DAY 5 | CYMRIC WATERLINE DAY 5 | CYMRIC WATERLINE DAY 5 | CYMRIC WATERLINE DAY 5 | CYMRIC WATERLINE DAY 5
2018-09-06 | [11 empty] | ANASTASIYA OFF |  | RAINEY BEFORE 2 |  |  | SAM BTS | MATT BTS |  | COLIN BTS |  | GILLIAN BTS | [6 empty] | TOM BTS | PRESTON BTS |  | KAITLYN BTS | ROBERT V BTS | JAMIE BTS |  | CJ BTS | JACOB BTS |  |  | BRET BTS |  |  | MITCH BTS |  | BRANT BTS |  | BRIT BTS
2018-09-07 | [11 empty] | ANASTASIYA OFF |  | RAINEY BTS |  |  | SAM BTS |  |  | COLIN BTS |  | GILLIAN BTS | [6 empty] | TOM BTS | PRESTON BTS |  |  | ROBERT V BTS | JAMIE BTS |  | CJ BTS |  |  |  | BRET BTS |  |  | MITCH BTS |  | BRANT BTS |  | BRIT BTS
2018-09-08 | [9 empty] | KIM OFF |  | ANASTASIYA OFF | [9 empty] | GILLIAN BTS |  |  | LEILANI OFF |  |  |  | TOM BTS | PRESTON BTS |  |  | ROBERT V BTS | JAMIE BTS |  | CJ BTS |  |  |  | BRET BTS |  |  | MITCH BTS (OK IF NEEDED) |  | BRANT BTS |  | BRIT BTS
2018-09-09 | [9 empty] | KIM OFF |  | ANASTASIYA OFF | [9 empty] | GILLIAN BTS |  |  | LEILANI OFF |  |  |  | TOM BTS | PRESTON BTS |  |  | ROBERT V BTS | JAMIE BTS |  | CJ BTS |  |  |  | BRET BTS |  |  | MITCH BTS (OK IF NEEDED) |  | BRANT BTS |  | BRIT BTS
2018-09-10 | [9 empty] | KIM OFF |  | ANASTASIYA OFF | ARACELI OFF | RAINEY BTS |  |  | SAM BTS | MATT BTS |  | COLIN BTS |  | GILLIAN BTS | [6 empty] | TOM BTS | PRESTON BTS |  | KAITLYN BTS | ROBERT V BTS | JAMIE BTS |  | CJ BTS | JACOB BTS |  |  | BRET BTS |  |  | MITCH BTS |  | BRANT BTS |  | BRIT BTS
2018-09-11 | [9 empty] | KIM OFF |  | ANASTASIYA OFF |  | RAINEY BEFORE 2 |  |  | SAM BTS | MATT BTS |  | COLIN BTS |  | GILLIAN BTS | [6 empty] | TOM BTS | PRESTON BTS |  | KAITLYN BTS | ROBERT V BTS | JAMIE BTS |  | CJ BTS | JACOB BTS |  |  | BRET BTS |  |  | MITCH BTS |  | BRANT BTS |  | BRIT BTS
2018-09-12 | [9 empty] | KIM OFF |  | ANASTASIYA OFF |  | RAINEY BTS |  |  | SAM BTS | MATT BTS |  | COLIN BTS |  | GILLIAN BTS | [6 empty] | TOM BTS | PRESTON BTS |  | KAITLYN BTS | ROBERT V BTS | JAMIE BTS |  | CJ BTS | JACOB BTS |  |  | BRET BTS |  |  | MITCH BTS |  | BRANT BTS |  | BRIT BTS
2018-09-13 | [9 empty] | KIM OFF |  | ANASTASIYA OFF |  | RAINEY BEFORE 2 |  |  | SAM BTS | MATT BTS |  | COLIN BTS |  | GILLIAN BTS | [6 empty] | TOM BTS | PRESTON BTS |  | KAITLYN BTS | ROBERT V BTS | JAMIE BTS |  | CJ BTS | JACOB BTS |  |  | BRET BTS |  |  | MITCH BTS |  | BRANT BTS |  | BRIT BTS
2018-09-14 | [9 empty] | KIM OFF |  | ANASTASIYA OFF |  | RAINEY BTS |  |  | SAM BTS |  |  | COLIN BTS |  | GILLIAN BTS | [6 empty] | TOM BTS | PRESTON BTS |  |  | ROBERT V BTS | JAMIE BTS |  | CJ BTS |  |  |  | BRET BTS |  |  | MITCH BTS |  | BRANT BTS |  | BRIT BTS
2018-09-15 | [9 empty] | KIM OFF |  | ANASTASIYA OFF | [8 empty] | KAT OFF | GILLIAN BTS |  |  | LEILANI OFF |  |  |  | TOM BTS | PRESTON BTS |  |  | ROBERT V BTS | JAMIE BTS |  | CJ BTS |  |  |  | BRET BTS |  |  | MITCH BTS |  | BRANT BTS |  | BRIT BTS

## GPS Log
Survey | Date Completed | GPS
CHEV 32US EAST & SEC29 DAY 1 | 2018-04-25 | 10 (Alex) | 14 (Dayna) | Ashleigh | Spencer | Sarah | Araceli | Staff
Derby Acres Burn Site Day 1 | 2018-04-25 |  | Blaine | Kim |  |  |  | Seasonal
CEMC 2-22 DAY 1 | 2018-04-25 | 7 (Kat) | Sabrina
CHEV 32US EAST & SEC29 DAY 2 | 2018-04-26 | 10 (Alex) | 14 (Dayna) | Spencer | Sarah
Derby Acres Burn Site Day 2 | 2018-04-26 | Araceli | Korissa
CHEV 32US EAST & SEC29 DAY 3 | 2018-04-27 | 10 (Alex) | (14) Dayna | Spencer | Donna | Sarah
Derby Acres Burn Site Day 3 | 2018-04-27 | Blaine | Araceli
CEMC 2-22 DAY 2 | 2018-04-27 | 7 (Rainey) | Sabrina

## Sheet1
| AARON | JARED | ASHLEIGH | SABRINA | ERIKA | SPENCER | ALLI | BLAINE | TOM | KAYLA | JAKE | WOODY | JACKIE | MARANDA | KATIE | SAM | CORY | SARAH P | CODY | SARAH S | ETHAN | SHADY | JORDAN | RAINEY | ARACELI | JESSICA | KATHARYN | GARRETT
2017-04-15
2017-04-16
2017-04-17 | BERRY MONITORING | BERRY MONITORING
2017-04-18 | BERRY MONITORING | BERRY MONITORING
2017-04-19 | BERRY MONITORING | BERRY MONITORING
2017-04-20 | BERRY MONITORING | BERRY MONITORING
2017-04-21
2017-04-22
2017-04-23
2017-04-24 | BERRY MONITORING | BERRY MONITORING
2017-04-25 | BERRY MONITORING | BERRY MONITORING
2017-04-26 | BERRY MONITORING | BERRY MONITORING
2017-04-27 | BERRY MONITORING | BERRY MONITORING
2017-04-28
2017-04-29
2017-04-30 |  |  | DEHY 2 to Cymric PL DAY 1 | DEHY 2 to Cymric PL DAY 1 | DEHY 2 to Cymric PL DAY 1
2017-05-01 | BERRY MONITORING | BERRY MONITORING | DEHY 2 to Cymric PL DAY 2 | DEHY 2 to Cymric PL DAY 2 | DEHY 2 to Cymric PL DAY 2
2017-05-02 | BERRY MONITORING | BERRY MONITORING | DEHY 2 to Cymric PL DAY 3 | DEHY 2 to Cymric PL DAY 3 | DEHY 2 to Cymric PL DAY 3 | TAFT HS DAY 1 | TAFT HS DAY 1
2017-05-03 | BERRY MONITORING | BERRY MONITORING | DEHY 2 to Cymric PL DAY 4 | DEHY 2 to Cymric PL DAY 4 | DEHY 2 to Cymric PL DAY 4
2017-05-04 | BERRY MONITORING | BERRY MONITORING | DEHY 2 to Cymric PL DAY 5 | DEHY 2 to Cymric PL DAY 5 | DEHY 2 to Cymric PL DAY 5 | TAFT HS DAY 2 | TAFT HS DAY 2
2017-05-05 | TAFT HS DAY 3 | TAFT HS DAY 3 | DEHY 2 to Cymric PL DAY 6 | DEHY 2 to Cymric PL DAY 6 | DEHY 2 to Cymric PL DAY 6 | CEMC CO POLV & CAGEL DAY 1 | CEMC CO POLV & CAGEL DAY 1 | CMEC 36M 502, 307, BUICK DAY 1 | CMEC 36M 502, 307, BUICK DAY 1 | CMEC 36M 502, 307, BUICK DAY 1 | Hill So Cal Gas Line DAY 1 | Hill So Cal Gas Line DAY 1 | Hill So Cal Gas Line DAY 1
2017-05-06 |  | TOO COLD |  | DEHY 2 to Cymric PL DAY 7 | DEHY 2 to Cymric PL DAY 7 | DEHY 2 to Cymric PL DAY 7
2017-05-07 |  | TOO COLD
2017-05-08 | BERRY MONITORING | BERRY MONITORING
2017-05-09 | BERRY MONITORING | BERRY MONITORING | DEHY 2 to Cymric PL DAY 8 | DEHY 2 to Cymric PL DAY 8 | DEHY 2 to Cymric PL DAY 8 | TAFT HS DAY 4 | TAFT HS DAY 4 | CEMC 7-3A & CHEV 1Y SSP SW DAY 1 | CEMC 7-3A & CHEV 1Y SSP SW DAY 1 | CEMC 7-3A & CHEV 1Y SSP SW DAY 1 |  |  | CEMC CO POLV & CAGEL DAY 2 | CEMC CO POLV & CAGEL DAY 2
2017-05-10 | BERRY MONITORING | BERRY MONITORING | CEMC DMT 5 & ANT. SHALE DAY 1 | CEMC DMT 5 & ANT. SHALE DAY 1 | CEMC 7-3A & CHEV 1Y SSP SW DAY 2 | CEMC 7-3A & CHEV 1Y SSP SW DAY 2 | CEMC 7-3A & CHEV 1Y SSP SW DAY 2
2017-05-11 | BERRY MONITORING | BERRY MONITORING | CEMC CO POLV & CAGEL DAY 3 | CEMC CO POLV & CAGEL DAY 3 | CEMC DMT 5 & ANT. SHALE DAY 2 | CEMC DMT 5 & ANT. SHALE DAY 2 | CEMC 7-3A & CHEV 1Y SSP SW DAY 3 | CEMC 7-3A & CHEV 1Y SSP SW DAY 3 | CEMC 7-3A & CHEV 1Y SSP SW DAY 3
2017-05-12
2017-05-13
2017-05-14
2017-05-15
2017-05-16
2017-05-17
2017-05-18 |  |  | CEMC CO POLV & CAGEL DAY 4 | CEMC CO POLV & CAGEL DAY 4 | CHEV CO 23D CEMC 2B 3B DAY 1 | CHEV CO 23D CEMC 2B 3B DAY 1 | CHEV CO 23D CEMC 2B 3B DAY 1 | CHEV CO 23D CEMC 2B 3B DAY 1 | CHEV CO 23D CEMC 2B 3B DAY 1
2017-05-19 |  |  | CMEC 35G & WELL 23 DAY 1 | CMEC 35G & WELL 23 DAY 1 | CMEC 35G & WELL 23 DAY 1 | CMEC 35G & WELL 23 DAY 1 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 1 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 1 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 1 | Hill So Cal Gas Line DAY 2 |  | Hill So Cal Gas Line DAY 2 | Hill So Cal Gas Line DAY 2 | [7 empty] | CEMC F15B & TUM 15, 5, 35U DAY 1 | CEMC F15B & TUM 15, 5, 35U DAY 1 | CEMC F15B & TUM 15, 5, 35U DAY 1
2017-05-20 |  |  | CMEC 35G & WELL 23 DAY 2 | CMEC 35G & WELL 23 DAY 2 | CMEC 35G & WELL 23 DAY 2 | CMEC 35G & WELL 23 DAY 2 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 2 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 2 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 2 | Hill So Cal Gas Line DAY 3 | Hill So Cal Gas Line DAY 3 | Hill So Cal Gas Line DAY 3 | [8 empty] | CEMC F15B & TUM 15, 5, 35U DAY 2 | CEMC F15B & TUM 15, 5, 35U DAY 2 | CEMC F15B & TUM 15, 5, 35U DAY 2
2017-05-21 |  |  | CMEC 35G & WELL 23 DAY 3 | CMEC 35G & WELL 23 DAY 3 | CMEC 35G & WELL 23 DAY 3 | CMEC 35G & WELL 23 DAY 3 |  |  |  | Hill So Cal Gas Line DAY 4 | Hill So Cal Gas Line DAY 4 | Hill So Cal Gas Line DAY 4 | [8 empty] | CEMC F15B & TUM 15, 5, 35U DAY 3 | CEMC F15B & TUM 15, 5, 35U DAY 3 | CEMC F15B & TUM 15, 5, 35U DAY 3
2017-05-22 |  |  | CEMC F15B & TUM 15, 5, 35U DAY 4 | CEMC F15B & TUM 15, 5, 35U DAY 4 | CEMC F15B & TUM 15, 5, 35U DAY 4 | EPC Landfill DAY 1 | EPC Landfill DAY 1 | CMEC 35G & WELL 23 DAY 4 | CMEC 35G & WELL 23 DAY 4 | CMEC 35G & WELL 23 DAY 4 | CMEC 35G & WELL 23 DAY 4 |  |  | EPC Landfill DAY 1 | Training |  |  | Training |  |  | Hill So Cal Gas Line DAY 5 | Hill So Cal Gas Line DAY 5 | Hill So Cal Gas Line DAY 5 | Training | Training
2017-05-23 |  |  | CHEV Stevens & MCK MT DAY 1 | CHEV Stevens & MCK MT DAY 1 | CHEV Stevens & MCK MT DAY 1 | CHEV Stevens & MCK MT DAY 1 | EPC Landfill DAY 2 | HST set 1 DAY 1 | HST set 1 DAY 1 | HST set 1 DAY 1 | HST set 1 DAY 1 | HST set 1 DAY 1 |  | HST set 1 DAY 1 | EPC Landfill DAY 2 |  |  | EPC Landfill DAY 2
2017-05-24 |  |  | CORN CAMP DAY 1 | CORN CAMP DAY 1 | CORN CAMP DAY 1 | EPC Landfill DAY 3 | EPC Landfill DAY 3 | HST set 1 DAY 2 | HST set 1 DAY 2 | HST set 1 DAY 2 | HST set 1 DAY 2 | HST set 1 DAY 2 | HST set 1 DAY 2 | [7 empty] | EPC Landfill DAY 3 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 3 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 3 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 3
2017-05-25 |  |  |  | CHEV MWSS Borrow Area, STA 190 & 31F ETCH DAY 1 | CHEV MWSS Borrow Area, STA 190 & 31F ETCH DAY 1 | EPC Landfill DAY 4 | EPC Landfill DAY 4 | HST set 1 DAY 3 | HST set 1 DAY 3 | HST set 1 DAY 3 | HST set 1 DAY 3 | HST set 1 DAY 3 |  | HST set 1 DAY 3 | EPC Landfill DAY 4 | [6 empty] | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 4 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 4 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 4
2017-05-26 |  |  | Tulare 2017 DAY 1 | Tulare 2017 DAY 1 | Tulare 2017 DAY 1 | HST set 1 DAY 4 | HST set 1 DAY 4 | HST set 1 DAY 4 | HST set 1 DAY 4 | HST set 1 DAY 4 | HST set 1 DAY 4 |  |  | Pleasant Valley DAY 1 | Pleasant Valley DAY 1 |  |  | Pleasant Valley DAY 1 |  |  | Pleasant Valley DAY 1 | Pleasant Valley DAY 1 | Pleasant Valley DAY 1 | [11 empty] | CHEV CO 23D CEMC 2B 3B DAY 2 | CHEV CO 23D CEMC 2B 3B DAY 2 | CHEV CO 23D CEMC 2B 3B DAY 2 | CHEV CO 23D CEMC 2B 3B DAY 2 | CHEV CO 23D CEMC 2B 3B DAY 2 | 1Y FEL, 35W 8-1A, 36W LL DAY 1 | 1Y FEL, 35W 8-1A, 36W LL DAY 1
2017-05-27 | [13 empty] | Pleasant Valley DAY 2 | Pleasant Valley DAY 2 |  |  | Pleasant Valley DAY 2 |  |  | Pleasant Valley DAY 2 | Pleasant Valley DAY 2 | Pleasant Valley DAY 2 | [11 empty] | CHEV CO 23D CEMC 2B 3B DAY 3 | CHEV CO 23D CEMC 2B 3B DAY 3 | CHEV CO 23D CEMC 2B 3B DAY 3 | CHEV CO 23D CEMC 2B 3B DAY 3 | CHEV CO 23D CEMC 2B 3B DAY 3 | 1Y FEL, 35W 8-1A, 36W LL DAY 2 | 1Y FEL, 35W 8-1A, 36W LL DAY 2
2017-05-28 | [12 empty] | Pleasant Valley DAY 3 | Pleasant Valley DAY 3 | Pleasant Valley DAY 3 | Pleasant Valley DAY 3 |  | Pleasant Valley DAY 3 |  |  | Pleasant Valley DAY 3 | [10 empty] | MC ACC &FFA ACC DAY 1 | MC ACC &FFA ACC DAY 1 |  | CHEV CO 23D CEMC 2B 3B DAY 4 | CHEV CO 23D CEMC 2B 3B DAY 4 | CHEV CO 23D CEMC 2B 3B DAY 4 | CHEV CO 23D CEMC 2B 3B DAY 4 | CHEV CO 23D CEMC 2B 3B DAY 4 | 1Y FEL, 35W 8-1A, 36W LL DAY 3 | 1Y FEL, 35W 8-1A, 36W LL DAY 3
2017-05-29 | BERRY MONITORING | BERRY MONITORING | BERRY MONITORING | HST SET 2 DAY 1 | HST SET 2 DAY 1 | HST SET 2 DAY 1 | HST SET 2 DAY 1 | HST SET 2 DAY 1 | HST SET 2 DAY 1 |  |  |  | Pleasant Valley DAY 4 | Pleasant Valley DAY 4 | Pleasant Valley DAY 4 | Pleasant Valley DAY 4 |  | Pleasant Valley DAY 4 |  |  | Pleasant Valley DAY 4 | [10 empty] | MC ACC &FFA ACC DAY 2 | MC ACC &FFA ACC DAY 2 | [6 empty] | 1Y FEL, 35W 8-1A, 36W LL DAY 4 | 1Y FEL, 35W 8-1A, 36W LL DAY 4
2017-05-30 | BERRY MONITORING | BERRY MONITORING | BERRY MONITORING | HST SET 2 DAY 2 | HST SET 2 DAY 2 | HST SET 2 DAY 2 | HST SET 2 DAY 2 | HST SET 2 DAY 2 | HST SET 2 DAY 2 | [11 empty] | CEMC 7-3A & CHEV 1Y SSP SW DAY 4 |  | CEMC 7-3A & CHEV 1Y SSP SW DAY 4 | CEMC 7-3A & CHEV 1Y SSP SW DAY 4 | [7 empty] | MC ACC &FFA ACC DAY 3 | MC ACC &FFA ACC DAY 3 | [9 empty] | Tulare 2017 DAY 2 | Tulare 2017 DAY 2 | Tulare 2017 DAY 2
2017-05-31 | BERRY MONITORING | BERRY MONITORING | BERRY MONITORING | HST SET 2 DAY 3 | HST SET 2 DAY 3 | HST SET 2 DAY 3 | HST SET 2 DAY 3 | HST SET 2 DAY 3 | HST SET 2 DAY 3 | [11 empty] | CEMC DMT 5 & ANT. SHALE DAY 3 |  | CEMC DMT 5 & ANT. SHALE DAY 3 | [8 empty] | MC ACC &FFA ACC DAY 4 | MC ACC &FFA ACC DAY 4 | [9 empty] | Tulare 2017 DAY 3 | Tulare 2017 DAY 3 | Tulare 2017 DAY 3
2017-06-01 | BERRY MONITORING | BERRY MONITORING | BERRY MONITORING | HST SET 2 DAY 4 | HST SET 2 DAY 4 | HST SET 2 DAY 4 | HST SET 2 DAY 4 | HST SET 2 DAY 4 | CHEV Stevens & MCK MT DAY 2 | CHEV Stevens & MCK MT DAY 2 | CHEV Stevens & MCK MT DAY 2 | HST SET 2 DAY 4 |  | CHEV MWSS Borrow Area, STA 190 & 31F ETCH DAY 2 | CHEV MWSS Borrow Area, STA 190 & 31F ETCH DAY 2 | CORN CAMP DAY 2 |  | CORN CAMP DAY 2 | CORN CAMP DAY 2 |  | CEMC DMT 5 & ANT. SHALE DAY 4 |  | CEMC DMT 5 & ANT. SHALE DAY 4 | CHEV Stevens & MCK MT DAY 2 | [18 empty] | Tulare 2017 DAY 4 | Tulare 2017 DAY 4 | Tulare 2017 DAY 4
2017-06-02 |  | BERRY HB DAY 1 | BERRY HB DAY 1 | BERRY HB DAY 1 | BERRY HB DAY 1 | BERRY HB DAY 1 |  |  | CHEV Stevens & MCK MT DAY 3 | CHEV Stevens & MCK MT DAY 3 | CHEV Stevens & MCK MT DAY 3 | CHEV Stevens & MCK MT DAY 3 | CHEV MWSS Borrow Area, STA 190 & 31F ETCH DAY 3 | CHEV MWSS Borrow Area, STA 190 & 31F ETCH DAY 3 | CORN CAMP DAY 3 | CORN CAMP DAY 3 |  | CORN CAMP DAY 3 |  |  | South DEHY 2 to Cymric PL DAY 1 |  | South DEHY 2 to Cymric PL DAY 1 | South DEHY 2 to Cymric PL DAY 1
2017-06-03 |  | BERRY HB DAY 2 | BERRY HB DAY 2 | BERRY HB DAY 2 | BERRY HB DAY 2 | BERRY HB DAY 2 | CHEV MWSS Borrow Area, STA 109 & 31F ETCH DAY 4 | CHEV MWSS Borrow Area, STA 109 & 31F ETCH DAY 4 | 35W 8-1A, 36W LL, 1Y FEL DAY 1 | 35W 8-1A, 36W LL, 1Y FEL DAY 1 | CHEV Stevens & MCK MT DAY 4 | CHEV Stevens & MCK MT DAY 4 | CHEV Stevens & MCK MT DAY 4 | CHEV Stevens & MCK MT DAY 4 |  | CORN CAMP DAY 4 |  | CORN CAMP DAY 4 | CORN CAMP DAY 4 |  | South DEHY 2 to Cymric PL DAY 2 |  | South DEHY 2 to Cymric PL DAY 2 | South DEHY 2 to Cymric PL DAY 2 | [6 empty] | Tulare 2017 DAY 5 | Tulare 2017 DAY 5 | Tulare 2017 DAY 5 | CHEV MWSS Borrow Area, STA 109 & 31F ETCH DAY 5 | CHEV MWSS Borrow Area, STA 109 & 31F ETCH DAY 5 | CEMC F15B & TUM 15, 5, 35U DAY 5 | CEMC F15B & TUM 15, 5, 35U DAY 5 | CEMC F15B & TUM 15, 5, 35U DAY 5 | CEMC 145, CWOD B6-2, 51 DAY 5 | CEMC 145, CWOD B6-2, 51 DAY 5 |  |  |  | CMEC 35G & WELL 23 DAY 5 | CMEC 35G & WELL 23 DAY 5 | CMEC 35G & WELL 23 DAY 5 | CMEC 35G & WELL 23 DAY 5
2017-06-04 |  | DEL MONTE DAY 1 | DEL MONTE DAY 1 | DEL MONTE DAY 1 | CMEC 36M 502, 307, BUICK DAY 2 | CMEC 36M 502, 307, BUICK DAY 2 | CMEC 36M 502, 307, BUICK DAY 2 |  | 35W 8-1A, 36W LL, 1Y FEL DAY 2 | 35W 8-1A, 36W LL, 1Y FEL DAY 2 | BERRY HB DAY 3 | BERRY HB DAY 3 | BERRY HB DAY 3 | BERRY HB DAY 3 | BERRY HB DAY 3 | CORN CAMP DAY 5 |  | CORN CAMP DAY 5 | CORN CAMP DAY 5 |  | South DEHY 2 to Cymric PL DAY 3 |  | South DEHY 2 to Cymric PL DAY 3 | South DEHY 2 to Cymric PL DAY 3 | [6 empty] | Tulare 2017 DAY 6 | Tulare 2017 DAY 6 | Tulare 2017 DAY 6 | CHEV MWSS Borrow Area, STA 109 & 31F ETCH DAY 6 | CHEV MWSS Borrow Area, STA 109 & 31F ETCH DAY 6 | CEMC F15B & TUM 15, 5, 35U DAY 6 | CEMC F15B & TUM 15, 5, 35U DAY 6 | CEMC F15B & TUM 15, 5, 35U DAY 6 | CEMC 145, CWOD B6-2, 51 DAY 6 | CEMC 145, CWOD B6-2, 51 DAY 6 | Hill So Cal Gas Line DAY 6 | Hill So Cal Gas Line DAY 6 | Hill So Cal Gas Line DAY 6 | CMEC 35G & WELL 23 DAY 6 | CMEC 35G & WELL 23 DAY 6 | CMEC 35G & WELL 23 DAY 6 | CMEC 35G & WELL 23 DAY 6
2017-06-05 | BERRY MONITORING | BERRY MONITORING | BERRY MONITORING |  |  | DEL MONTE DAY 2 | DEL MONTE DAY 2 | DEL MONTE DAY 2 | BERRY HB DAY 4 | BERRY HB DAY 4 | BERRY HB DAY 4 | BERRY HB DAY 4 | BERRY HB DAY 4 | CMEC 36M 502, 307, BUICK DAY 3 | CMEC 36M 502, 307, BUICK DAY 3 | CMEC 36M 502, 307, BUICK DAY 3 |  | 35W 8-1A, 36W LL, 1Y FEL DAY 3 | 35W 8-1A, 36W LL, 1Y FEL DAY 3 |  | South DEHY 2 to Cymric PL DAY 4 |  | South DEHY 2 to Cymric PL DAY 4 | South DEHY 2 to Cymric PL DAY 4 | AERA BERMS DAY 1 | AERA BERMS DAY 1 | AERA BERMS DAY 1 |  |  |  | Tulare 2017 DAY 7 | Tulare 2017 DAY 7 | Tulare 2017 DAY 7 | CHEV MWSS Borrow Area, STA 109 & 31F ETCH DAY 7 | CHEV MWSS Borrow Area, STA 109 & 31F ETCH DAY 7 | CEMC F15B & TUM 15, 5, 35U DAY 7 | CEMC F15B & TUM 15, 5, 35U DAY 7 | CEMC F15B & TUM 15, 5, 35U DAY 7 | CEMC 145, CWOD B6-2, 51 DAY 7 | CEMC 145, CWOD B6-2, 51 DAY 7 | Hill So Cal Gas Line DAY 7 | Hill So Cal Gas Line DAY 7 | Hill So Cal Gas Line DAY 7 | CMEC 35G & WELL 23 DAY 7 | CMEC 35G & WELL 23 DAY 7 | CMEC 35G & WELL 23 DAY 7 | CMEC 35G & WELL 23 DAY 7
2017-06-06 | BERRY MONITORING | BERRY MONITORING | BERRY MONITORING |  |  | ORAGAMI 21Z DAY 1 | ORAGAMI 21Z DAY 1 | ORAGAMI 21Z DAY 4 | CEMC LK WW #1 DAY 1 | CEMC LK WW #1 DAY 1 | CEMC LK WW #1 DAY 1 | DEL MONTE DAY 3 |  | DEL MONTE DAY 3 | DEL MONTE DAY 3 | CEMC 145, CWOD B6-2, 51 DAY 1 |  | CEMC 145, CWOD B6-2, 51 DAY 1 | CMEC 36M 502, 307, BUICK DAY 4 | CMEC 36M 502, 307, BUICK DAY 4 | CMEC 36M 502, 307, BUICK DAY 4 |  | 35W 8-1A, 36W LL, 1Y FEL DAY 4 | 35W 8-1A, 36W LL, 1Y FEL DAY 4 | AERA BERMS DAY 2 | AERA BERMS DAY 2 | AERA BERMS DAY 2 | LH HZ AREA DAY 1 | LH HZ AREA DAY 1 | LH HZ AREA DAY 1 | Tulare 2017 DAY 8 | Tulare 2017 DAY 8 | Tulare 2017 DAY 8 | CHEV MWSS Borrow Area, STA 109 & 31F ETCH DAY 8 | CHEV MWSS Borrow Area, STA 109 & 31F ETCH DAY 8 | CEMC F15B & TUM 15, 5, 35U DAY 8 | CEMC F15B & TUM 15, 5, 35U DAY 8 | CEMC F15B & TUM 15, 5, 35U DAY 8 | CEMC 145, CWOD B6-2, 51 DAY 8 | CEMC 145, CWOD B6-2, 51 DAY 8 | Hill So Cal Gas Line DAY 8 | Hill So Cal Gas Line DAY 8 | Hill So Cal Gas Line DAY 8 | CMEC 35G & WELL 23 DAY 8 | CMEC 35G & WELL 23 DAY 8 | CMEC 35G & WELL 23 DAY 8 | CMEC 35G & WELL 23 DAY 8
2017-06-07 | BERRY MONITORING | BERRY MONITORING | BERRY MONITORING |  |  | ORAGAMI 21Z DAY 1 | ORAGAMI 21Z DAY 2 | ORAGAMI 21Z DAY 2 | CMEC 36M 502, 307, BUICK DAY 5 | CMEC 36M 502, 307, BUICK DAY 5 | CMEC 36M 502, 307, BUICK DAY 5 | DEL MONTE DAY 4 | DEL MONTE DAY 4 | DEL MONTE DAY 4 | CEMC 145, CWOD B6-2, 51 DAY 2 | CEMC 145, CWOD B6-2, 51 DAY 2 |  | AERA BERMS DAY 3 | CEMC LK WW #1 DAY 2 | CEMC LK WW #1 DAY 2 | CEMC LK WW #1 DAY 2 |  | AERA BERMS DAY 3 | AERA BERMS DAY 3 | EPC Landfill DAY 5 | EPC Landfill DAY 5 | EPC Landfill DAY 5 | LH HZ AREA DAY 2 | LH HZ AREA DAY 2 | LH HZ AREA DAY 2 | Tulare 2017 DAY 9 | Tulare 2017 DAY 9 | Tulare 2017 DAY 9 | CHEV MWSS Borrow Area, STA 109 & 31F ETCH DAY 9 | CHEV MWSS Borrow Area, STA 109 & 31F ETCH DAY 9 | CEMC F15B & TUM 15, 5, 35U DAY 9 | CEMC F15B & TUM 15, 5, 35U DAY 9 | CEMC F15B & TUM 15, 5, 35U DAY 9 | CEMC 145, CWOD B6-2, 51 DAY 9 | CEMC 145, CWOD B6-2, 51 DAY 9 | Hill So Cal Gas Line DAY 9 | Hill So Cal Gas Line DAY 9 | Hill So Cal Gas Line DAY 9 | CMEC 35G & WELL 23 DAY 9 | CMEC 35G & WELL 23 DAY 9 | CMEC 35G & WELL 23 DAY 9 | CMEC 35G & WELL 23 DAY 9
2017-06-08 | BERRY MONITORING | BERRY MONITORING | BERRY MONITORING |  |  | ORAGAMI 21Z DAY 2 | ORAGAMI 21Z DAY 3 | ORAGAMI 21Z DAY 3 | CEMC LK WW #1 DAY 3 | CEMC LK WW #1 DAY 3 | CEMC LK WW #1 DAY 3 |  |  |  | CEMC 145, CWOD B6-2, 51 DAY 3 | CEMC 145, CWOD B6-2, 51 DAY 3 |  |  |  |  | AERA BERMS DAY 4 |  | AERA BERMS DAY 4 | AERA BERMS DAY 4 |  |  |  | LH HZ AREA DAY 3 | LH HZ AREA DAY 3 | LH HZ AREA DAY 3 | Tulare 2017 DAY 10 | Tulare 2017 DAY 10 | Tulare 2017 DAY 10 | CHEV MWSS Borrow Area, STA 109 & 31F ETCH DAY 10 | CHEV MWSS Borrow Area, STA 109 & 31F ETCH DAY 10 | CEMC F15B & TUM 15, 5, 35U DAY 10 | CEMC F15B & TUM 15, 5, 35U DAY 10 | CEMC F15B & TUM 15, 5, 35U DAY 10 | CEMC 145, CWOD B6-2, 51 DAY 10 | CEMC 145, CWOD B6-2, 51 DAY 10 | Hill So Cal Gas Line DAY 10 | Hill So Cal Gas Line DAY 10 | Hill So Cal Gas Line DAY 10 | CMEC 35G & WELL 23 DAY 10 | CMEC 35G & WELL 23 DAY 10 | CMEC 35G & WELL 23 DAY 10 | CMEC 35G & WELL 23 DAY 10
2017-06-09 | South DEHY 2 to Cymric PL DAY 5 | South DEHY 2 to Cymric PL DAY 5 | South DEHY 2 to Cymric PL DAY 5 | ORAGAMI 21Z DAY 3 | ORAGAMI 21Z DAY 4 | ORAGAMI 21Z DAY 4 |  |  | CEMC LK WW #1 DAY 4 | CEMC LK WW #1 DAY 4 | CEMC LK WW #1 DAY 4 |  |  |  | CEMC 145, CWOD B6-2, 51 DAY 4 | CEMC 145, CWOD B6-2, 51 DAY 4 | [11 empty] | LH HZ AREA DAY 4 | LH HZ AREA DAY 4 | LH HZ AREA DAY 4 | Tulare 2017 DAY 11 | Tulare 2017 DAY 11 | Tulare 2017 DAY 11 | CHEV MWSS Borrow Area, STA 109 & 31F ETCH DAY 11 | CHEV MWSS Borrow Area, STA 109 & 31F ETCH DAY 11 | CEMC F15B & TUM 15, 5, 35U DAY 11 | CEMC F15B & TUM 15, 5, 35U DAY 11 | CEMC F15B & TUM 15, 5, 35U DAY 11 | CEMC 145, CWOD B6-2, 51 DAY 11 | CEMC 145, CWOD B6-2, 51 DAY 11 | Hill So Cal Gas Line DAY 11 | Hill So Cal Gas Line DAY 11 | Hill So Cal Gas Line DAY 11 | CMEC 35G & WELL 23 DAY 11 | CMEC 35G & WELL 23 DAY 11 | CMEC 35G & WELL 23 DAY 11 | CMEC 35G & WELL 23 DAY 11
2017-06-10 |  | South DEHY 2 to Cymric PL DAY 6 | South DEHY 2 to Cymric PL DAY 6 | South DEHY 2 to Cymric PL DAY 6 | [26 empty] | Tulare 2017 DAY 12 | Tulare 2017 DAY 12 | Tulare 2017 DAY 12 | CHEV MWSS Borrow Area, STA 109 & 31F ETCH DAY 12 | CHEV MWSS Borrow Area, STA 109 & 31F ETCH DAY 12 | CEMC F15B & TUM 15, 5, 35U DAY 12 | CEMC F15B & TUM 15, 5, 35U DAY 12 | CEMC F15B & TUM 15, 5, 35U DAY 12 | CEMC 145, CWOD B6-2, 51 DAY 12 | CEMC 145, CWOD B6-2, 51 DAY 12 | Hill So Cal Gas Line DAY 12 | Hill So Cal Gas Line DAY 12 | Hill So Cal Gas Line DAY 12 | CMEC 35G & WELL 23 DAY 12 | CMEC 35G & WELL 23 DAY 12 | CMEC 35G & WELL 23 DAY 12 | CMEC 35G & WELL 23 DAY 12
2017-06-11 |  | South DEHY 2 to Cymric PL DAY 7 | South DEHY 2 to Cymric PL DAY 7 | South DEHY 2 to Cymric PL DAY 7 | [26 empty] | CEMC DMT 5 & ANT. SHALE DAY 5 | CEMC DMT 5 & ANT. SHALE DAY 5 | [6 empty] | Pleasant Valley DAY 5 | Pleasant Valley DAY 5 | Pleasant Valley DAY 5 | Pleasant Valley DAY 5 | Pleasant Valley DAY 5 | Pleasant Valley DAY 5 | AERA BERMS DAY 5 | AERA BERMS DAY 5 | AERA BERMS DAY 5
2017-06-12 | BERRY MONITORING | BERRY MONITORING | BERRY MONITORING | HST set 1 DAY 5 | HST set 1 DAY 5 | HST set 1 DAY 5 | HST set 1 DAY 5 | HST set 1 DAY 5 | HST set 1 DAY 5 | [8 empty] | South DEHY 2 to Cymric PL DAY 8 | South DEHY 2 to Cymric PL DAY 8 | South DEHY 2 to Cymric PL DAY 8 | [10 empty] | CEMC DMT 5 & ANT. SHALE DAY 6 | CEMC DMT 5 & ANT. SHALE DAY 6 | CMEC 36M 502, 307, BUICK DAY 6 | CMEC 36M 502, 307, BUICK DAY 6 | CMEC 36M 502, 307, BUICK DAY 6 | CORN CAMP DAY 6 | CORN CAMP DAY 6 | CORN CAMP DAY 6 | Pleasant Valley DAY 6 | Pleasant Valley DAY 6 | Pleasant Valley DAY 6 | Pleasant Valley DAY 6 | Pleasant Valley DAY 6 | Pleasant Valley DAY 6 | AERA BERMS DAY 6 | AERA BERMS DAY 6 | AERA BERMS DAY 6
2017-06-13 | BERRY MONITORING | BERRY MONITORING | BERRY MONITORING | HST set 1 DAY 6 | HST set 1 DAY 6 | HST set 1 DAY 6 | HST set 1 DAY 6 | HST set 1 DAY 6 | HST set 1 DAY 6 | [21 empty] | CEMC DMT 5 & ANT. SHALE DAY 7 | CEMC DMT 5 & ANT. SHALE DAY 7 | CMEC 36M 502, 307, BUICK DAY 7 | CMEC 36M 502, 307, BUICK DAY 7 | CMEC 36M 502, 307, BUICK DAY 7 | CORN CAMP DAY 7 | CORN CAMP DAY 7 | CORN CAMP DAY 7 | Pleasant Valley DAY 7 | Pleasant Valley DAY 7 | Pleasant Valley DAY 7 | Pleasant Valley DAY 7 | Pleasant Valley DAY 7 | Pleasant Valley DAY 7 | AERA BERMS DAY 7 | AERA BERMS DAY 7 | AERA BERMS DAY 7
2017-06-14 | BERRY MONITORING | BERRY MONITORING | BERRY MONITORING | HST set 1 DAY 7 | HST set 1 DAY 7 | HST set 1 DAY 7 | HST set 1 DAY 7 | HST set 1 DAY 7 | HST set 1 DAY 7 | [21 empty] | CEMC DMT 5 & ANT. SHALE DAY 8 | CEMC DMT 5 & ANT. SHALE DAY 8 | CMEC 36M 502, 307, BUICK DAY 8 | CMEC 36M 502, 307, BUICK DAY 8 | CMEC 36M 502, 307, BUICK DAY 8 | CORN CAMP DAY 8 | CORN CAMP DAY 8 | CORN CAMP DAY 8 | Pleasant Valley DAY 8 | Pleasant Valley DAY 8 | Pleasant Valley DAY 8 | Pleasant Valley DAY 8 | Pleasant Valley DAY 8 | Pleasant Valley DAY 8 | AERA BERMS DAY 8 | AERA BERMS DAY 8 | AERA BERMS DAY 8
2017-06-15 | BERRY MONITORING | BERRY MONITORING | BERRY MONITORING | HST set 1 DAY 8 | HST set 1 DAY 8 | HST set 1 DAY 8 | HST set 1 DAY 8 | HST set 1 DAY 8 | HST set 1 DAY 8 | [21 empty] | CEMC DMT 5 & ANT. SHALE DAY 9 | CEMC DMT 5 & ANT. SHALE DAY 9 | CMEC 36M 502, 307, BUICK DAY 9 | CMEC 36M 502, 307, BUICK DAY 9 | CMEC 36M 502, 307, BUICK DAY 9 | CORN CAMP DAY 9 | CORN CAMP DAY 9 | CORN CAMP DAY 9 | Pleasant Valley DAY 9 | Pleasant Valley DAY 9 | Pleasant Valley DAY 9 | Pleasant Valley DAY 9 | Pleasant Valley DAY 9 | Pleasant Valley DAY 9 | AERA BERMS DAY 9 | AERA BERMS DAY 9 | AERA BERMS DAY 9
2017-06-16 | [30 empty] | CEMC DMT 5 & ANT. SHALE DAY 10 | CEMC DMT 5 & ANT. SHALE DAY 10 | CMEC 36M 502, 307, BUICK DAY 10 | CMEC 36M 502, 307, BUICK DAY 10 | CMEC 36M 502, 307, BUICK DAY 10 | CORN CAMP DAY 10 | CORN CAMP DAY 10 | CORN CAMP DAY 10 | Pleasant Valley DAY 10 | Pleasant Valley DAY 10 | Pleasant Valley DAY 10 | Pleasant Valley DAY 10 | Pleasant Valley DAY 10 | Pleasant Valley DAY 10 | AERA BERMS DAY 10 | AERA BERMS DAY 10 | AERA BERMS DAY 10
2017-06-17 | [30 empty] | CEMC DMT 5 & ANT. SHALE DAY 11 | CEMC DMT 5 & ANT. SHALE DAY 11 | CMEC 36M 502, 307, BUICK DAY 11 | CMEC 36M 502, 307, BUICK DAY 11 | CMEC 36M 502, 307, BUICK DAY 11 | CORN CAMP DAY 11 | CORN CAMP DAY 11 | CORN CAMP DAY 11 | Pleasant Valley DAY 11 | Pleasant Valley DAY 11 | Pleasant Valley DAY 11 | Pleasant Valley DAY 11 | Pleasant Valley DAY 11 | Pleasant Valley DAY 11 | AERA BERMS DAY 11 | AERA BERMS DAY 11 | AERA BERMS DAY 11 |  |  | CHEV BEECROFT PIPE DAY 1 | CHEV BEECROFT PIPE DAY 1 | CHEV BEECROFT PIPE DAY 1 | VALLEY WATER MCK PONDS DAY 1 | VALLEY WATER MCK PONDS DAY 1 | VALLEY WATER MCK PONDS DAY 1 | CYM WATER LINE DAY 1 | CYM WATER LINE DAY 1 | CYM WATER LINE DAY 1 | CYM WATER LINE DAY 1 | CYM WATER LINE DAY 1 | CYM WATER LINE DAY 1
2017-06-18 | [30 empty] | CEMC DMT 5 & ANT. SHALE DAY 12 | CEMC DMT 5 & ANT. SHALE DAY 12 | CMEC 36M 502, 307, BUICK DAY 12 | CMEC 36M 502, 307, BUICK DAY 12 | CMEC 36M 502, 307, BUICK DAY 12 | CORN CAMP DAY 12 | CORN CAMP DAY 12 | CORN CAMP DAY 12 | Pleasant Valley DAY 12 | Pleasant Valley DAY 12 | Pleasant Valley DAY 12 | Pleasant Valley DAY 12 | Pleasant Valley DAY 12 | Pleasant Valley DAY 12 | AERA BERMS DAY 12 | AERA BERMS DAY 12 | AERA BERMS DAY 12 |  |  | CHEV BEECROFT PIPE DAY 2 | CHEV BEECROFT PIPE DAY 2 | CHEV BEECROFT PIPE DAY 3 | VALLEY WATER MCK PONDS DAY 2 | VALLEY WATER MCK PONDS DAY 2 | VALLEY WATER MCK PONDS DAY 2 | CYM WATER LINE DAY 2 | CYM WATER LINE DAY 2 | CYM WATER LINE DAY 2 | CYM WATER LINE DAY 2 | CYM WATER LINE DAY 2 | CYM WATER LINE DAY 2
2017-06-19 | BERRY MONITORING | BERRY MONITORING | BERRY MONITORING | HST SET 2 DAY 5 | HST SET 2 DAY 5 | HST SET 2 DAY 5 | HST SET 2 DAY 5 | HST SET 2 DAY 5 | HST SET 2 DAY 5 | [24 empty] | 35W 8-1A, 36W LL, 1Y FEL DAY 5 | 35W 8-1A, 36W LL, 1Y FEL DAY 5 | CEMC CO POLV & CAGEL DAY 5 | CEMC CO POLV & CAGEL DAY 5 | DEL MONTE DAY 5 | DEL MONTE DAY 5 | DEL MONTE DAY 5 | MC ACC &FFA ACC DAY 5 | MC ACC &FFA ACC DAY 5 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 5 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 5 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 5 | TAFT HS DAY 5 | TAFT HS DAY 5 | 1Y FEL, 35W 8-1A, 36W LL DAY 5 | 1Y FEL, 35W 8-1A, 36W LL DAY 5 | CHEV BEECROFT PIPE DAY 3 | CHEV BEECROFT PIPE DAY 3 | CHEV BEECROFT PIPE DAY 4 | VALLEY WATER MCK PONDS DAY 3 | VALLEY WATER MCK PONDS DAY 3 | VALLEY WATER MCK PONDS DAY 3 | CYM WATER LINE DAY 3 | CYM WATER LINE DAY 3 | CYM WATER LINE DAY 3 | CYM WATER LINE DAY 3 | CYM WATER LINE DAY 3 | CYM WATER LINE DAY 3
2017-06-20 | BERRY MONITORING | BERRY MONITORING | BERRY MONITORING | HST SET 2 DAY 6 | HST SET 2 DAY 6 | HST SET 2 DAY 6 | HST SET 2 DAY 6 | HST SET 2 DAY 6 | HST SET 2 DAY 6 | [21 empty] | EPC Landfill DAY 6 | EPC Landfill DAY 6 | EPC Landfill DAY 6 | 35W 8-1A, 36W LL, 1Y FEL DAY 6 | 35W 8-1A, 36W LL, 1Y FEL DAY 6 | CEMC CO POLV & CAGEL DAY 6 | CEMC CO POLV & CAGEL DAY 6 | DEL MONTE DAY 6 | DEL MONTE DAY 6 | DEL MONTE DAY 6 | MC ACC &FFA ACC DAY 6 | MC ACC &FFA ACC DAY 6 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 6 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 6 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 6 | TAFT HS DAY 6 | TAFT HS DAY 6 | 1Y FEL, 35W 8-1A, 36W LL DAY 6 | 1Y FEL, 35W 8-1A, 36W LL DAY 6 | CHEV BEECROFT PIPE DAY 4 | CHEV BEECROFT PIPE DAY 4 | CHEV BEECROFT PIPE DAY 2 | VALLEY WATER MCK PONDS DAY 4 | VALLEY WATER MCK PONDS DAY 4 | VALLEY WATER MCK PONDS DAY 4 | CYM WATER LINE DAY 4 | CYM WATER LINE DAY 4 | CYM WATER LINE DAY 4 | CYM WATER LINE DAY 4 | CYM WATER LINE DAY 4 | CYM WATER LINE DAY 4
2017-06-21 | BERRY MONITORING | BERRY MONITORING | BERRY MONITORING | HST SET 2 DAY 7 | HST SET 2 DAY 7 | HST SET 2 DAY 7 | HST SET 2 DAY 7 | HST SET 2 DAY 7 | HST SET 2 DAY 7 | [21 empty] | EPC Landfill DAY 7 | EPC Landfill DAY 7 | EPC Landfill DAY 7 | 35W 8-1A, 36W LL, 1Y FEL DAY 7 | 35W 8-1A, 36W LL, 1Y FEL DAY 7 | CEMC CO POLV & CAGEL DAY 7 | CEMC CO POLV & CAGEL DAY 7 | DEL MONTE DAY 7 | DEL MONTE DAY 7 | DEL MONTE DAY 7 | MC ACC &FFA ACC DAY 7 | MC ACC &FFA ACC DAY 7 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 7 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 7 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 7 | TAFT HS DAY 7 | TAFT HS DAY 7 | 1Y FEL, 35W 8-1A, 36W LL DAY 7 | 1Y FEL, 35W 8-1A, 36W LL DAY 7 | CHEV BEECROFT PIPE DAY 5 | CHEV BEECROFT PIPE DAY 5 | CHEV BEECROFT PIPE DAY 5 | VALLEY WATER MCK PONDS DAY 5 | VALLEY WATER MCK PONDS DAY 5 | VALLEY WATER MCK PONDS DAY 5 | CYM WATER LINE DAY 5 | CYM WATER LINE DAY 5 | CYM WATER LINE DAY 5 | CYM WATER LINE DAY 5 | CYM WATER LINE DAY 5 | CYM WATER LINE DAY 5
2017-06-22 | BERRY MONITORING | BERRY MONITORING | BERRY MONITORING | HST SET 2 DAY 8 | HST SET 2 DAY 8 | HST SET 2 DAY 8 | HST SET 2 DAY 8 | HST SET 2 DAY 8 | HST SET 2 DAY 8 | [21 empty] | EPC Landfill DAY 8 | EPC Landfill DAY 8 | EPC Landfill DAY 8 | 35W 8-1A, 36W LL, 1Y FEL DAY 8 | 35W 8-1A, 36W LL, 1Y FEL DAY 8 | CEMC CO POLV & CAGEL DAY 8 | CEMC CO POLV & CAGEL DAY 8 | DEL MONTE DAY 8 | DEL MONTE DAY 8 | DEL MONTE DAY 8 | MC ACC &FFA ACC DAY 8 | MC ACC &FFA ACC DAY 8 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 8 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 8 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 8 | TAFT HS DAY 8 | TAFT HS DAY 8 | 1Y FEL, 35W 8-1A, 36W LL DAY 8 | 1Y FEL, 35W 8-1A, 36W LL DAY 8 | CHEV BEECROFT PIPE DAY 6 | CHEV BEECROFT PIPE DAY 6 | CHEV BEECROFT PIPE DAY 6 | VALLEY WATER MCK PONDS DAY 6 | VALLEY WATER MCK PONDS DAY 6 | VALLEY WATER MCK PONDS DAY 6 | CYM WATER LINE DAY 6 | CYM WATER LINE DAY 6 | CYM WATER LINE DAY 6 | CYM WATER LINE DAY 6 | CYM WATER LINE DAY 6 | CYM WATER LINE DAY 6
2017-06-23 | [30 empty] | EPC Landfill DAY 9 | EPC Landfill DAY 9 | EPC Landfill DAY 9 | 35W 8-1A, 36W LL, 1Y FEL DAY 9 | 35W 8-1A, 36W LL, 1Y FEL DAY 9 | CEMC CO POLV & CAGEL DAY 9 | CEMC CO POLV & CAGEL DAY 9 | DEL MONTE DAY 9 | DEL MONTE DAY 9 | DEL MONTE DAY 9 | MC ACC &FFA ACC DAY 9 | MC ACC &FFA ACC DAY 9 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 9 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 9 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 9 | TAFT HS DAY 9 | TAFT HS DAY 9 | 1Y FEL, 35W 8-1A, 36W LL DAY 9 | 1Y FEL, 35W 8-1A, 36W LL DAY 9 | CHEV BEECROFT PIPE DAY 7 | CHEV BEECROFT PIPE DAY 7 | CHEV BEECROFT PIPE DAY 7 | VALLEY WATER MCK PONDS DAY 7 | VALLEY WATER MCK PONDS DAY 7 | VALLEY WATER MCK PONDS DAY 7 | CYM WATER LINE DAY 7 | CYM WATER LINE DAY 7 | CYM WATER LINE DAY 7 | CYM WATER LINE DAY 7 | CYM WATER LINE DAY 7 | CYM WATER LINE DAY 7
2017-06-24 | [30 empty] | EPC Landfill DAY 10 | EPC Landfill DAY 10 | EPC Landfill DAY 10 | 35W 8-1A, 36W LL, 1Y FEL DAY 10 | 35W 8-1A, 36W LL, 1Y FEL DAY 10 | CEMC CO POLV & CAGEL DAY 10 | CEMC CO POLV & CAGEL DAY 10 | DEL MONTE DAY 10 | DEL MONTE DAY 10 | DEL MONTE DAY 10 | MC ACC &FFA ACC DAY 10 | MC ACC &FFA ACC DAY 10 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 10 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 10 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 10 | TAFT HS DAY 10 | TAFT HS DAY 10 | 1Y FEL, 35W 8-1A, 36W LL DAY 10 | 1Y FEL, 35W 8-1A, 36W LL DAY 10 | CHEV BEECROFT PIPE DAY 8 | CHEV BEECROFT PIPE DAY 8 | CHEV BEECROFT PIPE DAY 8 | VALLEY WATER MCK PONDS DAY 8 | VALLEY WATER MCK PONDS DAY 8 | VALLEY WATER MCK PONDS DAY 8 | CYM WATER LINE DAY 8 | CYM WATER LINE DAY 8 | CYM WATER LINE DAY 8 | CYM WATER LINE DAY 8 | CYM WATER LINE DAY 8 | CYM WATER LINE DAY 8
2017-06-25 | [30 empty] | EPC Landfill DAY 11 | EPC Landfill DAY 11 | EPC Landfill DAY 11 | 35W 8-1A, 36W LL, 1Y FEL DAY 11 | 35W 8-1A, 36W LL, 1Y FEL DAY 11 | CEMC CO POLV & CAGEL DAY 11 | CEMC CO POLV & CAGEL DAY 11 | DEL MONTE DAY 11 | DEL MONTE DAY 11 | DEL MONTE DAY 11 | MC ACC &FFA ACC DAY 11 | MC ACC &FFA ACC DAY 11 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 11 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 11 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 11 | TAFT HS DAY 11 | TAFT HS DAY 11 | 1Y FEL, 35W 8-1A, 36W LL DAY 11 | 1Y FEL, 35W 8-1A, 36W LL DAY 11 | CHEV BEECROFT PIPE DAY 9 | CHEV BEECROFT PIPE DAY 9 | CHEV BEECROFT PIPE DAY 9 | VALLEY WATER MCK PONDS DAY 9 | VALLEY WATER MCK PONDS DAY 9 | VALLEY WATER MCK PONDS DAY 9 | CYM WATER LINE DAY 9 | CYM WATER LINE DAY 9 | CYM WATER LINE DAY 9 | CYM WATER LINE DAY 9 | CYM WATER LINE DAY 9 | CYM WATER LINE DAY 9
2017-06-26 | BERRY MONITORING | BERRY MONITORING | BERRY MONITORING | HST set 1 DAY 9 | HST set 1 DAY 9 | HST set 1 DAY 9 | HST set 1 DAY 9 | HST set 1 DAY 9 | HST set 1 DAY 9 | [21 empty] | EPC Landfill DAY 12 | EPC Landfill DAY 12 | EPC Landfill DAY 12 | 35W 8-1A, 36W LL, 1Y FEL DAY 12 | 35W 8-1A, 36W LL, 1Y FEL DAY 12 | CEMC CO POLV & CAGEL DAY 12 | CEMC CO POLV & CAGEL DAY 12 | DEL MONTE DAY 12 | DEL MONTE DAY 12 | DEL MONTE DAY 12 | MC ACC &FFA ACC DAY 12 | MC ACC &FFA ACC DAY 12 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 12 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 12 | CHEV 2017 7Z 8Z & CEMC MCN ABAN DAY 12 | TAFT HS DAY 12 | TAFT HS DAY 12 | 1Y FEL, 35W 8-1A, 36W LL DAY 12 | 1Y FEL, 35W 8-1A, 36W LL DAY 12 | CHEV BEECROFT PIPE DAY 10 | CHEV BEECROFT PIPE DAY 10 | CHEV BEECROFT PIPE DAY 10 | VALLEY WATER MCK PONDS DAY 10 | VALLEY WATER MCK PONDS DAY 10 | VALLEY WATER MCK PONDS DAY 10 | CYM WATER LINE DAY 10 | CYM WATER LINE DAY 10 | CYM WATER LINE DAY 10 | CYM WATER LINE DAY 10 | CYM WATER LINE DAY 10 | CYM WATER LINE DAY 10
2017-06-27 | BERRY MONITORING | BERRY MONITORING | BERRY MONITORING | HST set 1 DAY 10 | HST set 1 DAY 10 | HST set 1 DAY 10 | HST set 1 DAY 10 | HST set 1 DAY 11 | HST set 1 DAY 11 | [21 empty] | LH HZ AREA DAY 5 | LH HZ AREA DAY 5 | LH HZ AREA DAY 5 | CHEV CO 23D CEMC 2B 3B DAY 5 | CHEV CO 23D CEMC 2B 3B DAY 5 | CHEV CO 23D CEMC 2B 3B DAY 5 | CHEV CO 23D CEMC 2B 3B DAY 5 | CHEV CO 23D CEMC 2B 3B DAY 5 | ORAGAMI 21Z DAY 5 | ORAGAMI 21Z DAY 5 | ORAGAMI 21Z DAY 5 | CEMC LK WW #1 DAY 5 | CEMC LK WW #1 DAY 5 | CEMC LK WW #1 DAY 5 | BERRY HB DAY 5 | BERRY HB DAY 5 | BERRY HB DAY 5 | BERRY HB DAY 5 | BERRY HB DAY 5 | CHEV BEECROFT PIPE DAY 11 | CHEV BEECROFT PIPE DAY 11 | CHEV BEECROFT PIPE DAY 11 | VALLEY WATER MCK PONDS DAY 11 | VALLEY WATER MCK PONDS DAY 11 | VALLEY WATER MCK PONDS DAY 11 | CYM WATER LINE DAY 11 | CYM WATER LINE DAY 11 | CYM WATER LINE DAY 11 | CYM WATER LINE DAY 11 | CYM WATER LINE DAY 11 | CYM WATER LINE DAY 11
2017-06-28 | BERRY MONITORING | BERRY MONITORING | BERRY MONITORING | HST set 1 DAY 11 | HST set 1 DAY 11 | HST set 1 DAY 11 | HST set 1 DAY 11 | HST set 1 DAY 12 | HST set 1 DAY 12 | [21 empty] | LH HZ AREA DAY 6 | LH HZ AREA DAY 6 | LH HZ AREA DAY 6 | CHEV CO 23D CEMC 2B 3B DAY 6 | CHEV CO 23D CEMC 2B 3B DAY 6 | CHEV CO 23D CEMC 2B 3B DAY 6 | CHEV CO 23D CEMC 2B 3B DAY 6 | CHEV CO 23D CEMC 2B 3B DAY 6 | ORAGAMI 21Z DAY 6 | ORAGAMI 21Z DAY 6 | ORAGAMI 21Z DAY 6 | CEMC LK WW #1 DAY 6 | CEMC LK WW #1 DAY 6 | CEMC LK WW #1 DAY 6 | BERRY HB DAY 6 | BERRY HB DAY 6 | BERRY HB DAY 6 | BERRY HB DAY 6 | BERRY HB DAY 6 | CHEV BEECROFT PIPE DAY 12 | CHEV BEECROFT PIPE DAY 12 | CHEV BEECROFT PIPE DAY 12 | VALLEY WATER MCK PONDS DAY 12 | VALLEY WATER MCK PONDS DAY 12 | VALLEY WATER MCK PONDS DAY 12 | CYM WATER LINE DAY 12 | CYM WATER LINE DAY 12 | CYM WATER LINE DAY 12 | CYM WATER LINE DAY 12 | CYM WATER LINE DAY 12 | CYM WATER LINE DAY 12
2017-06-29 | BERRY MONITORING | BERRY MONITORING | BERRY MONITORING | HST set 1 DAY 12 | HST set 1 DAY 12 | HST set 1 DAY 12 | HST set 1 DAY 12 | HST set 1 DAY 10 | HST set 1 DAY 10 | [21 empty] | LH HZ AREA DAY 7 | LH HZ AREA DAY 7 | LH HZ AREA DAY 7 | CHEV CO 23D CEMC 2B 3B DAY 7 | CHEV CO 23D CEMC 2B 3B DAY 7 | CHEV CO 23D CEMC 2B 3B DAY 7 | CHEV CO 23D CEMC 2B 3B DAY 7 | CHEV CO 23D CEMC 2B 3B DAY 7 | ORAGAMI 21Z DAY 7 | ORAGAMI 21Z DAY 7 | ORAGAMI 21Z DAY 7 | CEMC LK WW #1 DAY 7 | CEMC LK WW #1 DAY 7 | CEMC LK WW #1 DAY 7 | BERRY HB DAY 7 | BERRY HB DAY 7 | BERRY HB DAY 7 | BERRY HB DAY 7 | BERRY HB DAY 7
2017-06-30 | [30 empty] | LH HZ AREA DAY 8 | LH HZ AREA DAY 8 | LH HZ AREA DAY 8 | CHEV CO 23D CEMC 2B 3B DAY 8 | CHEV CO 23D CEMC 2B 3B DAY 8 | CHEV CO 23D CEMC 2B 3B DAY 8 | CHEV CO 23D CEMC 2B 3B DAY 8 | CHEV CO 23D CEMC 2B 3B DAY 8 | ORAGAMI 21Z DAY 8 | ORAGAMI 21Z DAY 8 | ORAGAMI 21Z DAY 8 | CEMC LK WW #1 DAY 8 | CEMC LK WW #1 DAY 8 | CEMC LK WW #1 DAY 8 | BERRY HB DAY 8 | BERRY HB DAY 8 | BERRY HB DAY 8 | BERRY HB DAY 8 | BERRY HB DAY 8
2017-07-01 | [30 empty] | LH HZ AREA DAY 9 | LH HZ AREA DAY 9 | LH HZ AREA DAY 9 | CHEV CO 23D CEMC 2B 3B DAY 9 | CHEV CO 23D CEMC 2B 3B DAY 9 | CHEV CO 23D CEMC 2B 3B DAY 9 | CHEV CO 23D CEMC 2B 3B DAY 9 | CHEV CO 23D CEMC 2B 3B DAY 9 | ORAGAMI 21Z DAY 9 | ORAGAMI 21Z DAY 9 | ORAGAMI 21Z DAY 9 | CEMC LK WW #1 DAY 9 | CEMC LK WW #1 DAY 9 | CEMC LK WW #1 DAY 9 | BERRY HB DAY 9 | BERRY HB DAY 9 | BERRY HB DAY 9 | BERRY HB DAY 9 | BERRY HB DAY 9
2017-07-02 | [30 empty] | LH HZ AREA DAY 10 | LH HZ AREA DAY 10 | LH HZ AREA DAY 10 | CHEV CO 23D CEMC 2B 3B DAY 10 | CHEV CO 23D CEMC 2B 3B DAY 10 | CHEV CO 23D CEMC 2B 3B DAY 10 | CHEV CO 23D CEMC 2B 3B DAY 10 | CHEV CO 23D CEMC 2B 3B DAY 10 | ORAGAMI 21Z DAY 10 | ORAGAMI 21Z DAY 10 | ORAGAMI 21Z DAY 10 | CEMC LK WW #1 DAY 10 | CEMC LK WW #1 DAY 10 | CEMC LK WW #1 DAY 10 | BERRY HB DAY 10 | BERRY HB DAY 10 | BERRY HB DAY 10 | BERRY HB DAY 10 | BERRY HB DAY 10
2017-07-03 | BERRY MONITORING | BERRY MONITORING |  | BERRY MONITORING | HST SET 2 DAY 9 | HST SET 2 DAY 9 | HST SET 2 DAY 9 | HST SET 2 DAY 9 | HST SET 2 DAY 9 | HST SET 2 DAY 10 | [20 empty] | LH HZ AREA DAY 11 | LH HZ AREA DAY 11 | LH HZ AREA DAY 11 | CHEV CO 23D CEMC 2B 3B DAY 11 | CHEV CO 23D CEMC 2B 3B DAY 11 | CHEV CO 23D CEMC 2B 3B DAY 11 | CHEV CO 23D CEMC 2B 3B DAY 11 | CHEV CO 23D CEMC 2B 3B DAY 11 | ORAGAMI 21Z DAY 11 | ORAGAMI 21Z DAY 11 | ORAGAMI 21Z DAY 11 | CEMC LK WW #1 DAY 11 | CEMC LK WW #1 DAY 11 | CEMC LK WW #1 DAY 11 | BERRY HB DAY 11 | BERRY HB DAY 11 | BERRY HB DAY 11 | BERRY HB DAY 11 | BERRY HB DAY 11
2017-07-04 | BERRY MONITORING | BERRY MONITORING |  | BERRY MONITORING | HST SET 2 DAY 10 | HST SET 2 DAY 10 | HST SET 2 DAY 10 | HST SET 2 DAY 10 | HST SET 2 DAY 10 | HST SET 2 DAY 11 | [20 empty] | LH HZ AREA DAY 12 | LH HZ AREA DAY 12 | LH HZ AREA DAY 12 | CHEV CO 23D CEMC 2B 3B DAY 12 | CHEV CO 23D CEMC 2B 3B DAY 12 | CHEV CO 23D CEMC 2B 3B DAY 12 | CHEV CO 23D CEMC 2B 3B DAY 12 | CHEV CO 23D CEMC 2B 3B DAY 12 | ORAGAMI 21Z DAY 12 | ORAGAMI 21Z DAY 12 | ORAGAMI 21Z DAY 12 | CEMC LK WW #1 DAY 12 | CEMC LK WW #1 DAY 12 | CEMC LK WW #1 DAY 12 | BERRY HB DAY 12 | BERRY HB DAY 12 | BERRY HB DAY 12 | BERRY HB DAY 12 | BERRY HB DAY 12
2017-07-05 | BERRY MONITORING | BERRY MONITORING |  | BERRY MONITORING | HST SET 2 DAY 11 | HST SET 2 DAY 11 | HST SET 2 DAY 11 | HST SET 2 DAY 11 | HST SET 2 DAY 11 | HST SET 2 DAY 12 | [20 empty] | CEMC 7-3A & CHEV 1Y SSP SW DAY 5 | CEMC 7-3A & CHEV 1Y SSP SW DAY 5 | CEMC 7-3A & CHEV 1Y SSP SW DAY 5 | CHEV Stevens & MCK MT DAY 5 | CHEV Stevens & MCK MT DAY 5 | CHEV Stevens & MCK MT DAY 5 | CHEV Stevens & MCK MT DAY 5
2017-07-06 | BERRY MONITORING | BERRY MONITORING |  | BERRY MONITORING | HST SET 2 DAY 12 | HST SET 2 DAY 12 | HST SET 2 DAY 12 | HST SET 2 DAY 12 | HST SET 2 DAY 12 | HST SET 2 DAY 9 | [20 empty] | CEMC 7-3A & CHEV 1Y SSP SW DAY 6 | CEMC 7-3A & CHEV 1Y SSP SW DAY 6 | CEMC 7-3A & CHEV 1Y SSP SW DAY 6 | CHEV Stevens & MCK MT DAY 6 | CHEV Stevens & MCK MT DAY 6 | CHEV Stevens & MCK MT DAY 6 | CHEV Stevens & MCK MT DAY 6
2017-07-07 | [30 empty] | CEMC 7-3A & CHEV 1Y SSP SW DAY 7 | CEMC 7-3A & CHEV 1Y SSP SW DAY 7 | CEMC 7-3A & CHEV 1Y SSP SW DAY 7 | CHEV Stevens & MCK MT DAY 7 | CHEV Stevens & MCK MT DAY 7 | CHEV Stevens & MCK MT DAY 7 | CHEV Stevens & MCK MT DAY 7
2017-07-08 | [30 empty] | CEMC 7-3A & CHEV 1Y SSP SW DAY 8 | CEMC 7-3A & CHEV 1Y SSP SW DAY 8 | CEMC 7-3A & CHEV 1Y SSP SW DAY 8 | CHEV Stevens & MCK MT DAY 8 | CHEV Stevens & MCK MT DAY 8 | CHEV Stevens & MCK MT DAY 8 | CHEV Stevens & MCK MT DAY 8
2017-07-09 | [30 empty] | CEMC 7-3A & CHEV 1Y SSP SW DAY 9 | CEMC 7-3A & CHEV 1Y SSP SW DAY 9 | CEMC 7-3A & CHEV 1Y SSP SW DAY 9 | CHEV Stevens & MCK MT DAY 9 | CHEV Stevens & MCK MT DAY 9 | CHEV Stevens & MCK MT DAY 9 | CHEV Stevens & MCK MT DAY 9
2017-07-10 | BERRY MONITORING | BERRY MONITORING |  | BERRY MONITORING | [26 empty] | CEMC 7-3A & CHEV 1Y SSP SW DAY 10 | CEMC 7-3A & CHEV 1Y SSP SW DAY 10 | CEMC 7-3A & CHEV 1Y SSP SW DAY 10 | CHEV Stevens & MCK MT DAY 10 | CHEV Stevens & MCK MT DAY 10 | CHEV Stevens & MCK MT DAY 10 | CHEV Stevens & MCK MT DAY 10
2017-07-11 | BERRY MONITORING | BERRY MONITORING |  | BERRY MONITORING | [26 empty] | CEMC 7-3A & CHEV 1Y SSP SW DAY 11 | CEMC 7-3A & CHEV 1Y SSP SW DAY 11 | CEMC 7-3A & CHEV 1Y SSP SW DAY 11 | CHEV Stevens & MCK MT DAY 11 | CHEV Stevens & MCK MT DAY 11 | CHEV Stevens & MCK MT DAY 11 | CHEV Stevens & MCK MT DAY 11
2017-07-12 | BERRY MONITORING | BERRY MONITORING |  | BERRY MONITORING | [26 empty] | CEMC 7-3A & CHEV 1Y SSP SW DAY 12 | CEMC 7-3A & CHEV 1Y SSP SW DAY 12 | CEMC 7-3A & CHEV 1Y SSP SW DAY 12 | CHEV Stevens & MCK MT DAY 12 | CHEV Stevens & MCK MT DAY 12 | CHEV Stevens & MCK MT DAY 12 | CHEV Stevens & MCK MT DAY 12
2017-07-13 | BERRY MONITORING | BERRY MONITORING |  | BERRY MONITORING
2017-07-14
2017-07-15
[33 empty] | ARCADIS Midway-Temblor DAY 1 | ARCADIS Midway-Temblor DAY 1 | ARCADIS Midway-Temblor DAY 1 |  | ARCADIS Vedder Tap DAY 1 | ARCADIS Vedder Tap DAY 1 | ARCADIS Vedder Tap DAY 1 |  | ARCADIS Belridge Tap DAY 1 | ARCADIS Belridge Tap DAY 1
[33 empty] | ARCADIS Midway-Temblor DAY 2 | ARCADIS Midway-Temblor DAY 2 | ARCADIS Midway-Temblor DAY 2 |  | ARCADIS Vedder Tap DAY 2 | ARCADIS Vedder Tap DAY 2 | ARCADIS Vedder Tap DAY 2 |  | ARCADIS Belridge Tap DAY 2 | ARCADIS Belridge Tap DAY 2
[33 empty] | ARCADIS Midway-Temblor DAY 3 | ARCADIS Midway-Temblor DAY 3 | ARCADIS Midway-Temblor DAY 3 |  | ARCADIS Vedder Tap DAY 3 | ARCADIS Vedder Tap DAY 3 | ARCADIS Vedder Tap DAY 3 |  | ARCADIS Belridge Tap DAY 3 | ARCADIS Belridge Tap DAY 3
[33 empty] | ARCADIS Midway-Temblor DAY 4 | ARCADIS Midway-Temblor DAY 4 | ARCADIS Midway-Temblor DAY 4 |  | ARCADIS Vedder Tap DAY 4 | ARCADIS Vedder Tap DAY 4 | ARCADIS Vedder Tap DAY 4 |  | ARCADIS Belridge Tap DAY 4 | ARCADIS Belridge Tap DAY 4
[33 empty] | ARCADIS Midway-Temblor DAY 5 | ARCADIS Midway-Temblor DAY 5 | ARCADIS Midway-Temblor DAY 5 |  | ARCADIS Vedder Tap DAY 5 | ARCADIS Vedder Tap DAY 5 | ARCADIS Vedder Tap DAY 5 |  | ARCADIS Belridge Tap DAY 5 | ARCADIS Belridge Tap DAY 5
[33 empty] | ARCADIS Midway-Temblor DAY 6 | ARCADIS Midway-Temblor DAY 6 | ARCADIS Midway-Temblor DAY 6 |  | ARCADIS Vedder Tap DAY 6 | ARCADIS Vedder Tap DAY 6 | ARCADIS Vedder Tap DAY 6 |  | ARCADIS Belridge Tap DAY 6 | ARCADIS Belridge Tap DAY 6
[33 empty] | ARCADIS Fellows-Taft DAY 1 | ARCADIS Fellows-Taft DAY 1 | ARCADIS Fellows-Taft DAY 1 |  | ARCADIS Tupman-Norco Tap DAY 1 | ARCADIS Tupman-Norco Tap DAY 1 | ARCADIS Tupman-Norco Tap DAY 1 |  | ARCADIS Fellows-Midsun DAY 1 | ARCADIS Fellows-Midsun DAY 1 | ARCADIS Fellows-Midsun DAY 1
[33 empty] | ARCADIS Fellows-Taft DAY 2 | ARCADIS Fellows-Taft DAY 2 | ARCADIS Fellows-Taft DAY 2 |  | ARCADIS Tupman-Norco Tap DAY 2 | ARCADIS Tupman-Norco Tap DAY 2 | ARCADIS Tupman-Norco Tap DAY 2 |  | ARCADIS Fellows-Midsun DAY 2 | ARCADIS Fellows-Midsun DAY 2 | ARCADIS Fellows-Midsun DAY 2
[33 empty] | ARCADIS Fellows-Taft DAY 3 | ARCADIS Fellows-Taft DAY 3 | ARCADIS Fellows-Taft DAY 3 |  | ARCADIS Tupman-Norco Tap DAY 3 | ARCADIS Tupman-Norco Tap DAY 3 | ARCADIS Tupman-Norco Tap DAY 3 |  | ARCADIS Fellows-Midsun DAY 3 | ARCADIS Fellows-Midsun DAY 3 | ARCADIS Fellows-Midsun DAY 3
[33 empty] | ARCADIS Fellows-Taft DAY 4 | ARCADIS Fellows-Taft DAY 4 | ARCADIS Fellows-Taft DAY 4 |  | ARCADIS Tupman-Norco Tap DAY 4 | ARCADIS Tupman-Norco Tap DAY 4 | ARCADIS Tupman-Norco Tap DAY 4 |  | ARCADIS Fellows-Midsun DAY 4 | ARCADIS Fellows-Midsun DAY 4 | ARCADIS Fellows-Midsun DAY 4
[33 empty] | ARCADIS Fellows-Taft DAY 5 | ARCADIS Fellows-Taft DAY 5 | ARCADIS Fellows-Taft DAY 5 |  | ARCADIS Tupman-Norco Tap DAY 5 | ARCADIS Tupman-Norco Tap DAY 5 | ARCADIS Tupman-Norco Tap DAY 5 |  | ARCADIS Fellows-Midsun DAY 5 | ARCADIS Fellows-Midsun DAY 5 | ARCADIS Fellows-Midsun DAY 5
[33 empty] | ARCADIS Fellows-Taft DAY 6 | ARCADIS Fellows-Taft DAY 6 | ARCADIS Fellows-Taft DAY 6 |  | ARCADIS Tupman-Norco Tap DAY 6 | ARCADIS Tupman-Norco Tap DAY 6 | ARCADIS Tupman-Norco Tap DAY 6 |  | ARCADIS Fellows-Midsun DAY 6 | ARCADIS Fellows-Midsun DAY 6 | ARCADIS Fellows-Midsun DAY 6
Note on AI58: JayAnna Miller: after july 7
Note on AK58: JayAnna Miller: after july 9
Note on AL58: JayAnna Miller: after june 21
Note on AP58: JayAnna Miller: after july 9
Note on AS58: JayAnna Miller: after june 28
Note on AT58: JayAnna Miller: after june 20
Note on AG66: JayAnna Miller: after june 30
Note on AK66: JayAnna Miller: after july 9
Note on AN66: JayAnna Miller: after july 9
Note on AS66: JayAnna Miller: after june 28
Note on AW66: JayAnna Miller: after july 8
Note on AG74: JayAnna Miller: after june 30
Note on AK74: JayAnna Miller: after july 6
Note on AL74: JayAnna Miller: after june 25
Note on AP74: JayAnna Miller: after july 7
Note on AR74: JayAnna Miller: after june 25
Note on AS74: JayAnna Miller: after june 29
Note on AV74: JayAnna Miller: after june 8
Note on AY74: JayAnna Miller: after june 28
Note on AQ79: JayAnna Miller: after july 6
Note on AJ82: JayAnna Miller: after june 23
Note on AT82: JayAnna Miller: after july 9
Note on AY82: JayAnna Miller: after july 6
Note on AG90: JayAnna Miller: after june 27
Note on AM90: JayAnna Miller: after july 10

## Sheet3
Problems | Solution
O-P N & S not paired w Trap & Pan on 5/7 & 5/10 | Trap & Pan surveyed on 5/11 and 5/12 alone
8S was not completed on 5/11. Transects 1-4 (North) skipped due to down team member | Surveyed with CHEV 30D & 2F on 5/22
SSM 687,8,12 not paired with Temblor Poles on 5/3. | SSM 687,8,12 surveyed alone on 5/12
CHEV HILL N&S not paired with CHEV HILL N/S Add On (5/23 - 5/26) | Add 2 person, 4 consec day survey separate at some point. Pair w/ Chev Hill N/S after that
CHEV 7S West did not finish last transect by 2pm on | last transect was picked up on 6/14
SEC 11&13 DID NOT FINISH WEST SECTION ON 6/4 | SEC 11 WEST ONLY 4 PERSON SURVEY ON 6/6
25 HILL S ON 5/23 DID NOT FINISH BEFORE 2PM | ASHLEIGH WILL ASK ABOUT ADDITIONAL SURVEY DAY NEEDED?
CEMC 6SF, 7S, D-06 FIRST 4 NOT COMPLETED BY 6/14 | FIRST 4 COMPLETED (6/16 - 6/19). 30 DAY SPACING WILL NOT BE MET FOR CDFW PROTOCOL
7S north last down and back not completed on 6/18 due to rolled ankle. | last 6 transects completed on 6/21
O-P N & S ONLY completed on 6/17 | Trap & Pan completed by two separate crews following their regularly sheduled survey on 6/19
transect 40 on 25 Hill

## Sheet2
|  |  |  | 6 PEOPLE LEAD UNTIL MAY 14 | RAINEY (SOME), CODY (SOME)
COLIN CAN WORK WED & FRI
Arcadis, PG&E | Area, PIC (one of these people have to be on the crew)
Randi | Blaine
steve | Kim
jared | Spenc
ash | araceli
sab | Anastacia
erika | Sabrina
blaine
Tom
Garrett
donna
spenc
araceli
7 Day Streak
Name | Week
Steve | 4/30-5/6
Level 2- Lead |  |  | 28
Steve |  | Kaitlin c | Start 5/12
Jared |  | Molly | Start 6/1
ash |  | Brett | Start ~6/7
sab |  | Preston | Start Maybe May?
erika
blaine
garrett
donna
specn
sarah
Kayla
Araceli?
Rainey?
Cody-
Sam
Woody*(HSR)
Matt?
Tom
Molly (2?)